## Sheet1
SITE ID | NO OF SECTOR | BAND | CMP | Team | Current Status | LATITUDE | LONGITUDE | ALLOTMENT LOT | ALLOTMENT DATE | MATERIAL DISPATCHED DATE | INSTALLATION DATE | INTEGRATION DATE | ATP 11A DATE | ATP 11B & ATP 11C DATE
I-UE-LCKN-ENB-6056 | 1 | A6 I&C | Lucknow-2 | Shyam/Ram Prakash outsource | Done | 26.8541 | 80.9204 | Allotment- AIR01 | 2024-01-10 | 2024-01-10 | 2024-01-11 | 2024-01-11 | 2024-01-12 | 2024-01-25
I-UE-LCKN-ENB-6067 | 2 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8599 | 80.9067 | Allotment- AIR01 | 2024-01-10 | 2024-01-10 | 2024-01-11 | 2024-01-11 | 2024-01-13 | 2024-01-19
I-UE-LCKN-ENB-0438 | 3 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8595 | 80.9006 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-15 | 2024-01-15 | 2024-01-16 | 2024-01-23
I-UE-LCKN-ENB-6157 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8625 | 80.9091 | Allotment- AIR01 | 2024-01-10 | 2024-01-10 | 2024-01-12 | 2024-01-12 | 2024-01-12 | 2024-01-19
I-UE-LCKN-ENB-0029 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8786 | 80.8906 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2024-01-27
I-UE-LCKN-ENB-0063 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8401 | 80.8931 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-16 | 2024-01-16 | 2024-01-23 | 2024-01-27
I-UE-LCKN-ENB-0608 | 3 | A6 I&C | Lucknow-2 | Shyam/Ram Prakash outsource | Done | 26.8598 | 80.9108 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-17 | 2024-01-17 | 2024-01-18 | 2024-01-22
I-UE-LCKN-ENB-1445 | 2 | A6 I&C | Lucknow-2 | Ashish & team | Done | 26.8378 | 80.8531 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2023-02-02
I-UE-LCKN-ENB-6041 | 3 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8408 | 80.9322 | Allotment- AIR03 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-01-31 | 2024-02-15 | 2024-02-01
I-UE-LCKN-ENB-1738 | 1 | A6 I&C | Lucknow-2 | Shyam/Ram Prakash outsource | Done | 26.8559 | 80.9213 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-16 | 2024-01-16 | 2024-01-16 | 2024-01-22
I-UE-LCKN-ENB-0441 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8729 | 80.9083 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-17 | 2024-01-17 | 2024-01-17 | 2024-01-23
I-UE-LCKN-ENB-6107 | 2 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8545 | 80.9126 | Allotment- AIR01 | 2024-01-10 | 2024-01-10 | 2024-01-11 | 2024-01-19 | 2024-01-21 | 2023-02-02
I-UE-LCKN-ENB-6015 | 1 | A6 I&C | Lucknow-2 | Shyam/Ram Prakash outsource | Done | 26.8584 | 80.915 | Allotment- AIR01 | 2024-01-10 | 2024-01-10 | 2024-01-19 | 2024-01-19 | 2024-01-12 | 2024-01-20
I-UE-LCKN-ENB-1794 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.7905 | 80.9315 | Allotment- AIR01 | 2024-01-10 | 2024-01-10 | 2024-01-19 | 2024-01-19 | 2024-01-20 | 2024-01-22
I-UE-LCKN-ENB-0442 | 1 | A6 I&C | Lucknow-2 | ROHIT/Ashish & team | Done | 26.8667 | 80.8824 | Allotment- AIR02 | 2024-01-14 | 2024-01-14 | 2024-01-31 | 2024-01-31 | 2024-02-07 | 2024-02-01
I-UE-LCKN-ENB-0902 | 2 | A6 I&C | Lucknow-1 | Anil & team | Done | 26.8858 | 80.9242 | Allotment- AIR03 | 2024-01-30 | 2024-01-30 | 2024-01-31 | 2024-02-01 | 2024-02-01 | 2024-02-01
I-UE-LCKN-ENB-0520 | 1 | A6 I&C | Lucknow-1 | Harshit & team | Done | 26.8899 | 80.9198 | Allotment- AIR04 | 2024-02-03 | 2024-02-03 | 2024-02-05 | 2024-02-07 | 2024-02-09 | 2024-02-09
I-UE-LCKN-ENB-0558 | 1 | A6 I&C | Lucknow-1 | Anil & team | Done | 26.8919 | 80.9996 | Allotment- AIR04 | 2024-02-03 | 2024-02-03 | 2024-02-05 | 2024-02-05 | 2024-02-07 | 2024-02-16
I-UE-LCKN-ENB-1314 | 1 | A6 I&C | Lucknow-1 | Ashish & team | Done | 26.8937 | 81.0106 | Allotment- AIR04 | 2024-02-03 | 2024-02-03 | 2024-02-05 | 2024-02-05 | 2024-02-08 | 2024-02-08
I-UE-LCKN-ENB-0500 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.7816 | 80.9356 | Allotment- AIR04 | 2024-02-03 | 2024-02-03 | 2024-02-05 | 2024-02-07 | 2024-02-07 | 2024-02-08
I-UE-LCKN-ENB-0766 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.7837 | 80.9307 | Allotment- AIR04 | 2024-02-03 | 2024-02-03 | 2024-02-05 | 2024-02-05 | 2024-02-06 | 2024-02-06
I-UE-LCKN-ENB-8988 | 1 | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8259 | 80.8733 | Allotment- AIR04 | 2024-02-03 | 2024-02-03 | 2024-02-06 | 2024-02-06 | 2024-02-06 | 2024-02-23
I-UE-LCKN-ENB-1335 |  | A6 I&C | Lucknow-1 | Harshit & team | Done | 26.9158 | 80.9378 | Allotment- AIR05 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-09
I-UE-LCKN-ENB-8630 |  | A6 I&C | Lucknow-2 | Harshit & team |  | 26.8382 | 80.9505 | Allotment- AIR05 | 2024-02-06 | 2024-02-06 | 2024-02-08 | 2024-02-08 | 2024-02-08 | 2024-02-09
I-UE-LCKN-ENB-0704 |  | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.7977 | 80.8926 | Allotment- AIR05 | 2024-02-06 | 2024-02-06 | 2024-02-07 | 2024-02-07 | 2024-02-07 | 2024-02-08
I-UE-LCKN-ENB-8903 |  | A6 I&C | Lucknow-2 | Rohit & team | Done | 26.8361 | 80.8546 | Allotment- AIR05 | 2024-02-06 | 2024-02-06 | 2024-02-22 | 2024-02-22 | 2024-02-22 | 2024-02-23
I-UE-LCKN-ENB-0237 | 1 | A6 I&C | Lucknow-1 |  | MRN DONE | 26.9171 | 80.9671 | Allotment- AIR04 | 2024-02-03 | 2024-02-03
I-UE-LCKN-ENB-6075 | 2 | A6 I&C | Lucknow-2 |  | MRN DONE | 26.8008 | 80.8873 | Allotment- AIR03 | 2024-01-30 | 2024-01-30
I-UE-LCKN-ENB-0437 | 3 | A6 I&C | Lucknow-2 |  | MRN DONE | 26.8576 | 80.9064 | Allotment- AIR02 | 2024-01-14 | 2024-01-14
I-UE-SJPR-ENB-0094 | 3 | A6 I&C | Shahjahanpur | Nishant ref Shivam | Done | 27.8631 | 79.9101 | Allotment- AIR06 | 2024-04-27 | 2024-04-29 | 2024-05-02 | 2024-05-02 | 2024-05-02 | 2024-05-08