## AIR FIBER
SITE ID | PMP ID | Sector | NO OF SECTOR | BAND | JC NAME | CMP | Team | Plan Date | Current Status | LATITUDE | LONGITUDE | SITE TYPE | SITE IP | ACTIVITY | ACTIVITY CHANGES IF ANY | EXTRA MIN IF ANY | ALLOTMENT LOT | ALLOTMENT DATE | MATERIAL DISPATCHED DATE | INSTALLATION DATE | INTEGRATION DATE | ATP 11A DATE | ATP11C | ATP11C DONE BY | HOTO DATE | 11A SUBMISSION DATE | 11BC SUBMISSION DATE | HOTO SUBMISSION DATE | Material Need to MRN | EXTRA MIN (YES/NO) | MRN REQUIRED (YES/NO) | MRN FINALIZATION STATUS | REASON IF MRN PENDING | RECO STATUS | READY FOR BILLING OR NOT | REMARKS IF ANY | Digitcom Remark | POWER CABLE LENGTH | CPRI LENGTH | HARD CONDUIT LENGTH | SITE NAME | SITE ADDRESS | JIO Technician Name | Jio Technician Contact | Rigger Name | Rigger Contact | Superviser Name | Su[perviser Contact | MIN Location | MRN Location
I-RJ-GGPC-ENB-0012 | I-RJ-GGPC-PMP-0005 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Karan & team |  | Done | 26.5032 | 76.7112 | GBT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-14 | 2024-09-14 | 2024-09-20 | RAJKUMAR | 2024-09-17 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 85 | 0 | Mirjapur mode |  | HIMMAT SINGH GURJAR | 9571214999 | DILKUSH MEENA | 9414736021 |  |  | JLKD
I-RJ-GGPC-ENB-I001 | I-RJ-GGPC-PMP-0034 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Karan & team |  | Done | 26.4809 | 76.7402 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-18 | RAJKUMAR | 2024-09-20 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 85 | 0 | Near Balaji Temple |  | LAKHAN LAL MEENA | 6350491164 | DILKUSH MEENA | 9414736021 |  |  | JLKD
I-RJ-SMDP-ENB-9059 | I-RJ-SMDP-PMP-0041 | 1 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.9383 | 76.3749 | GBT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-16 | SANDEEP | 2024-09-24 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | 0 |  | SURENDRA BAIRWA | 6350491571 | DESHRAJ BAIRWA | 9001903735 |  |  | JLKD
I-RJ-GGPC-ENB-V001 | I-RJ-GGPC-PMP-0046 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Karan & team |  | Done | 26.4701 | 76.7242 | GBT | ATC | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-16 | 2024-09-16 | 2024-09-17 | 2024-09-18 | RAJKUMAR | 2024-09-20 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 85 | 0 | Sindhi colony |  | PRAHLAD MEENA | 9602895557 | LUKMAN KHAN | 8209271082 |  |  | JLKD
I-RJ-MLRN-ENB-6003 | I-RJ-MLRN-PMP-0004 | 1/3 | 2 | A6 I&C | Gangapur | Kota | Karan & team |  | Done | 26.284 | 76.4708 | GBT | Rcom | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-17 | 2024-09-17 | 2024-09-19 | 2024-09-20 | RAJKUMAR | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | MALARNA DOONGAR |  | RAMESH CHANDRA MALI | 6377201510 | SAHIL KHAN | 9001903735 |  |  | JLKD
I-RJ-GGPC-ENB-I012 | I-RJ-GGPC-PMP-0043 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Rajkumar & team |  | Done | 26.4679 | 76.737 | GBT | Indus | A6 I&C , ATP11A & 11C | extra visit approved | 1 1G SFP MIN REQD, 1 FAULTY 1G SFP MRN REQD | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-17 | 2024-09-19 | 2024-09-20 | 2024-09-19 | RAJKUMAR | 2024-09-20 |  |  |  | 1 1G SFP MRN REQUIRED AGAINST FAULTY | NO | NO | NA |  |  | Ready |  | first day rajkumar installed 2 sec a6 on wrong sector | 150 | 105 | 0 | Mahu Kalan |  | LAKHAN LAL MEENA | 6350491164 | DILKUSH MEENA | 9414736021 |  |  | JLKD
I-RJ-CHTB-ENB-V002 | I-RJ-CHTB-PMP-0008 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.1817 | 76.0659 | GBT | ATC | A6 I&C , ATP11A & 11C | extra visit approved | 1 60M 1 5M CPRI MIN REQD AGAINST FAULTY | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-19 | 2024-09-19 | 2024-09-19 | 2024-09-19 | ANEESH | 2024-09-24 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 190 | 86 | Sarsoap |  | BRIJMOHAN | 6350491172 | POORAN VERMA | 7690881734 |  |  | JLKD
I-RJ-BMNW-ENB-6000 | I-RJ-BMNW-PMP-0001 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Karan & team |  | Done | 26.5571 | 76.5595 | GBT | Rcom | A6 I&C , ATP11A & 11C | extra visit approved | 6 10G SFP MIN, 6 1G SFP MRN REQD | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-19 | 2024-09-23 | 2024-09-23 | 2024-09-23 | RAJKUMAR | 2024-09-23 |  |  |  | 6 1G SFP MRN REQUIRED AGAINST WRONG MATERIAL | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | Bamanwas |  | PRAHLAD MEENA | 9602895557 | LUKMAN KHAN | 8209271082 |  |  | JLKD
I-RJ-CHBR-ENB-9032 | I-RJ-CHBR-PMP-0007 | 2/3 | 2 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 24.6213 | 76.7149 | GBT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-20 | 2024-09-20 | 2024-09-20 | 2024-09-20 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Chhipabarod |  | HARISH KUMAR JANGID | 6350491245 | CHATURBHUJ NAGAR | 6350491623 |  |  | JLKD
I-RJ-ATRU-ENB-I001 | I-RJ-ATRU-PMP-0010 | 1/2/3 | 3 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 24.8774 | 76.6693 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2024-09-22 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Ward No.1(Atru) |  | RAKESH GOUTAM | 6350491656 | PRAMOD KUMAR | 8000504389 |  |  | JLKD
I-RJ-BRNN-ENB-9021 | I-RJ-BRNN-PMP-0030 | 1 | 1 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 25.0496 | 76.4811 | GBT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2024-09-22 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Dhakad basti |  | RAVINDRA KUMAR CARPENTER | 9351228572 | VIKAS SUMAN | 6350491530 |  |  | JLKD
I-RJ-ANTA-ENB-I009 | I-RJ-ANTA-PMP-0007 | 1/2/3 | 3 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 25.1565 | 76.2993 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2024-09-22 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Ward No. 19 |  | MUKESH KUMAR NAGAR | 9950050888 | Bhagirath Ram | 6350491173 |  |  | JLKD
I-RJ-MNGO-ENB-I004 | I-RJ-MNGO-PMP-0011 | 2/3 | 2 | A6 I&C | Baran | Kota | Karan & team |  | Done | 25.4119 | 76.5422 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2024-09-23 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Bamori Kalan |  | NARENDRA SINGH PAL | 6350491230 | NARESH KUMAR | 6350491231 |  |  | JLKD
I-RJ-PIIS-ENB-I010 | I-RJ-PIIS-PMP-0016 | 1/2/3 | 3 | A6 I&C | Kota | Kota | Rajkumar & team |  | Done | 25.5374 | 76.3794 | GBT | Indus | A6 I&C , ATP11A & 11C | extra visit approved |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-23 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 110 | 0 | Main market(Itawa) |  | Nawal Singh | 6350491235 | NARESH KUMAR | 6350491231 |  |  | JLKD
I-RJ-MNGO-ENB-I005 | I-RJ-MNGO-PMP-0012 | 3 | 1 | A6 I&C | Baran | Kota | Karan & team |  | Done | 25.3458 | 76.3586 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-23 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Seeswali |  | NARENDRA SINGH PAL | 6350491230 | NARESH KUMAR | 6350491231 |  |  | JLKD
I-RJ-MNGO-ENB-9020 | I-RJ-MNGO-PMP-0006 | 2/3 | 2 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 25.342 | 76.3496 | GBT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-22 | 2024-09-22 | 2024-09-22 | 2024-09-23 | ANEESH | 2024-09-23 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Mangrol |  | NARENDRA SINGH PAL | 6350491230 | NARESH KUMAR | 6350491231 |  |  | JLKD
I-RJ-SMDP-ENB-0038 | I-RJ-SMDP-PMP-0019 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.9955 | 76.3839 | RTT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-15 | SANDEEP | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Ward No-31 |  | SURENDRA BAIRWA | 6350491571 | DESHRAJ BAIRWA | 9001903735 |  |  | JLKD
I-RJ-SMDP-ENB-0015 | I-RJ-SMDP-PMP-0010 | 2 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.9935 | 76.3856 | GBM | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-13 | 2024-09-13 | 2024-09-14 | 2024-09-15 | SANDEEP | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Near Police chowki |  | SURENDRA BAIRWA | 6350491571 | DESHRAJ BAIRWA | 9001903735 |  |  | JLKD
I-RJ-SMDP-ENB-6006 | I-RJ-SMDP-PMP-0030 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.9915 | 76.3833 | GBT | Rcom | A6 I&C , ATP11A & 11C | extra visit approved |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-14 | 2024-09-14 | 2024-09-14 | 2024-09-16 | SANDEEP | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 61 | Sawai Madhopur_2 |  | NARENDRA KUMAR BAIRWA | 8949151149 | DESHRAJ BAIRWA | 9001903735 |  |  | JLKD
I-RJ-SMDP-ENB-V002 | I-RJ-SMDP-PMP-0057 | 3 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.994 | 76.3347 | GBT | ATC | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-16 | SANDEEP | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Ricco colony, Khairda-01 |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 |  |  | JLKD
I-RJ-SMDP-ENB-V001 | I-RJ-SMDP-PMP-0056 | 2/3 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0166 | 76.3485 | GBT | ATC | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-16 | SANDEEP | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 80 | 80 | 0 | Bajaria |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 |  |  | JLKD
I-RJ-SMDP-ENB-V004 | I-RJ-SMDP-PMP-0059 | 1/3 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.124 | 76.466 | GBT | ATC | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR01 | 2024-09-11 | 2024-09-12 | 2024-09-16 | 2024-09-16 | 2024-09-16 | 2024-09-16 | SANDEEP | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Kundera |  | NARENDRA KUMAR BAIRWA | 8949151149 | DESHRAJ BAIRWA | 9001903735 |  |  | JLKD
I-RJ-SMDP-ENB-I002 | I-RJ-SMDP-PMP-0051 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Karan & team |  | Done | 26.0119 | 76.3572 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-09-21 | 2024-09-21 | 2024-09-21 | 2024-09-24 | ANEESH | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Ranthambhor Circle |  | MOHAMMED ARIF | 6350491165 | SAHIL KHAN | 9001903735 |  |  | JLKD
I-RJ-SMDP-ENB-I013 | I-RJ-SMDP-PMP-0054 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0003 | 76.337 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-24 | 2024-09-24 | 2024-09-24 | 2024-09-24 | ANEESH | 2024-09-25 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | Swaimodhopur-1 |  | NARENDRA KUMAR BAIRWA | 8949151149 | DESHRAJ BAIRWA | 9001903735 |  |  | JLKD
I-RJ-NOHR-ENB-I005 | I-RJ-NOHR-PMP-0022 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar |  |  | MRN Done | 29.1389 | 74.5942 | GBT | Indus | A6 I&C , ATP11A & 11C | OWNER ISSUE |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | NR | NR | NR | NR | NA | NR |  |  |  |  | NO | YES | FINALIZED |  |  | Ready |  |  | 0 | 0 | 0 | Birkali | [7 empty] | JLKD
I-RJ-NOHR-ENB-I014 | I-RJ-NOHR-PMP-0028 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.257 | 74.4091 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-24 | 2024-09-26 | 2024-10-02 | 2024-10-02 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | RAWATSAR_RAMPUR ROAD | [7 empty] | JLKD
I-RJ-TBBI-ENB-V001 | I-RJ-TBBI-PMP-0016 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 29.5552 | 74.5031 | GBT | ATC | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-25 | RAJKUMAR | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Tibbi | [7 empty] | JLKD
I-RJ-TBBI-ENB-I002 | I-RJ-TBBI-PMP-0013 | 1 | 1 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.6528 | 74.499 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-25 | RAJKUMAR | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | 4 FTP | [7 empty] | JLKD
I-RJ-INDA-ENB-9025 | I-RJ-INDA-PMP-0009 | 1 | 1 | A6 I&C | Bundi | Kota | Aneesh & team |  | Done | 25.6378 | 76.1918 | GBT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-25 | ANEESH | 2024-09-30 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Indergarh | [7 empty] | JLKD
I-RJ-SNRA-ENB-9002 | I-RJ-SNRA-PMP-0002 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.7855 | 74.4621 | RTT | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-25 | 2024-09-25 | 2024-09-25 | 2024-09-29 | SANDEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | SANGARIA | [7 empty] | JLKD
I-RJ-BOLI-ENB-A001 | I-RJ-BOLI-PMP-0005 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.3299 | 76.2271 | GBT | ATC | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-27 | ANEESH | 2024-09-30 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Kotpada | [7 empty] | JLKD
I-RJ-HMGR-ENB-6005 | I-RJ-HMGR-PMP-0031 | 1/3 | 2 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.6437 | 74.2207 | GBT | RCOM | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | RAJKUMAR | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | 7 JRK | [7 empty] | JLKD
I-RJ-HMGR-ENB-S001 | I-RJ-HMGR-PMP-0065 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 29.6825 | 74.162 | GBT | ASCEND | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-27 | RAJKUMAR | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | 28 LLW[VILLAGE] | [7 empty] | JLKD
I-RJ-HMGR-ENB-I004 | I-RJ-HMGR-PMP-0057 | 2/3 | 2 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.6075 | 74.2898 | GBT | INDUS | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-09-30 | SANDEEP | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 0 | Near Hotel Narang | [7 empty] | JLKD
I-RJ-SNRA-ENB-I011 | I-RJ-SNRA-PMP-0019 | 1 | 1 | A6 I&C | Nohar | Ganganagar | Rajkumar & team |  | Done | 29.7967 | 74.461 | GBM | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2024-09-29 | SANDEEP | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | BusStSangaria_A |  | Anil Kumar | 9587718040 | RAKESH SNRA | 9660263890 | VACANT HMGR | 0 | JLKD
I-RJ-NUKR-ENB-6000 | I-RJ-NUKR-PMP-0001 | 1/2 | 2 | A6 I&C | Nohar | Ganganagar | Rajkumar & team |  | Done | 29.8883 | 74.3661 | GBT | Rcom | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2024-09-30 | ANEESH | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | 3 PTP (NUKERA) |  | Amar Chand | 6350492193 | RAKESH SNRA | 9660263890 | VACANT HMGR | 0 | JLKD
I-RJ-SNRA-ENB-I007 | I-RJ-SNRA-PMP-0016 | 2 | 1 | A6 I&C | Nohar | Ganganagar | Karan & team |  | Done | 29.9044 | 74.4138 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2024-09-30 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | 1 PTP (SANTPURA) |  | Anil Kumar | 9587718040 | RAKESH SNRA | 9660263890 | VACANT HMGR | 0 | JLKD
I-RJ-GGPC-ENB-0033 | I-RJ-GGPC-PMP-0014 | 2 | 1 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4779 | 76.7302 | GBM | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2024-09-28 | ANEESH | 2024-09-30 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Madhopur;Raj |  | PRAHLAD MEENA | 9602895557 | LUKMAN KHAN | 8209271082 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-GGPC-ENB-0019 | I-RJ-GGPC-PMP-0009 | 3 | 1 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4807 | 76.7188 | GBM | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2024-09-28 | ANEESH | 2024-09-30 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Sitla Mata Road |  | HIMMAT SINGH GURJAR | 9783773210 | SOMENT VAISHNAV | 8824273976 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-HIRZ-ENB-6000 | I-RJ-HIRZ-PMP-0001 | 1/2/3 | 3 | A6 I&C | Nohar | Ganganagar | Karan & team |  | Done | 29.9233 | 74.4814 | GBT | Rcom | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2024-09-29 | SANDEEP | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | 2 STP (HARIPURA) |  | Amar Chand | 6350492193 | RAKESH SNRA | 9660263890 | VACANT HMGR | 0 | JLKD
I-RJ-DBNH-ENB-6000 | I-RJ-DBNH-PMP-0001 | 1/3 | 2 | A6 I&C | Nohar | Ganganagar | Karan & team |  | Done | 29.8761 | 74.5088 | GBT | Rcom | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2024-09-30 | SANDEEP | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | 7 BGP-A |  | Amar Chand | 6350492193 | RAKESH SNRA | 9660263890 | VACANT HMGR | 0 | JLKD
I-RJ-KWII-ENB-I001 | I-RJ-KWII-PMP-0002 | 2/3 | 2 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 24.7689 | 76.7339 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-29 | 2024-09-29 | 2024-09-29 | 2024-09-30 | ANEESH | 2024-10-01 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Salpur |  | RAKESH GOUTAM | 6350491656 | PRAMOD KUMAR | 8000504389 | BRIJESH SEN | 9636956881 | JLKD
I-RJ-CBRA-ENB-9033 | I-RJ-CBRA-PMP-0007 | 1/2/3 | 3 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 24.6686 | 76.8412 | GBM | Own Built | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | ANEESH | 2024-10-01 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Nagar Palika Bus Stand | [7 empty] | JLKD
I-RJ-CBRA-ENB-S001 | I-RJ-CBRA-PMP-0016 | 1/2 | 2 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 24.6646 | 76.8467 | GBT | ASCEND | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-09-30 | ANEESH | 2024-10-01 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 0 | 0 | [7 empty] | JLKD
I-RJ-GGPC-ENB-V002 | I-RJ-GGPC-PMP-0047 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.5665 | 76.887 | GBT | ATC | A6 I&C , ATP11A & 11C | extra visit approved |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-10-01 | ANEESH/ADDITIONAL VISIT NEED TO CLAIM | 2024-09-30 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Wazirpur_Gangapur | [7 empty] | JLKD
I-RJ-PLBG-ENB-A002 | I-RJ-PLBG-PMP-0020 | 2 | 1 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.3872 | 73.8783 | GBT | ATC | A6 I&C , ATP11A & 11C | extra visit approved |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-30 | 2024-09-30 | 2024-09-30 | 2024-10-01 | SANDEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Suratgarh Cantt | [7 empty] | JLKD
I-RJ-SRTG-ENB-I001 | I-RJ-SRTG-PMP-0002 | 1/2/3 | 3 | A6 I&C | Nohar | Ganganagar | Rajkumar & team |  | Done | 29.6297 | 74.05 | GBM | Indus | A6 I&C , ATP11A & 11C | extra visit approved |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-10-01 | SANDEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | GOLUWALA_Rel |  | DEEP CHAND | 9680768182 | Sandeep Kumar Goluwala | 6350491320 | VACANT HMGR | 0 | JLKD
I-RJ-SNRA-ENB-I008 | I-RJ-SNRA-PMP-0017 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 29.7924 | 74.4649 | RT Tower | Indus | A6 I&C , ATP11A & 11C | extra visit approved | 30m 2 cpri min, 5m 2 cpri mrn reqd | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-09-29 | SANDEEP | 2024-10-11 |  |  |  | 2 5M CPRI MRN REQUIRED | NO | NO | NA |  |  | Ready |  | 30m cpri installed by karan | 90 | 90 | 0 | BusStSangaria_infill | [7 empty] | JLKD
I-RJ-SNRA-ENB-6001 | I-RJ-SNRA-PMP-0001 | 3 | 1 | A6 I&C | Nohar | Ganganagar | Karan & team |  | Done | 29.7952 | 74.4661 | GBT | Rcom | A6 I&C , ATP11A & 11C | extra visit approved |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-28 | 2024-09-28 | 2024-09-28 | 2024-10-02 | SANDEEP | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Sangaria |  | Amar Chand | 6350492193 | RAKESH SNRA | 9660263890 | VACANT HMGR | 0 | JLKD
I-RJ-SNRA-ENB-V001 | I-RJ-SNRA-PMP-0020 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.7476 | 74.2751 | GBT | ATC | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-09-26 | 2024-09-26 | 2024-09-26 | 2024-10-02 | SANDEEP | 2024-10-11 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | 12 DLP | [7 empty] | JLKD
I-RJ-SNRA-ENB-I001 | I-RJ-SNRA-PMP-0013 | 3 | 1 | A6 I&C | Nohar | Ganganagar | Rajkumar & team |  | Done | 29.8359 | 74.3496 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-09-29 | 2024-09-30 | 2024-10-02 | 2024-10-02 | SANDEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Jatwala Sikhan |  | Anil Kumar | 9587718040 | RAKESH SNRA | 9660263890 | VACANT HMGR | 0 | JLKD
I-RJ-NHRE-ENB-S001 | I-RJ-NHRE-PMP-0042 | 2 | 1 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 29.2365 | 74.7405 | GBT | ASCEND | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-10-03 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | BHOOKAR KA BARANI | [7 empty] | JLKD
I-RJ-MSNA-ENB-9002 | I-RJ-MSNA-PMP-0002 | 1/3 | 2 | A6 I&C | Nohar | Ganganagar | Karan & team |  | Done | 29.3382 | 74.8989 | GBT | Rcom | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR04 | 2024-09-26 | 2024-09-26 | 2024-10-03 | 2024-10-03 | 2024-10-03 | 2024-10-03 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | V.P.O-Phephana; Tehsil-Nohar; Distt-Hanumangarh (Raj) |  | AJAY SINGH | 9079000357 | IRFAN KHAN | 7568683286 | AMIT KUMAR | 7597389705 | JLKD
I-RJ-BDRA-ENB-I016 | I-RJ-BDRA-PMP-0022 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 29.096 | 75.1671 | GBT | Indus | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR03 | 2024-09-23 | 2024-09-23 | 2024-10-04 | 2024-10-04 | 2024-10-04 | 2024-10-04 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Haatipura Bas | [7 empty] | JLKD
I-RJ-KHDR-ENB-V001 | I-RJ-KHDR-PMP-0007 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.9048 | 76.505 | GBT | ATC | A6 I&C , ATP11A & 11C | extra visit approved |  | Allotment- AIR02 | 2024-09-17 | 2024-09-18 | 2024-10-07 | 2024-10-07 | 2024-10-07 | 2024-10-07 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Bharawanda Khurd |  | HARIMOHAN MEENA | 6350491176 | ANIL KUMAR BAIRWA | 6350491665 |  |  | JLKD
I-RJ-BDRA-ENB-6007 | I-RJ-BDRA-PMP-0005 | 1/3 | 2 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 28.9615 | 74.9581 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Kunji |  | SHER SINGH | 9887604383 | Biram Kumar | 82901 49216 | AMIT KUMAR | 7597389705 | JLKD
I-RJ-NHRE-ENB-6002 | I-RJ-NHRE-PMP-0003 | 2 | 1 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 28.9853 | 74.834 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-09 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Meghana |  | RAKESH BENIWAL | 9928877790 | JOGENDER | 8209735796 | AMIT KUMAR | 7597389705 | JLKD
I-RJ-NHRE-ENB-9049 | I-RJ-NHRE-PMP-0017 | 1 | 1 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.1188 | 74.7701 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-09 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Dhani Saharanan |  | RAKESH BENIWAL | 9928877790 | IRFAN KHAN | 7568683286 | AMIT KUMAR | 7597389705 | JLKD
I-RJ-MSNA-ENB-9002 | I-RJ-MSNA-PMP-0002 | 2 | 2 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 29.3382 | 74.8989 | GBT | Kadevi-Hybrid | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-09 | RAJKUMAR | 2024-10-16 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | V.P.O-Phephana; Tehsil-Nohar; Distt-Hanumangarh (Raj) |  | AJAY SINGH | 9079000357 | IRFAN KHAN | 7568683286 | AMIT KUMAR | 7597389705 | JLKD
I-RJ-JLWR-ENB-9007 | I-RJ-JLWR-PMP-0009 | 1/2/3 | 3 | A6 I&C | Jhalawar | Kota | Aneesh & team |  | Done | 24.5776 | 76.1764 | GBT | Kadevi | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-08 | 2024-10-08 | 2024-10-08 | 2024-10-08 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Khandiya Colony |  | VIKAS PARETA | 6350491269 | GIRIRAJ VERMA | 8003106045 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-JLWR-ENB-9000 | I-RJ-JLWR-PMP-0008 | 3 | 1 | A6 I&C | Jhalawar | Kota | Aneesh & team |  | Done | 24.5891 | 76.1688 | GBM | 25 M GBM-Old | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-09 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Jhalawar Bus Stand and DWS |  | VIKAS PARETA | 6350491269 | GIRIRAJ VERMA | 8003106045 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-JLWR-ENB-6003 | I-RJ-JLWR-PMP-0003 | 1/2/3 | 3 | A6 I&C | Jhalawar | Kota | Aneesh & team |  | Done | 24.5953 | 76.1666 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-10 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 54 | Jhalawar |  | Ram Kumar Tibtiya | 9664032575 | GIRIRAJ VERMA | 8003106045 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-JLWR-ENB-9036 | I-RJ-JLWR-PMP-0014 | 1/3 | 2 | A6 I&C | Jhalawar | Kota | Aneesh & team |  | Done | 24.5961 | 76.1387 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-10 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | 0 |  | KK SHARMA | 9950964563 | RAKESH KUMAR RATHOR | 8003106045 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-HMGR-ENB-I017 | I-RJ-HMGR-PMP-0061 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Karan & team |  | Done | 29.5752 | 74.3361 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-10 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 3 | Indra Chowk(Hanumangarh) |  | PRAVEEN KUMAR | 8005913202 | RAKESH KUMAR HMGR | 8094115268 | VACANT HMGR | 0 | JLKD
I-RJ-HMGR-ENB-6001 | I-RJ-HMGR-PMP-0027 | 1/2 | 2 | A6 I&C | Hanumangarh | Ganganagar | Rajkumar & team |  | Done | 29.381 | 74.2797 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-10 | 2024-10-10 | 2024-10-10 | 2024-10-10 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | 3 C |  | HARSH KUMAR | 7976229390 | HANUMAN PARSAD | 9664048710 | AMIT KUMAR | 7597389705 | JLKD
I-RJ-MHAR-ENB-V001 | I-RJ-MHAR-PMP-0011 | 1/2/3 | 3 | A6 I&C | Jhalawar | Kota | Aneesh & team |  | Done | 24.2366 | 76.8057 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-10-11 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | GandhiChauk(ManoharThana) |  | DIVYANSHU SHARMA | 6350491620 | PAVAN LODHA | 6350491637 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-HMGR-ENB-0037 | I-RJ-HMGR-PMP-0020 | 1 | 1 | A6 I&C | Hanumangarh | Ganganagar | Karan & Team |  | Done | 29.6064 | 74.2992 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-10-11 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 6 | Tiwari Colony |  | DEEPAK KUMAR | 8078699524 | RAKESH KUMAR HMGR | 8094115268 | VACANT HMGR | 0 | JLKD
I-RJ-CBRA-ENB-6000 | I-RJ-CBRA-PMP-0001 | 1 | 1 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 24.6671 | 76.8472 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR05 | 2024-10-07 | 2024-10-07 | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-10-14 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Chhabra |  | NARENDRA AIRWAL | 6350492145 | VINOD KUMAR CBRA | 9571065406 | BRIJESH SEN | 9636956881 | JLKD
I-RJ-BRNN-ENB-6005 | I-RJ-BRNN-PMP-0024 | 2 | 1 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 25.1134 | 76.5762 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-10-14 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | FATEHPUR |  | Raghuveer Suman | 6375297725 | VIKAS SUMAN | 6350491530 | SUSHIL PANDEY | 8078698882 | JLKD
I-RJ-VJIG-ENB-V001 | I-RJ-VJIG-PMP-0022 | 1/2/3 | 3 | A6 I&C | Suratgarh | Ganganagar | Rajkumar & team |  | Done | 29.2437 | 73.5272 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-12 | 2024-10-14 | 2024-10-14 | 2024-10-14 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | SRI VIJAYNAGAR |  | SURENDER SINGH | 8955001723 | SANTOSH KUMAR | 6350491304 | VACANT VJIG// ANUG | 0 | JLKD
I-RJ-BRNN-ENB-0008 | I-RJ-BRNN-PMP-0005 | 3 | 1 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 25.1042 | 76.4996 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-13 | 2024-10-14 | 2024-10-14 | 2024-10-14 | ANEESH | 2024-10-18 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Inside Grain Mandi Premises |  | Harish Suman | 6350491201 | VIKAS SUMAN | 6350491530 | SUSHIL PANDEY | 8078698882 | JLKD
I-RJ-GGGR-ENB-6016 | I-RJ-GGGR-PMP-0046 | 1/2/3 | 3 | A6 I&C | Ganganagar | Ganganagar | Karan & Team |  | Done | 29.83 | 73.726 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-13 | 2024-10-14 | 2024-10-14 | 2024-10-14 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | 0 |  | MADAN LAL | 9649987829 | GURSIMAR GILL | 9877807007 | VACANT GGGR | 0 | JLKD
I-RJ-SKRN-ENB-9042 | I-RJ-SKRN-PMP-0009 | 1 | 1 | A6 I&C | Ganganagar | Ganganagar |  |  | MRN Done | 29.8567 | 73.4828 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | NR | NR | NR | NR | NA | NR |  |  |  |  | NO | YES | FINALIZED |  |  | Ready |  |  | 0 | 0 | 0 | 0 |  | Mahender Singh | 6350492130 | Vinod SKRN | 6350492138 | VACANT GGGR | 0 | JLKD
I-RJ-CHTB-ENB-V001 | I-RJ-CHTB-PMP-0007 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0499 | 76.153 | GBT | 0 | A6 I&C , ATP11A & 11C |  | 5mtr cpri 1 10g sfp min reqd | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-15 | 2024-10-15 | 2024-10-15 | 2024-10-15 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | CHAUTH KA BARWARA |  | BRIJMOHAN | 6350491172 | POORAN VERMA | 7690881734 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-GGPC-ENB-I002 | I-RJ-GGPC-PMP-0035 | 1 | 1 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4862 | 76.7392 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR06 | 2024-10-09 | 2024-10-09 | 2024-10-16 | 2024-10-16 | 2024-10-16 | 2024-10-16 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 7 | Gangapur City New |  | LAKHAN LAL MEENA | 6350491164 | DILKHUSH MEENA | 9414736021 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-GGPC-ENB-0053 | I-RJ-GGPC-PMP-0049 | 1/2/3 | 3 | A6 I&C | Kota | Kota | Aneesh & team |  | Done | 26.4893 | 76.7306 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | GANGAPUR CITY |  | HIMMAT SINGH GURJAR | 9571214999 | DILKUSH MEENA | 9414736021 | Bhupendra Rajawat | 7850947540 | JLKD
I-RJ-GGPC-ENB-6001 | I-RJ-GGPC-PMP-0019 | 1 | 1 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4735 | 76.728 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2024-10-18 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Gangapur |  | PRAHLAD MEENA | 9602895557 | LUKMAN KHAN | 8209271082 | Bhupendra Rajawat | 7850947540 | JLKD
I-RJ-SMDP-ENB-0011 | I-RJ-SMDP-PMP-0008 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0328 | 76.3564 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Adarsh Nagar |  | KAMLESH KUMAR GURJAR | 8000505208 | SOMENT VAISHNAV | 8824273976 | FIROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-I001 | I-RJ-SMDP-PMP-0050 | 1/3 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0275 | 76.3545 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-19 | 2024-10-19 | 2024-10-19 | 2024-10-19 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 7 | Akashwani |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FIROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0041 | I-RJ-SMDP-PMP-0021 | 1 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0203 | 76.3703 | NBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-20 | 2024-10-20 | 2024-10-20 | 2024-10-20 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 5 | Kishanpura |  | MOHAMMED ARIF | 6350491165 | SAHIL KHAN | 9001903735 | FIROJ KHAN | 6350491277 | JLKD
I-RJ-GGGR-ENB-0026 | I-RJ-GGGR-PMP-0016 | 2 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rahul |  | Done | 29.9149 | 73.9124 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-19 | 2024-10-19 | 2024-10-24 | 2024-10-24 | TARACHAND REF RAHUL | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Near Tehsil |  | PAWAN DHAWAL | 9875250862 | GAGANDEEP SINGH | 9588220230 | VACANT GGGR | 0 | JLKD
I-RJ-GGGR-ENB-I024 | I-RJ-GGGR-PMP-0101 | 1/2/3 | 3 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rahul |  | Done | 29.9273 | 73.8616 | RT Tower | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-21 | 2024-10-21 | 2024-10-23 | 2024-10-23 | TARACHAND REF RAHUL | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 85 | 0 | Purani Sabji Mandi |  | MADAN LAL | 9649987829 | GURSIMAR GILL | 9877807007 | VACANT GGGR | 0 | JLKD
I-RJ-MKAR-ENB-0002 | I-RJ-MKAR-PMP-0002 | 1/2 | 2 | A6 I&C | Hanumangarh | Ganganagar | Aneesh & team |  | Done | 29.6009 | 74.2534 | GBM | 0 | A6 I&C , ATP11A & 11C |  | need ot claim 1 extra transportation | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-25 | 2024-10-25 | 2024-10-25 | 2024-10-25 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Makasar |  | DEEPAK KUMAR | 8078699524 | RAKESH KUMAR HMGR | 8094115268 | VACANT HMGR | 0 | JLKD
I-RJ-HMGR-ENB-V003 | I-RJ-HMGR-PMP-0068 | 1 | 1 | A6 I&C | Hanumangarh | Ganganagar | Aneesh & team |  | Done | 29.5776 | 74.3223 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR08 | 2024-10-21 | 2024-10-21 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-22 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Hanumangarh_1 |  | PRAVEEN KUMAR | 8005913202 | RAKESH KUMAR HMGR | 8094115268 | VACANT HMGR | 0 | JLKD
I-RJ-TBBI-ENB-A001 | I-RJ-TBBI-PMP-0008 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Aneesh & team |  | Done | 29.5165 | 74.589 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR08 | 2024-10-21 | 2024-10-21 | 2024-10-23 | 2024-10-23 | 2024-10-23 | 2024-10-23 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | 0 |  | PAWAN KUMAR TIBBI | 9636418516 | Rajesh Kumar | 9351228528 | VACANT HMGR | 0 | JLKD
I-RJ-NOHR-ENB-9060 | I-RJ-NOHR-PMP-0010 | 1/2/3 | 3 | A6 I&C | Hanumangarh | Ganganagar | Aneesh & team |  | Done | 29.258 | 74.3986 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR07 | 2024-10-16 | 2024-10-16 | 2024-10-24 | 2024-10-24 | 2024-10-24 | 2024-10-24 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Rawatsar |  | HARSH KUMAR | 7976229390 | RANJEET SINGH | 8239827805 | AMIT KUMAR | 0 | JLKD
I-RJ-ANGR-ENB-9024 | I-RJ-ANGR-PMP-0004 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rahul |  | Done | 29.0149 | 73.0731 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR08 | 2024-10-21 | 2024-10-21 | 2024-10-26 | 2024-10-26 | 2024-10-26 | 2024-10-26 | TARACHAND REF RAHUL | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | 03 STR; Gharsana |  | PRAMOD | 9875858295 | Vinod ANGR | 6350492215 | VACANT VJIG// ANUG | 0 | JLKD
I-RJ-SMDP-ENB-6008 | I-RJ-SMDP-PMP-0032 | 2/3 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.1027 | 76.3643 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-13 | 2024-11-13 | 2024-11-13 | 2024-11-13 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | SOORWAL |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-V006 | I-RJ-SMDP-PMP-0061 | 1 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0689 | 76.3656 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-13 | 2024-11-13 | 2024-11-13 | 2024-11-13 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 90 | 0 | Kamanda |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0027 | I-RJ-SMDP-PMP-0016 | 1 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0389 | 76.3557 | 25 M GBM-Old | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-17 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | Bhopal nagar |  | KAMLESH KUMAR GURJAR | 8000505208 | SOMENT VAISHNAV | 8824273976 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0013 | I-RJ-SMDP-PMP-0009 | 2 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0378 | 76.37 | Kadevi | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-17 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Post Katupura |  | KAMLESH KUMAR GURJAR | 8000505208 | SOMENT VAISHNAV | 8824273976 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0049 | I-RJ-SMDP-PMP-0025 | 1/2 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0239 | 76.3537 | 25 M GBM-Hybrid | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-14 | 2024-11-14 | 2024-11-14 | 2024-11-15 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 35 | 0 | Indira Ground Ke Samne; Sawaimadhopur |  | KAMLESH KUMAR GURJAR | 8000505208 | SOMENT VAISHNAV | 8824273976 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0041 | I-RJ-SMDP-PMP-0021 | 2/3 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0203 | 76.3703 | NBT-NEW | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-15 | 2024-11-15 | 2024-11-17 | 2024-11-17 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Kishanpura |  | MOHAMMED ARIF | 6350491165 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0023 | I-RJ-SMDP-PMP-0012 | 1/2 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0204 | 76.3801 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-15 | 2024-11-15 | 2024-11-17 | 2024-11-17 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Near Vatika resort |  | MOHAMMED ARIF | 6350491165 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-KHDR-ENB-V002 | I-RJ-KHDR-PMP-0008 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.011 | 76.6049 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-17 | 2024-11-17 | 2024-11-17 | 2024-11-17 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Khandar |  | HARIMOHAN MEENA | 6350491176 | vacant | vacant | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0047 | I-RJ-SMDP-PMP-0023 | 3 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0145 | 76.3533 | 25 M GBM-Hybrid | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-16 | 2024-11-18 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | Near Railway Over Bridge; Sawaimadhopur |  | SURENDRA BAIRWA | 6350491571 | DESHRAJ BAIRWA | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-6007 | I-RJ-SMDP-PMP-0031 | 3 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0043 | 76.3592 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-16 | 2024-11-16 | 2024-11-16 | 2024-11-18 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | MAHAVEER NAGAR |  | NARENDRA KUMAR BAIRWA | 8949151149 | DESHRAJ BAIRWA | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-CHTB-ENB-I007 | I-RJ-CHTB-PMP-0006 | 2/3 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.2004 | 76.0325 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-18 | 2024-11-18 | 2024-11-18 | 2024-11-18 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Siwar |  | BRIJMOHAN | 6350491172 | POORAN VERMA | 7690881734 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0021 | I-RJ-SMDP-PMP-0011 | 2 | 1 | A6 I&C | Sawai Madhopur | Kota |  |  | MRN Done | 26.0254 | 76.3883 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | NR | NR | NR | NR | NA | NR |  |  |  |  | NO | YES | FINALIZED |  |  | Ready |  |  | 0 | 0 | 0 | The Oberoi Vanyavilas,Ranthambore |  | MOHAMMED ARIF | 6350491165 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-GGPC-ENB-0023 | I-RJ-GGPC-PMP-0012 | 3 | 1 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4805 | 76.746 | Ramboll-Hybrid | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-21 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Gangapu city |  | LAKHAN LAL MEENA | 6350491164 | DILKHUSH MEENA | 9414736021 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-GGPC-ENB-I006 | I-RJ-GGPC-PMP-0038 | 1 | 1 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4764 | 76.7163 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR10 | 2024-11-19 | 2024-11-19 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-21 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Nagawala Ke Chawani |  | LAKHAN LAL MEENA | 6350491164 | DILKHUSH MEENA | 9414736021 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-GGPC-ENB-I009 | I-RJ-GGPC-PMP-0040 | 3 | 1 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4932 | 76.7383 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR10 | 2024-11-19 | 2024-11-19 | 2024-11-20 | 2024-11-20 | 2024-11-20 | 2024-11-21 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | BC_Pattharmarket1_infill |  | LAKHAN LAL MEENA | 6350491164 | DILKHUSH MEENA | 9414736021 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-BUND-ENB-0026 | I-RJ-BUND-PMP-0016 | 1/3 | 2 | A6 I&C | Bundi | Kota | Aneesh & team |  | Done | 25.4303 | 75.655 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR10 | 2024-11-19 | 2024-11-19 | 2024-11-22 | 2024-11-22 | 2024-11-22 | 2024-11-22 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 35 | 0 | Beebanwa |  | Riyazuddin | 6350491262 | PAPPU LAL RATHOR | 6350491214 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-SMDP-ENB-I012 | I-RJ-SMDP-PMP-0053 | 1/2 | 2 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0268 | 76.357 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR10 | 2024-11-19 | 2024-11-19 | 2024-11-23 | 2024-11-23 | 2024-11-23 | 2024-11-23 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 85 | 0 | Maharana Pratap Colony |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-KBNF-ENB-A001 | I-RJ-KBNF-PMP-0001 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.2548 | 76.3271 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-24 | 2024-11-24 | 2024-11-24 | 2024-11-24 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Khirni |  | YOGENDRA SINGH | 8104779681 | DILRAJ MEENA | 9079797012 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-MLRN-ENB-6001 | I-RJ-MLRN-PMP-0002 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.2548 | 76.3224 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR09 | 2024-11-09 | 2024-11-12 | 2024-11-26 | 2024-11-26 | 2024-11-26 | 2024-11-26 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 115 | 0 | KHIRNI |  | RAMESH CHANDRA MALI | 6377201510 | DILRAJ MEENA | 9079797012 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-BUND-ENB-V002 | I-RJ-BUND-PMP-0048 | 2 | 1 | A6 I&C | Bundi | Kota | Aneesh & team |  | Done | 25.437 | 75.6317 | RTD | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR11 | 2024-11-27 | 2024-11-27 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | GURUNANK COLONY |  | Riyazuddin | 6350491262 | PAPPU LAL RATHOR | 6350491214 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-SMDP-ENB-V005 | I-RJ-SMDP-PMP-0060 | 2 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0316 | 76.3527 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR11 | 2024-11-27 | 2024-11-27 | 2024-11-28 | 2024-11-28 | 2024-11-28 | 2024-11-28 | ANEESH | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Sawaimadhopur |  | KAMLESH KUMAR GURJAR | 8000505208 | SOMENT VAISHNAV | 8824273976 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-GGPC-ENB-I002 | I-RJ-GGPC-PMP-0035 | 2/3 | 2 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4862 | 76.7392 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 80 | 10 | 0 | Gangapur City New |  | LAKHAN LAL MEENA | 6350491164 | DILKHUSH MEENA | 9414736021 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-GGPC-ENB-I003 | I-RJ-GGPC-PMP-0036 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4781 | 76.7265 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-20 | 2024-12-20 | 2024-12-20 | 2024-12-20 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 85 | 0 | SubhashColony |  | PRAHLAD MEENA | 9602895557 | LUKMAN KHAN | 8209271082 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-SMDP-ENB-V001 | I-RJ-SMDP-PMP-0056 | 1 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 26.0166 | 76.3485 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Bajaria |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-V002 | I-RJ-SMDP-PMP-0057 | 1 | 1 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.994 | 76.3347 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-21 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Ricco colony, Khairda-01 |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-JAAL-ENB-6002 | I-RJ-JAAL-PMP-0001 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Vikram Team Outsource |  | Done | 27.2193 | 74.1881 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-23 | outsource | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | JAYAL |  | RATNA RAM | 6350492259 | BHARAT PAL CHAHAR | 6377200454 | NAVEEN KUMAR | 7300420675 | JLKD
I-RJ-KUKD-ENB-6000 | I-RJ-KUKD-PMP-0001 | 1/2 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Team Outsource |  | Done | 27.1497 | 74.3457 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-21 | 2024-12-21 | 2024-12-21 | 2024-12-23 | outsource | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | KHATU KURD |  | GIRWAR SINGH | 6350491970 | Mahaveer Kumar | 8078698874 | NAVEEN KUMAR | 7300420675 | JLKD
I-RJ-DENA-ENB-6080 | I-RJ-DENA-PMP-0003 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur |  |  | MRN Done | 26.7293 | 74.475 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | NR | NR | NR | NR | NA | NR |  |  |  | MRN DONE ON 31-DEC-2024 | NO | YES | FINALIZED |  |  | Ready |  |  | 0 | 0 | 0 | HARSOR |  | Jamal Deen | 6350491953 | JAGDISH KAREL | 7073280815 | RAJENDRA SINGH RATHORE | 6350491813 | JLKD
I-RJ-BUND-ENB-0008 | I-RJ-BUND-PMP-0007 | 2 | 1 | A6 I&C | Bundi | Kota | Aneesh & team |  | Done | 25.4114 | 75.6372 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-22 | 2024-12-22 | 2024-12-22 | 2024-12-22 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Chhatar pura |  | Riyazuddin | 6350491262 | PAPPU LAL RATHOR | 6350491214 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-TLER-ENB-I001 | I-RJ-TLER-PMP-0002 | 1/2 | 2 | A6 I&C | Bundi | Kota | Aneesh & team |  | Done | 25.2533 | 75.8639 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-12-23 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Teerath |  | SHAHMIK HUSSIAN | 6350491221 | vacant | vacant | BALJEET SINGH | 7988583845 | JLKD
I-RJ-KOTA-ENB-0024 | I-RJ-KOTA-PMP-0014 | 1 | 1 | A6 I&C | Kota | Kota | Aneesh & team |  | Done | 25.1931 | 75.8341 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-12-23 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 15 | Opposite Roadways Work Shop, balaPura |  | AQUIB JAVED | 6350491018 | SATYANARAYAN GURJAR | 6350491561 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-DDWN-ENB-I033 | I-RJ-DDWN-PMP-0032 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Vikram Team Outsource |  | Done | 27.393 | 74.5738 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-22 | 2024-12-22 | 2024-12-22 | 2024-12-24 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Deedwana II |  | MAHENDRA NEHRA | 6350491087 | MAHAVEER BURDAK | 7665889561 | NAVEEN KUMAR | 7300420675 | JLKD
I-RJ-DDWN-ENB-6013 | I-RJ-DDWN-PMP-0002 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.4051 | 74.5788 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-23 | 2024-12-23 | 2024-12-23 | 2024-12-24 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Didwana |  | MAHENDRA NEHRA | 6350491087 | MAHAVEER BURDAK | 7665889561 | NAVEEN KUMAR | 7300420675 | JLKD
I-RJ-DDWN-ENB-6012 | I-RJ-DDWN-PMP-0001 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Team Outsource |  | Done | 27.3977 | 74.5742 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-22 | 2024-12-22 | 2024-12-22 | 2024-12-24 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | DIDWANA |  | MAHENDRA NEHRA | 6350491087 | SUKHDEV ROYAL | 6377567213 | NAVEEN KUMAR | 7300420675 | JLKD
I-RJ-LDNU-ENB-I024 | I-RJ-LDNU-PMP-0034 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.6342 | 74.3814 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-22 | 2024-12-22 | 2024-12-22 | 2024-12-26 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 150 | 50 | 0 | Uncha Magra Baas |  | SITA RAM | 9875107105 | RAMAWTAR CHOYAL | 6376893895 | NAVEEN KUMAR | 7300420675 | JLKD
I-RJ-BUND-ENB-9044 | I-RJ-BUND-PMP-0052 | 1/2/3 | 3 | A6 I&C | Bundi | Kota | Aneesh & team |  | Done | 25.4416 | 75.6665 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-24 | 2024-12-24 | 2024-12-24 | 2024-12-24 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Nav Jeevan sang Colony |  | KALU GUJJAR | 6350491210 | RAM NARESH | 8955199695 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-DDWN-ENB-I028 | I-RJ-DDWN-PMP-0028 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Team Outsource |  | Done | 27.407 | 74.8057 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-22 | 2024-12-22 | 2024-12-22 | 2024-12-25 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | NOOWA |  | SOHAN RAM | 6376620646 | Mahaveer Kumar | 8078698874 | RAJENDRA SINGH RATHORE | 6350491813 | JLKD
I-RJ-DDWN-ENB-I032 | I-RJ-DDWN-PMP-0031 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Team Outsource |  | Done | 27.4278 | 74.8445 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR12 | 2024-12-17 | 2024-12-18 | 2024-12-22 | 2024-12-22 | 2024-12-22 | 2024-12-25 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Sudrasan |  | SOHAN RAM | 6376620646 | Mahaveer Kumar | 8078698874 | RAJENDRA SINGH RATHORE | 6350491813 | JLKD
I-RJ-BRNN-ENB-6002 | I-RJ-BRNN-PMP-0021 | 1 | 1 | A6 I&C | Baran | Kota | Aneesh & team |  | Done | 25.096 | 76.5213 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR13 | 2024-12-21 | 2024-12-23 | 2024-12-25 | 2024-12-25 | 2024-12-25 | 2024-12-25 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Ambedkar Circle |  | Raghuveer Suman | 6375297725 | VIKAS SUMAN | 6350491530 | SUSHIL PANDEY | 8078698882 | JLKD
I-RJ-SMDP-ENB-S001 | I-RJ-SMDP-PMP-0055 | 1/2/3 | 3 | A6 I&C | Sawai Madhopur | Kota | Aneesh & team |  | Done | 25.9889 | 76.3792 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR13 | 2024-12-21 | 2024-12-23 | 2024-12-26 | 2024-12-26 | 2024-12-26 | 2024-12-26 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Khandar Road |  | SURENDRA BAIRWA | 6350491571 | DESHRAJ BAIRWA | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-GGPC-ENB-0054 | I-RJ-GGPC-PMP-0050 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.4974 | 76.7356 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR13 | 2024-12-21 | 2024-12-23 | 2024-12-27 | 2024-12-27 | 2024-12-27 | 2024-12-27 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Gangapur City |  | BHARAT LAL MEENA | 9571214999 | DILKUSH MEENA | 9414736021 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-GGPC-ENB-0027 | I-RJ-GGPC-PMP-0051 | 1/2/3 | 3 | A6 I&C | Gangapur | Kota | Aneesh & team |  | Done | 26.484 | 76.7394 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR14 | 2024-12-30 | 2024-12-30 | 2024-12-31 | 2024-12-31 | 2024-12-31 | 2024-12-31 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 90 | 20 | 0 | Gangapur |  | LAKHAN LAL MEENA | 6350491164 | DILKHUSH MEENA | 9414736021 | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-CHTB-ENB-9007 | I-RJ-CHTB-PMP-0002 | 2 | 1 | A6 I&C | Sawai Madhopur | KOTA | Aneesh & team |  | Done | 26.034 | 76.2422 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-13 | 2025-01-12 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Vilopa |  | BRIJMOHAN | 6350491172 | POORAN VERMA | 7690881734 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0015 | I-RJ-SMDP-PMP-0010 | 1/3 | 2 | A6 I&C | Sawai Madhopur | KOTA | Aneesh & team |  | Done | 25.9935 | 76.3856 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 10 | 0 | Near Police chowki |  | SURENDRA BAIRWA | 6350491571 | DESHRAJ BAIRWA | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-9033 | I-RJ-SMDP-PMP-0036 | 1/3 | 2 | A6 I&C | Sawai Madhopur | KOTA | Aneesh & team |  | Done | 26.0256 | 76.2847 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-13 | 2025-01-13 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Dhumnn Kalan |  | BRIJMOHAN | 6350491172 | POORAN VERMA | 7690881734 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-BUND-ENB-0007 | I-RJ-BUND-PMP-0006 | 2/3 | 2 | A6 I&C | Bundi | KOTA | Aneesh & team |  | Done | 25.4282 | 75.6306 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-13 | 2025-01-13 | 2025-01-13 | 2025-01-13 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 25 | Teachers Colony |  | Riyazuddin | 6350491262 | PAPPU LAL RATHOR | 6350491214 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-KSTN-ENB-9005 | I-RJ-KSTN-PMP-0003 | 3 | 1 | A6 I&C | Bundi | KOTA | Aneesh & team |  | Done | 25.3254 | 75.9366 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-14 | 2025-01-14 | 2025-01-14 | 2025-01-14 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Keshorai Patan |  | SHAHMIK HUSSIAN | 6350491221 | vacant | vacant | BALJEET SINGH | 7988583845 | JLKD
I-RJ-KOTA-ENB-0093 | I-RJ-KOTA-PMP-0118 | 3 | 1 | A6 I&C | Kota | KOTA | Aneesh & team |  | Done | 25.1965 | 75.8588 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-16 | 2025-01-16 | 2025-01-16 | 2025-01-17 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Hospital, Information Center |  | vacant | vacant | KULDEEP SINGH | 6350491266 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KOTA-ENB-0116 | I-RJ-KOTA-PMP-0061 | 2/3 | 2 | A6 I&C | Kota | KOTA | Aneesh & team |  | Done | 25.149 | 75.8981 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-17 | 2025-01-17 | 2025-01-17 | 2025-01-17 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Khasra No.195-196,Raipura Circle |  | ASHOK KHALMANIA | 6350491166 | vacant | vacant | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KOTA-ENB-0199 | I-RJ-KOTA-PMP-0161 | 2/3 | 2 | A6 I&C | Kota | KOTA | Aneesh & team |  | Done | 25.1932 | 75.8388 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-15 | 2025-01-15 | 2025-01-15 | 2025-01-15 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 35 | 0 | Nagar Nigam Community Hall |  | AQUIB JAVED | 6350491018 | SATYANARAYAN GURJAR | 6350491561 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KOTA-ENB-0211 | I-RJ-KOTA-PMP-0169 | 1/3 | 2 | A6 I&C | Kota | KOTA | Aneesh & team |  | Done | 25.1883 | 75.8334 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-16 | 2025-01-16 | 2025-01-16 | 2025-01-16 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 35 | 0 | Sakatpura |  | AQUIB JAVED | 6350491018 | SATYANARAYAN GURJAR | 6350491561 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KOTA-ENB-0239 | I-RJ-KOTA-PMP-0369 | 1/2/3 | 3 | A6 I&C | Kota | KOTA | Aneesh & team |  | Done | 25.1482 | 75.8385 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-16 | 2025-01-16 | 2025-01-17 | 2025-01-17 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | House No. 4-K-40, Talwandi, Kota (Raj) |  | NARENDRA SHARMA | 7877055510 | Ramesh Singh | 6350491256 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KHUR-ENB-9042 | I-RJ-KHUR-PMP-0006 | 1 | 1 | A6 I&C | Jhalawar | KOTA | Aneesh & team |  | Done | 24.768 | 76.2538 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-18 | 2025-01-18 | 2025-01-18 | 2025-01-18 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Khanpur |  | TejKaran Gurjar | 6350491274 | Naresh Kumar Nagar | 6350491232 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-PIRR-ENB-6003 | I-RJ-PIRR-PMP-0001 | 3 | 1 | A6 I&C | Jhalawar | KOTA | Aneesh & team |  | Done | 24.3654 | 76.1799 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR15 | 2025-01-08 | 2025-01-11 | 2025-01-18 | 2025-01-18 | 2025-01-18 | 2025-01-18 | ANEESH | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | RAIPUR |  | Ram Kumar Tibtiya | 9664032575 | GIRIRAJ VERMA | 8003106045 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-HILI-ENB-6001 | I-RJ-HILI-PMP-0002 | 2 | 1 | A6 I&C | Bundi | KOTA | Rohit & team |  | Done | 25.5107 | 75.5382 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | BARA Nayagaon |  | Ranveer Singh | 8107444108 | LAKHAN PRAJAPAT | 8696898417 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-BUND-ENB-9048 | I-RJ-BUND-PMP-0033 | 2/3 | 2 | A6 I&C | Bundi | KOTA | Rohit & team |  | Done | 25.248 | 75.8487 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-24 | 2025-03-24 | 2025-03-24 | 2025-03-24 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Maharana |  | vacant | vacant | MANOJ SHARMA | 9588984702 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-KOTA-ENB-0548 | I-RJ-KOTA-PMP-0380 | 1/2/3 | 3 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 25.1927 | 75.8522 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-25 | 2025-03-25 | 2025-03-25 | 2025-03-25 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Ummed park |  | vacant | vacant | KULDEEP SINGH | 6350491266 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-SMDP-ENB-9053 | I-RJ-SMDP-PMP-0039 | 3 | 1 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 26.1246 | 76.3636 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-22 | 2025-03-22 | 2025-03-26 | 2025-03-23 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Menpura |  | KAMLESH KUMAR GURJAR | 8000505208 | SOMENT VAISHNAV | 8824273976 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-6008 | I-RJ-SMDP-PMP-0032 | 1 | 1 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 26.1027 | 76.3643 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-22 | 2025-03-22 | 2025-03-26 | 2025-03-23 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | SOORWAL |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-6001 | I-RJ-SMDP-PMP-0028 | 2 | 1 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 25.9699 | 76.2956 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-26 | 2025-03-26 | 2025-03-26 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 60 | 0 | KUSHTALA |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-KCPS-ENB-9002 | I-RJ-KCPS-PMP-0002 | 3 | 1 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 25.9747 | 76.289 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-26 | 2025-03-23 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | KUSTALA |  | SURENDRA BAIRWA | 6350491571 | DESHRAJ BAIRWA | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-NAWA-ENB-9025 | I-RJ-NAWA-PMP-0003 | 1 | 1 | A6 I&C | Bundi | KOTA | Rohit & team |  | Done | 25.6432 | 75.8285 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-23 | 2025-03-23 | 2025-03-27 | 2025-03-23 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Nainwa |  | PAWAN PARJAPAT | 6376917990 | PUSHPENDRA KUMAR SAINI | 8955176207 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-SMDP-ENB-0021 | I-RJ-SMDP-PMP-0011 | 1/2 | 2 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 26.0254 | 76.3883 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR18 | 2025-03-26 | 2025-03-26 | 2025-03-27 | 2025-03-27 | 2025-03-27 | 2025-03-27 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | The Oberoi Vanyavilas,Ranthambore |  | MOHAMMED ARIF | 6350491165 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-0023 | I-RJ-SMDP-PMP-0012 | 3 | 1 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 26.0204 | 76.3801 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR18 | 2025-03-26 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-28 | 2025-03-28 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Near Vatika resort |  | MOHAMMED ARIF | 6350491165 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-SMDP-ENB-9033 | I-RJ-SMDP-PMP-0036 | 2 | 1 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 26.0256 | 76.2847 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR18 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 60 | 0 | Dhumnn Kalan |  | BRIJMOHAN | 6350491172 | POORAN VERMA | 7690881734 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-CHTB-ENB-9007 | I-RJ-CHTB-PMP-0002 | 1 | 1 | A6 I&C | Sawai Madhopur | KOTA | Rohit & team |  | Done | 26.034 | 76.2422 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR18 | 2025-03-26 | 2025-03-26 | 2025-03-28 | 2025-03-28 | 2025-03-28 | 2025-03-28 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 60 | 0 | Vilopa |  | BRIJMOHAN | 6350491172 | POORAN VERMA | 7690881734 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-HILI-ENB-9022 | I-RJ-HILI-PMP-0009 | 1 | 1 | A6 I&C | Bundi | KOTA | Rohit & team |  | Done | 25.5403 | 75.5199 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-29 | 2025-03-29 | 2025-03-29 | 2025-03-29 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 60 | 0 | Hindoli |  | RAVI KUMAR DHAKAD | 6350491184 | LAKHAN PRAJAPAT | 8696898417 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-HILI-ENB-9005 | I-RJ-HILI-PMP-0006 | 1 | 1 | A6 I&C | Bundi | KOTA | Rohit & team |  | Done | 25.4595 | 75.5908 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-29 | 2025-03-29 | 2025-03-29 | 2025-03-29 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 60 | 0 | Talav gaon |  | RAVI KUMAR DHAKAD | 6350491184 | LAKHAN PRAJAPAT | 8696898417 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-TLER-ENB-I002 | I-RJ-TLER-PMP-0003 | 3 | 1 | A6 I&C | Bundi | KOTA | Rohit & team |  | Done | 25.0942 | 75.5151 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR16 | 2025-03-21 | 2025-03-21 | 2025-03-25 | 2025-03-26 | 2025-03-25 | 2025-03-29 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | DABI 3 INFILL |  | vacant | vacant | MANOJ SHARMA | 9588984702 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-BUND-ENB-I016 | I-RJ-BUND-PMP-0044 | 2/3 | 2 | A6 I&C | Bundi | KOTA | Rohit & team |  | Done | 25.0852 | 75.544 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | NEAR DABI |  | Manoj Prajapat | 9660156600 | MANOJ SHARMA | 9588984702 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-RWBH-ENB-9011 | I-RJ-RWBH-PMP-0002 | 3 | 1 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 24.8787 | 75.6609 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-30 | 2025-03-30 | 2025-03-30 | 2025-03-30 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Anushakti |  | Narendra Kumar | 6350491228 | BHARAT KUMAR DHAKER | 6350491025 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-RGMD-ENB-9047 | I-RJ-RGMD-PMP-0015 | 1 | 1 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 24.7239 | 75.9529 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Ramganjmandi |  | MUKESH SHARMA | 6350491226 | PAWAN KUMAR | 6350491241 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-RGMD-ENB-9010 | I-RJ-RGMD-PMP-0003 | 1 | 1 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 24.7315 | 75.9728 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Azad Nagar |  | MUKESH SHARMA | 6350491226 | PAWAN KUMAR | 6350491241 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-RGMD-ENB-9040 | I-RJ-RGMD-PMP-0010 | 2 | 1 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 24.6164 | 75.9701 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Ramganjmandi |  | MUKESH SHARMA | 6350491226 | PAWAN KUMAR | 6350491241 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-JLWR-ENB-W001 | I-RJ-JLWR-PMP-0032 | 3 | 1 | A6 I&C | Jhalawar | KOTA | Rohit & team |  | Done | 24.5639 | 76.1437 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-02 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Undel |  | Ram Kumar Tibtiya | 9664032575 | GIRIRAJ VERMA | 8003106045 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-MHAR-ENB-9012 | I-RJ-MHAR-PMP-0002 | 3 | 1 | A6 I&C | Jhalawar | KOTA | Rohit & team |  | Done | 24.2958 | 76.7879 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-04-01 | 2025-04-01 | 2025-04-01 | 2025-04-01 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 60 | 0 | Samrol |  | DIVYANSHU SHARMA | 6350491620 | PAVAN LODHA | 6350491637 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-SAOD-ENB-6001 | I-RJ-SAOD-PMP-0002 | 1 | 1 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 24.9279 | 76.2909 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-04-02 | 2025-04-02 | 2025-04-02 | 2025-04-02 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Sangod |  | SURENDRA MEENA | 6350491272 | HEMANT MALAV | 6377209976 | DINESH KUMAR | 6350491191 | JLKD
I-RJ-SAOD-ENB-6000 | I-RJ-SAOD-PMP-0001 | 3 | 1 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 24.9729 | 76.4294 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR17 | 2025-03-24 | 2025-03-25 | 2025-04-02 | 2025-04-02 | 2025-04-02 | 2025-04-02 | ROHIT | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | BAPAWAR KALAN |  | Raghuveer Suman | 6375297725 | Naresh Kumar Nagar | 6350491232 | SUSHIL PANDEY | 8078698882 | JLKD
I-RJ-KOTA-ENB-0551 | I-RJ-KOTA-PMP-0399 | 1/2/3 | 3 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 25.2007 | 75.8599 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR18 | 2025-04-03 | 2025-04-03 | 2025-04-04 | 2025-04-04 | 2025-04-04 | 2025-04-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 65 | 0 | Ladpura |  | vacant | vacant | KULDEEP SINGH | 6350491266 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KOTA-ENB-0542 | I-RJ-KOTA-PMP-0395 | 1/2/3 | 3 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 25.18 | 75.8829 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR18 | 2025-04-03 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-05 | 2025-04-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 65 | 0 | Devli Arab |  | Lalit kumar Tailor | 6376917151 | NARENDRA KUMAR | 9636163665 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KOTA-ENB-0049 | I-RJ-KOTA-PMP-0083 | 2/3 | 2 | A6 I&C | Kota | KOTA | Rohit & team |  | Done | 25.1487 | 75.8603 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR18 | 2025-04-03 | 2025-04-03 | 2025-04-05 | 2025-04-05 | 2025-04-05 | 2025-04-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 10 | 0 | Indra Colony |  | DWARKI LAL | 6350491192 | Ramesh Singh | 6350491256 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KSGR-ENB-9013 | I-RJ-KSGR-PMP-0036 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.6137 | 75.038 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-12 | 2025-04-12 | 2025-04-12 | 2025-04-14 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Bandarsindri |  | RAJU YADAV | 6376917822 | RAKESH KUMAR | 8740029627 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-BAUF-ENB-9001 | I-RJ-BAUF-PMP-0001 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.5975 | 75.0359 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-12 | 2025-04-12 | 2025-04-12 | 2025-04-14 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Bandarsindri |  | RAJU YADAV | 6376917822 | RAKESH KUMAR | 8740029627 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KSGR-ENB-V012 | I-RJ-KSGR-PMP-0071 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.5974 | 74.9283 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-12 | 2025-04-12 | 2025-04-12 | 2025-04-14 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Tolamal(Dhr-Ajm Hwy) |  | RAJU YADAV | 6376917822 | RAKESH KUMAR | 8740029627 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-BUND-ENB-9031 | I-RJ-BUND-PMP-0057 | 1/2/3 | 3 | A6 I&C | Bundi | Kota | Hanuman & Team |  | Done | 25.4284 | 75.7121 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-12 | 2025-04-12 | 2025-04-13 | 2025-04-17 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Matunda |  | KALU LAL GURJAR | 6350491210 | VACANT | VACANT | BALJEET SINGH | 7988583845 | JLKD
I-RJ-BUND-ENB-9079 | I-RJ-BUND-PMP-0036 | 2/3 | 2 | A6 I&C | Bundi | Kota | Hanuman & Team |  | Done | 25.4105 | 75.5947 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-04-17 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Vill-HATTIPURA |  | Riyazuddin . | 6350491262 | PAPPU LAL RATHOR | 6350491214 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-BUND-ENB-9045 | I-RJ-BUND-PMP-0055 | 2/3 | 2 | A6 I&C | Bundi | Kota | Hanuman & Team |  | Done | 25.3782 | 75.6111 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-13 | 2025-04-13 | 2025-04-13 | 2025-04-17 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Silor |  | Riyazuddin . | 6350491262 | PAPPU LAL RATHOR | 6350491214 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-CHEH-ENB-9001 | I-RJ-CHEH-PMP-0001 | 2/3 | 2 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 24.7693 | 75.8855 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-14 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 10 | 0 | Chechat |  | SURENDRA KUMAR | 6350491652 | BHARAT KUMAR DHAKER | 6350491025 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-MDKK-ENB-9001 | I-RJ-MDKK-PMP-0001 | 2 | 1 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 24.7196 | 75.9535 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-14 | 2025-04-14 | 2025-04-14 | 2025-04-16 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Ramganjmandi |  | MUKESH KUMAR SHARMA | 6350491226 | PAWAN KUMAR | 6350491241 | dinesh kumar sharma | 6350491191 | JLKD
I-RJ-UDPU-ENB-9001 | I-RJ-UDPU-PMP-0001 | 2 | 1 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 24.7257 | 75.9754 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-16 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Udpura |  | MUKESH KUMAR SHARMA | 6350491226 | PAWAN KUMAR | 6350491241 | dinesh kumar sharma | 6350491191 | JLKD
I-RJ-SKET-ENB-6000 | I-RJ-SKET-PMP-0001 | 2 | 1 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 24.6503 | 76.0431 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-16 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Suket |  | MUKESH KUMAR ORA | 6350491226 | PAWAN KUMAR | 6350491241 | dinesh kumar sharma | 6350491191 | JLKD
I-RJ-SKET-ENB-9001 | I-RJ-SKET-PMP-0003 | 1/2/3 | 3 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 24.6421 | 76.0405 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-15 | 2025-04-15 | 2025-04-15 | 2025-04-15 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Suket |  | MUKESH KUMAR ORA | 9351376042 | PAWAN KUMAR | 6350491241 | dinesh kumar sharma | 6350491191 | JLKD
I-RJ-RGMD-ENB-V002 | I-RJ-RGMD-PMP-0022 | 1 | 1 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 24.645 | 75.9418 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Ramganjmandi |  | MUKESH KUMAR SHARMA | 6350491226 | PAWAN KUMAR | 6350491241 | dinesh kumar sharma | 6350491191 | JLKD
I-RJ-BEWR-ENB-0088 | I-RJ-BEWR-PMP-0070 | 1/2/3 | 3 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.0903 | 74.3082 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Ambedkar bhawna, |  | NEMI CHAND | 9680086665 | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-BEWR-ENB-0090 | I-RJ-BEWR-PMP-0069 | 1/2/3 | 3 | A6 I&C | Beawar | Ajmer | Dileep & team |  | Done | 26.0954 | 74.2944 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-16 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Govindpura |  | NEMI CHAND | 9680086665 | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-BEWR-ENB-9033 | I-RJ-BEWR-PMP-0026 | 1 | 1 | A6 I&C | Beawar | Ajmer | Dileep & team |  | Done | 26.0806 | 74.2767 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-17 | 2025-04-17 | 2025-04-17 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Jaliya-I |  | NEMI CHAND | 9680086665 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-9047 | I-RJ-BEWR-PMP-0034 | 3 | 1 | A6 I&C | Beawar | Ajmer | Dileep & team |  | Done | 26.0414 | 74.2993 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Gohana |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-9043 | I-RJ-BEWR-PMP-0031 | 3 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.1225 | 74.3504 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Delwara |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-6000 | I-RJ-BEWR-PMP-0015 | 2 | 1 | CPRI MIGRATION | Beawar | Ajmer | Rohit & team |  | Done | 26.135 | 74.352 | GBT | 0 | CPRI INSTALLATION FOR CASCADING |  |  | Allotment- AIR20 | 2025-04-16 | 2025-04-16 | 2025-04-17 | 2025-04-17 | NA | NR | NA | NR |  |  |  |  | NO | NO | NA |  |  | Ready |  | 2 RE-VISIT ONLY IN BILL | 0 | 0 | 0 | BEAWER 1 |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-6000 | I-RJ-BEWR-PMP-0015 | 1 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.135 | 74.352 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-17 | 2025-04-17 | 2025-04-17 | 2025-04-17 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 40 | 0 | BEAWER 1 |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-TONK-ENB-9007 | I-RJ-TONK-PMP-0027 | 2 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0761 | 75.7193 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Mehandwas |  | Anil Kumar Chouhan | 6350491771 | Hansraj Gurjar | 6376917825 | VACANT | VACANT | JLKD
I-RJ-TONK-ENB-0033 | I-RJ-TONK-PMP-0016 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.1572 | 75.7988 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-18 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Village- Kasba Tonk Sharki |  | Mukesh Kumar Jat | 6350491773 | SATYANARAYAN BAIRWA | 9509017588 | VACANT | VACANT | JLKD
I-RJ-TOON-ENB-I007 | I-RJ-TOON-PMP-0006 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Rohit & team |  | Done | 26.2747 | 75.6427 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-19 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | JHIRANA |  | Brij Mohan Gurjar | 9024462337 | VACANT | VACANT | VACANT | VACANT | JLKD
I-RJ-MPUR-ENB-6002 | I-RJ-MPUR-PMP-0001 | 2 | 1 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 26.3755 | 75.4365 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-19 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | DIGGI |  | SATYANARAYAN SINGH | 7665666391 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-NWAI-ENB-9070 | I-RJ-NWAI-PMP-0030 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4631 | 75.9425 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-20 | 2025-04-20 | 2025-04-20 | 2025-04-20 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Gunsi |  | TRILOK RAJVANSHI | 8432564860 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-BSTL-ENB-9003 | I-RJ-BSTL-PMP-0002 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.3997 | 75.8706 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-20 | 2025-04-20 | 2025-04-20 | 2025-04-20 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Banasthali |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-SRWR-ENB-9006 | I-RJ-SRWR-PMP-0003 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.1267 | 74.9488 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-20 | 2025-04-20 | 2025-04-20 | 2025-04-20 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 0 | GOLIYA |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-PSKR-ENB-I001 | I-RJ-PSKR-PMP-0007 | 3 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4944 | 74.5422 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | PUSHKAR 3 INFILL |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-AJMR-ENB-9063 | I-RJ-AJMR-PMP-0161 | 1/2 | 2 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.5159 | 74.5435 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Pushkar |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-DOLI-ENB-9057 | I-RJ-DOLI-PMP-0007 | 2 | 1 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 25.8822 | 75.5571 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Banthali |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-9012 | I-RJ-DOLI-PMP-0006 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Rohit & team |  | Done | 25.8569 | 75.5326 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Santhali |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-6000 | I-RJ-UNRA-PMP-0001 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0752 | 75.9914 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-21 | 2025-04-21 | 2025-04-21 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | BANETHA |  | MAHENDRA KUMAR | 9799049201 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-9045 | I-RJ-NSRB-PMP-0010 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.4052 | 74.8254 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-18 | 2025-04-18 | 2025-04-22 | 2025-04-22 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Jilawara |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-9025 | I-RJ-NSRB-PMP-0006 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.3963 | 74.9015 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-18 | 2025-04-19 | 2025-04-22 | 2025-04-22 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Tihari |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-NSRB-ENB-I001 | I-RJ-NSRB-PMP-0014 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.3199 | 74.7429 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-18 | 2025-04-18 | 2025-04-22 | 2025-04-22 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | TRANSPORT NAGAR,NASIRABAD |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-9043 | I-RJ-NSRB-PMP-0009 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.2758 | 74.7484 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-18 | 2025-04-18 | 2025-04-18 | 2025-04-22 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Derathu |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-INDA-ENB-9031 | I-RJ-INDA-PMP-0010 | 1/3 | 2 | A6 I&C | Bundi | Kota | Hanuman & Team |  | Done | 25.7306 | 76.2218 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-22 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Indragarh |  | Rameshwar Prasad | 6350491257 | VINOD KUMAR SAINI | 6376917132 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-INDA-ENB-H002 | I-RJ-INDA-PMP-0012 | 2 | 1 | A6 I&C | Bundi | Kota | Hanuman & Team |  | Done | 25.8097 | 76.1974 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Babai |  | Rameshwar Prasad | 6350491257 | VINOD KUMAR SAINI | 6376917132 | BALJEET SINGH | 7988583845 | JLKD
I-RJ-NSRB-ENB-9004 | I-RJ-NSRB-PMP-0020 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.2031 | 74.7216 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Plot In Gram - Jharwasa |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-6004 | I-RJ-UNRA-PMP-0004 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.9561 | 76.2147 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-22 | 2025-04-22 | 2025-04-22 | 2025-04-22 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | PACHLA RPTR |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-SRWR-ENB-H001 | I-RJ-SRWR-PMP-0017 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.0991 | 74.8889 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Jotayan |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-KRRV-ENB-6000 | I-RJ-KRRV-PMP-0001 | 1 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.1931 | 74.4377 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-17 | 2025-04-18 | 2025-04-17 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | KHARWA |  | BHANWAR LAL SHARMA | 6350616694 | Ramchandra Jat | 6376917836 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-AJMR-ENB-9048 | I-RJ-AJMR-PMP-0159 | 1 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.5381 | 74.652 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Makadwali |  | GYAN SINGH RAWAT | 7014970918 | JITENDRA KANOJIYA | 6375556812 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-BDLY-ENB-9005 | I-RJ-BDLY-PMP-0006 | 1/3 | 2 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4605 | 74.7116 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-20 | 2025-04-20 | 2025-04-20 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Badliya, |  | Ajay Singh Rawat | 6350491821 | KULDEEP MEHRA | 9549964994 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-AJMR-ENB-0387 | I-RJ-AJMR-PMP-0259 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4641 | 74.6153 | RTP | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-19 | 2025-04-19 | 2025-04-19 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Foy Sagar Road |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-PSKR-ENB-9001 | I-RJ-PSKR-PMP-0002 | 3 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4941 | 74.5491 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | BADI BASTI |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-PSKR-ENB-6000 | I-RJ-PSKR-PMP-0001 | 2 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.492 | 74.5516 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 2025-04-23 | IMRAN OTS | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Pushkar |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-SMDP-ENB-6000 | I-RJ-SMDP-PMP-0027 | 3 | 1 | CPRI MIGRATION | Sawai Madhopur | Kota | Hanuman & Team |  | Done | 26.0436 | 76.3828 | GBT | 0 | CPRI INSTALLATION FOR CASCADING |  |  | Allotment- AIR20 | 2025-04-16 | 2025-04-16 | 2025-04-23 | 2025-04-23 | NA | NR | NA | NR |  |  |  |  | NO | NO | NA |  |  | Ready |  | 2 RE-VISIT ONLY IN BILL | 0 | 0 | 0 | Khilchipur |  | NARENDRA KUMAR BAIRWA | 8949151149 | SAHIL KHAN | 9001903735 | FEROJ KHAN | 6350491277 | JLKD
I-RJ-KHDR-ENB-V003 | I-RJ-KHDR-PMP-0009 | 2 | 1 | A6 I&C | Sawai Madhopur | Kota | Hanuman & Team |  | Done | 26.0189 | 76.6951 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-23 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Bharawanda Kalan |  | HARIMOHAN MEENA | 6350491176 | ANIL KUMAR BAIRWA | 6350491665 | BHUPENDRA SINGH RAJAWAT | 6350491277 | JLKD
I-RJ-TDRS-ENB-9035 | I-RJ-TDRS-PMP-0003 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Rohit & team |  | Done | 26.0194 | 75.4935 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-19 | 2025-04-21 | 2025-04-24 | 2025-04-24 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Todaraisingh |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-KKRI-ENB-6000 | I-RJ-KKRI-PMP-0001 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.0197 | 75.3141 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-24 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | BAGHERA |  | SAURABH GAUTTAM | 8947973523 | MANISH MEENA | 6350491497 | VACANT | VACANT | JLKD
I-RJ-GGPC-ENB-I011 | I-RJ-GGPC-PMP-0042 | 1/3 | 2 | A6 I&C | Gangapur | Kota | Hanuman & Team |  | Done | 26.547 | 76.8586 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Saroli |  | LAKHAN LAL MEENA | 9694452733 | VACANT | VACANT | MUZAHID KHAN | 9694268872 | JLKD
I-RJ-MLRN-ENB-6000 | I-RJ-MLRN-PMP-0001 | 1 | 1 | A6 I&C | Gangapur | Kota | Hanuman & Team |  | Done | 26.2453 | 76.3755 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Badoti |  | RAMESH CHANDRA MALI | 9950891123 | DILRAJ MEENA | 9079797012 | BHUPENDRA SINGH RAJAWAT | 6350491277 | JLKD
I-RJ-KEIW-ENB-9039 | I-RJ-KEIW-PMP-0005 | 2 | 1 | A6 I&C | Beawar | Ajmer | Dileep & team |  | Done | 25.9891 | 74.9257 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Biliya |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-KKRI-ENB-9031 | I-RJ-KKRI-PMP-0014 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.0026 | 75.1649 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-20 | 2025-04-24 | 2025-04-20 | 2025-04-24 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  | Re-visit Reqd | 100 | 55 | 0 | Kekri |  | SAURABH GAUTTAM | 8947973523 | MANISH MEENA | 6350491497 | VACANT | VACANT | JLKD
I-RJ-KKRI-ENB-9051 | I-RJ-KKRI-PMP-0008 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 25.9702 | 75.1437 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-25 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 85 | 0 | Beawar |  | SAURABH GAUTTAM | 8947973523 | MANISH MEENA | 6350491497 | VACANT | VACANT | JLKD
I-RJ-KEIW-ENB-9040 | I-RJ-KEIW-PMP-0006 | 3 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 25.9396 | 74.7223 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Barli |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-MSUD-ENB-I008 | I-RJ-MSUD-PMP-0014 | 2 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.0887 | 74.5168 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Masuda |  | BHANWAR LAL SHARMA | 6350616694 | Ramchandra Jat | 6376917836 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-KOTA-ENB-0314 | I-RJ-KOTA-PMP-0371 | 2/3 | 2 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 25.2038 | 75.844 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 10 | 0 | Girdharpura |  | AQUIB JAVED | 6350491018 | SATYANARAYAN GURJAR | 6350491561 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-KIHN-ENB-A001 | I-RJ-KIHN-PMP-0002 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.7923 | 74.8496 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-25 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Patta No. 45, Village & Post Roopangarh |  | KAILASH CHAND RAIGER | 7014767214 | RAVIRAJ MEGHWAL | 9783998177 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-DIRS-ENB-9024 | I-RJ-DIRS-PMP-0014 | 2/3 | 2 | A6 I&C | Kota | Kota | Hanuman & Team |  | Done | 25.1539 | 76.1693 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  | Re-visit Reqd | 80 | 10 | 0 | Vallabh pura |  | Mukesh Gocher | 6350491224 | LALIT KUMAR TAILOR | 6376917151 | SUSHEEL KUMAR PANDEY | 8078698882 | JLKD
I-RJ-UNRA-ENB-6003 | I-RJ-UNRA-PMP-0021 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.9681 | 76.086 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-24 | 2025-04-23 | 2025-04-23 | 2025-04-26 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | ALIGARH |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-NWAI-ENB-I004 | I-RJ-NWAI-PMP-0023 | 1/2 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.2185 | 75.9609 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-21 | 2025-04-22 | 2025-04-21 | 2025-04-26 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  | Re-visit Reqd | 65 | 120 | 0 | Natwara |  | HAJARI LAL BAIRWA | 9982083115 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-KSGR-ENB-0070 | I-RJ-KSGR-PMP-0027 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.6174 | 74.8476 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-26 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | Pabatsar Road; Kishangarh; Ajmer |  | Jaiveer Singh Rajawat | 6350491819 | CHANDRA PRAKASH | 8432556352 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KSGR-ENB-6015 | I-RJ-KSGR-PMP-0035 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.5697 | 74.8118 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-25 | 2025-04-25 | 2025-04-25 | 2025-04-26 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Dhani rathoran |  | Jaiveer Singh Rajawat | 6350491819 | CHANDRA PRAKASH | 8432556352 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KSGR-ENB-0021 | I-RJ-KSGR-PMP-0012 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.5586 | 74.8814 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Gujarwada |  | RAJU YADAV | 6376917822 | RAKESH KUMAR | 8740029627 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-BEWR-ENB-0048 | I-RJ-BEWR-PMP-0012 | 2 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.1132 | 74.3283 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | Beawar |  | VACANT | VACANT | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-MSUD-ENB-9028 | I-RJ-MSUD-PMP-0005 | 1 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.0823 | 74.3762 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Scrap Yard, Near BSNL Tower |  | VACANT | VACANT | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-A002 | I-RJ-BEWR-PMP-0038 | 1 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.1104 | 74.3278 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | Adarsh Nagar Beawer |  | VACANT | VACANT | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-0042 | I-RJ-BEWR-PMP-0062 | 2 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.101 | 74.3208 | RTP | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-26 | 2025-04-26 | 2025-04-26 | 2025-04-26 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | Shitla Mata Mandir |  | VACANT | VACANT | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-6001 | I-RJ-BEWR-PMP-0016 | 2 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 25.9432 | 74.2073 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Ajmer-Beawer Highway |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-H001 | I-RJ-BEWR-PMP-0045 | 2 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 25.8768 | 74.1482 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Taragarh |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-NWAI-ENB-9011 | I-RJ-NWAI-PMP-0010 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.3549 | 75.9515 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Jugalpura |  | BABU LAL GURJAR | 7976922712 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-NWAI-ENB-H001 | I-RJ-NWAI-PMP-0022 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4046 | 76.1147 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  | Re-visit Reqd | 60 | 60 | 0 | Badgaon |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-AJMR-ENB-9014 | I-RJ-AJMR-PMP-0155 | 1 | 1 | A6 I&C | Ajmer | Ajmer | Dileep & team |  | Done | 26.542 | 74.6069 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-25 | 2025-04-25 | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Panchayt Kori |  | Raj Kumar | 6350491825 | VACANT | VACANT | VACANT | MAHESH KUMAR | JLKD
I-RJ-AJMR-ENB-0210 | I-RJ-AJMR-PMP-0260 | 2/3 | 2 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.5281 | 74.64 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | nishi |  | GYAN SINGH RAWAT | 7014970918 | JITENDRA KANOJIYA | 6375556812 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-AJMR-ENB-0211 | I-RJ-AJMR-PMP-0241 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.5354 | 74.6903 | NGBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-27 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  | Re-visit Reqd | 120 | 50 | 0 | Bhauto Pole |  | GYAN SINGH RAWAT | 7014970918 | JITENDRA KANOJIYA | 6375556812 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-AJMR-ENB-0322 | I-RJ-AJMR-PMP-0237 | 2 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4627 | 74.6771 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Madar Krishi farm |  | Ajay Singh Rawat | 6350491821 | KULDEEP MEHRA | 9549964994 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-AJMR-ENB-0132 | I-RJ-AJMR-PMP-0236 | 3 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4377 | 74.6688 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-23 | 2025-04-23 | 2025-04-23 | 2025-04-27 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Virat nagar, Ajmer |  | Ajay Singh Rawat | 6350491821 | KULDEEP MEHRA | 9549964994 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-AJMR-ENB-0191 | I-RJ-AJMR-PMP-0098 | 1/3 | 2 | A6 I&C | Ajmer | Ajmer | Dileep & team |  | Done | 26.3471 | 74.5791 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-25 | 2025-04-25 | 2025-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Saradhna |  | Rakesh Paroda | 6350491793 | MOHAN SINGH | 9568428114 | 9568428114 | MUKESH PRAJAPAT | JLKD
I-RJ-MSUD-ENB-I002 | I-RJ-MSUD-PMP-0010 | 3 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 25.9621 | 74.4549 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-25 | 2025-04-25 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | KANPUR(Daulatpura) |  | GOVIND JYOTISHI | 7891237598 | Pawan Kumar Sharma | 6350491834 | 6350491834 | VACANT | JLKD
I-RJ-BHMN-ENB-9024 | I-RJ-BHMN-PMP-0008 | 2/3 | 2 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 25.9115 | 74.3333 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | BHinmal |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-PISN-ENB-9024 | I-RJ-PISN-PMP-0007 | 1/2 | 2 | A6 I&C | Beawar | Ajmer | Dileep & team |  | Done | 26.3818 | 74.4366 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-28 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Pisangan |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-AJMR-ENB-9007 | I-RJ-AJMR-PMP-0248 | 1 | 1 | A6 I&C | Ajmer | Ajmer | Dileep & team |  | Done | 26.3379 | 74.5612 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-28 | 2025-04-28 | 2025-04-28 | 2025-04-29 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Saradhana |  | Rakesh Paroda | 6350491793 | MOHAN SINGH | 9568428114 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-MSUD-ENB-I009 | I-RJ-MSUD-PMP-0011 | 1/2/3 | 3 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.1587 | 74.3813 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-25 | 2025-04-25 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Peeplai |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | 7014399733 | MUKESH PRAJAPAT | JLKD
I-RJ-PISN-ENB-9008 | I-RJ-PISN-PMP-0006 | 2 | 1 | A6 I&C | Beawar | Ajmer | Rohit & team |  | Done | 26.2739 | 74.5067 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | MANGLIYAWAS |  | BHANWAR LAL SHARMA | 6350616694 | Ramchandra Jat | 6376917836 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-KSGR-ENB-H004 | I-RJ-KSGR-PMP-0051 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.3504 | 75.1001 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-29 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Dhasook |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KSGR-ENB-9064 | I-RJ-KSGR-PMP-0040 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.5157 | 74.9277 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-29 | 2025-04-29 | 2025-04-29 | 2025-04-30 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 80 | 0 | Barna |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-MPUR-ENB-I010 | I-RJ-MPUR-PMP-0013 | 1 | 1 | A6 I&C | Tonk | Ajmer | Rohit & team |  | Done | 26.4716 | 75.3187 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-04-30 | 2025-04-30 | 2025-04-30 | 2025-04-30 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Pachewar |  | SUNIL KUMAR PAREWA | 6350491792 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-KOTA-ENB-V014 | I-RJ-KOTA-PMP-0346 | 2 | 1 | CPRI MIGRATION | Kota | Kota | Rajkumar & team |  | Done | 25.1453 | 75.8435 | RTT | 0 | CPRI INSTALLATION FOR CASCADING |  |  | Allotment- AIR20 | 2025-04-16 | 2025-04-16 | 2025-05-02 | 2025-05-02 | NA | NR | NA | NR |  |  |  |  | NO | NO | NA |  |  | Ready |  | 2 RE-VISIT ONLY IN BILL | 0 | 0 | 0 | INDIRA VIHAR |  | NARENDRA SHARMA | 7877055510 | Ramesh Singh | 6350491256 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-NWAI-ENB-9033 | I-RJ-NWAI-PMP-0011 | 1/2 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4001 | 76.0684 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-30 | 2025-04-30 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 0 | Niwai |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-TOON-ENB-9043 | I-RJ-TOON-PMP-0010 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4233 | 75.6343 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-30 | 2025-04-30 | 2025-05-02 | 2025-05-02 | 2025-05-02 | 2025-05-02 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | PIPLU |  | Brij Mohan Gurjar | 9024462337 | VACANT | VACANT | VACANT | VACANT | JLKD
I-RJ-TDRS-ENB-H002 | I-RJ-TDRS-PMP-0007 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0201 | 75.4263 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-04-24 | 2025-04-24 | 2025-04-24 | 2025-05-03 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Bhasu |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-SRWR-ENB-V001 | I-RJ-SRWR-PMP-0016 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Hanuman & Team |  | Done | 26.1388 | 74.818 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-30 | 2025-04-30 | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-03 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Tantoti |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-KSGR-ENB-H003 | I-RJ-KSGR-PMP-0050 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Rohit & Team |  | Done | 26.4701 | 74.9897 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-03 | 2025-05-03 | 2025-05-03 | 2025-05-03 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Katsoora |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-NSRB-ENB-H001 | I-RJ-NSRB-PMP-0022 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.3093 | 74.9269 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-04 | 2025-05-04 | 2025-05-04 | 2025-05-04 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Morajhari |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-BARW-ENB-V001 | I-RJ-BARW-PMP-0001 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.283 | 74.8801 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-04 | 2025-05-04 | 2025-05-04 | 2025-05-04 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Ramsar Ajmer |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-BAUE-ENB-V001 | I-RJ-BAUE-PMP-0001 | 2 | 1 | A6 I&C | Beawar | Ajmer | Hanuman & Team |  | Done | 26.1211 | 74.6944 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-04 | 2025-05-04 | 2025-05-04 | 2025-05-04 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Bandanwara-2 |  | GOVIND JYOTISHI | 7891237598 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-MSUD-ENB-9028 | I-RJ-MSUD-PMP-0005 | 2 | 1 | A6 I&C | Beawar | Ajmer | Dileep & team |  | Done | 26.0823 | 74.3762 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-04 | 2025-05-04 | 2025-05-04 | 2025-05-04 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Scrap Yard, Near BSNL Tower |  | VACANT | VACANT | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-NSRB-ENB-I007 | I-RJ-NSRB-PMP-0015 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.2769 | 74.7712 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-04 | 2025-05-05 | 2025-05-04 | 2025-05-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 55 | 100 | 0 | derathoo |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-9038 | I-RJ-NSRB-PMP-0008 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.2935 | 74.7051 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-04 | 2025-05-05 | 2025-05-04 | 2025-05-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Nandla |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-KEIW-ENB-I003 | I-RJ-KEIW-PMP-0010 | 2 | 1 | A6 I&C | Beawar | Ajmer | Hanuman & Team |  | Done | 25.969 | 74.8442 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Chapaneri |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-9011 | I-RJ-NSRB-PMP-0005 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.2857 | 74.6701 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Nasirabad |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-TONK-ENB-6002 | I-RJ-TONK-PMP-0022 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.2569 | 75.9534 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Parana |  | HAJARI LAL BAIRWA | 9982083115 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-TONK-ENB-H004 | I-RJ-TONK-PMP-0037 | 1/2 | 2 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.279 | 75.8871 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-05 | 2025-05-05 | 2025-05-05 | 2025-05-05 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Shivad Baroni |  | HAJARI LAL BAIRWA | 9982083115 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-TDRS-ENB-V002 | I-RJ-TDRS-PMP-0009 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.1545 | 75.2197 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Uniyara Khurd |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-9008 | I-RJ-UNRA-PMP-0007 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.9602 | 76.1629 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-06 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Choru |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-I002 | I-RJ-UNRA-PMP-0017 | 2 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.008 | 76.0575 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-06 | 2025-05-06 | 2025-05-06 | 2025-05-07 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | KHOHLYA |  | MAHENDRA KUMAR | 9799049201 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-KSGR-ENB-0086 | I-RJ-KSGR-PMP-0079 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Rohit & Team |  | Done | 26.5752 | 74.8361 | RTP | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR23 | 2025-04-25 | 2025-04-25 | 2025-04-26 | 2025-05-05 | 2025-04-26 | 2025-05-07 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  | Re-visit Reqd | 40 | 40 | 0 | KISHANGARH |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-UNRA-ENB-6002 | I-RJ-UNRA-PMP-0003 | 2 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.8906 | 76.1869 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Shop |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-KSGR-ENB-I006 | I-RJ-KSGR-PMP-0057 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.7321 | 74.8738 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR21 | 2025-04-19 | 2025-04-19 | 2025-05-07 | 2025-05-07 | 2025-05-07 | 2025-05-07 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Sursura |  | KAILASH CHAND RAIGER | 7014767214 | RAVIRAJ MEGHWAL | 9783998177 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KSGR-ENB-I013 | I-RJ-KSGR-PMP-0060 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rohit & team |  | Done | 26.4046 | 75.0067 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-06 | 2025-05-06 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | SEEL-LAMBA |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-PSKR-ENB-I002 | I-RJ-PSKR-PMP-0008 | 1 | 1 | A6 I&C | Ajmer | Ajmer | Hanuman & Team |  | Done | 26.4883 | 74.5494 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-06 | 2025-05-06 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Badi Basti |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-PISN-ENB-6001 | I-RJ-PISN-PMP-0002 | 1 | 1 | A6 I&C | Beawar | Ajmer | Hanuman & Team |  | Done | 26.4544 | 74.3845 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-06 | 2025-05-06 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-08 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | GOVINDGARH |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KSGR-ENB-0086 | I-RJ-KSGR-PMP-0079 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.5752 | 74.8361 | RTP | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-06 | 2025-05-06 | 2025-05-08 | 2025-05-09 | 2025-05-09 | 2025-05-09 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | KISHANGARH |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-KSGR-ENB-I010 | I-RJ-KSGR-PMP-0058 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.45 | 75.0387 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-05-08 | 2025-05-08 | 2025-05-08 | 2025-05-09 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 35 | 0 | Arain |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-NGUR-ENB-0062 | I-RJ-NGUR-PMP-0084 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Rajkumar & team |  | Done | 27.2039 | 73.7231 | RTP | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-11 | 2025-05-11 | 2025-05-11 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 90 | 0 | Senik Basti |  | MAHENDRA JAT | 8290502749 | NENA RAM | 8696050229 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DENA-ENB-9080 | I-RJ-DENA-PMP-0015 | 3 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 26.6701 | 74.3374 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-10 | Hanuman | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | makrana |  | Jamal Deen | 6350491953 | Arjun Rao | VACANT | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9056 | I-RJ-DENA-PMP-0012 | 1 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 26.9447 | 74.3528 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-10 | Hanuman | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | DEGANA |  | JITENDRA PATIDAR | 6350491976 | RAJESH KASWAN | VACANT | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DDWN-ENB-9092 | I-RJ-DDWN-PMP-0042 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Hanuman & Team |  | Done | 27.3961 | 74.5931 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-11 | 2025-05-11 | 2025-05-11 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | IN NAGAR PALIKA LAND; NEAR LOHIYA STADIUM; SUJANGARH |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | VACANT | OM PRAKASH | 6350491377 | JLJH
I-RJ-LDNU-ENB-I018 | I-RJ-LDNU-PMP-0031 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Hanuman & Team |  | Done | 27.609 | 74.5872 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-11 | 2025-05-11 | 2025-05-11 | 2025-05-11 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Rodoo |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 8696050229 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NGUR-ENB-V005 | I-RJ-NGUR-PMP-0071 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Rajkumar & team |  | Done | 26.923 | 73.6765 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Sankhwas |  | DHARMARAM JAJRA | 6376202299 | MAHENDRA DHUNDHWAL | 8696050229 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-NAWW-ENB-9078 | I-RJ-NAWW-PMP-0014 | 2 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.162 | 74.8769 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Kuchaman City |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 8696050229 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I022 | I-RJ-NAWW-PMP-0046 | 2 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.0251 | 75.0002 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | NawaInfill |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 8696050229 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KEIW-ENB-I007 | I-RJ-KEIW-PMP-0012 | 1 | 1 | A6 I&C | Beawar | Ajmer | Hanuman & Team |  | Done | 26.0059 | 74.8736 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-06 | 2025-05-06 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Nagola |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-VJNG-ENB-I002 | I-RJ-VJNG-PMP-0002 | 3 | 1 | A6 I&C | Beawar | Ajmer | Hanuman & Team |  | Done | 25.9301 | 74.649 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR22 | 2025-04-21 | 2025-04-21 | 2025-05-14 | 2025-05-14 | 2025-05-14 | 2025-05-14 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  | 2-revist reqd | 40 | 5 | 0 | Nari Mohalla |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-MRTA-ENB-V003 | I-RJ-MRTA-PMP-0043 | 1/3 | 2 | A6 I&C | Nagaur | Nagaur | Rajkumar & team |  | Done | 26.6494 | 74.0337 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-13 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 35 | 0 | Merta City-2 |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 8696050229 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MRTA-ENB-9116 | I-RJ-MRTA-PMP-0044 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Rajkumar & team |  | Done | 26.6289 | 73.9328 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-10 | 2025-05-10 | 2025-05-10 | 2025-05-13 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | MOKALPUR |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 8696050229 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-I016 | I-RJ-JAAL-PMP-0025 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Hanuman & Team |  | Done | 27.1423 | 74.1933 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | UCHAIRA |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PISN-ENB-6003 | I-RJ-PISN-PMP-0004 | 2 | 1 | A6 I&C | Beawar | Ajmer | Dileep & team |  | Done | 26.2266 | 74.4781 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR24 | 2025-05-02 | 2025-05-02 | 2025-04-06 | 2025-04-06 | 2025-04-06 | 2025-05-17 | SANDEEP | [5 empty] | NO | NO | NA |  |  | Ready |  | 1-EXTRA VISIT REQD | 60 | 60 | 0 | Lamana |  | BHANWAR LAL SHARMA | 6350616694 | Ramchandra Jat | 6376917836 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-DENA-ENB-I018 | I-RJ-DENA-PMP-0038 | 3 | 1 | A6 I&C | Makrana | Nagaur | Rajkumar & team |  | Done | 26.9945 | 74.3165 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | MANJHEE |  | JITENDRA PATIDAR | 6350491976 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-I006 | I-RJ-DENA-PMP-0031 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Dileep & team |  | Done | 26.8027 | 74.2225 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-17 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | BANWARLA |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NGUR-ENB-I012 | I-RJ-NGUR-PMP-0063 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Hanuman & Team |  | Done | 27.4118 | 73.7927 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-17 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Jodhiyasi |  | BHARAT THALOR | 8078698860 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MRTA-ENB-9078 | I-RJ-MRTA-PMP-0025 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Dileep & team |  | Done | 26.7114 | 74.1837 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-17 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Jalwana |  | IMARAN KHAN | 9887333514 | SALEEM MOHAMMAD DESHWALI | 7891896395 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MENW-ENB-V001 | I-RJ-MENW-PMP-0006 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Rajkumar & team |  | Done | 26.6391 | 73.7397 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-17 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | JKCementColony |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-LDNU-ENB-6006 | I-RJ-LDNU-PMP-0012 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Hanuman & Team |  | Done | 27.5312 | 74.3403 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2025-05-17 | 2025-05-17 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | NIMBI JODHAN |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KCMC-ENB-I001 | I-RJ-KCMC-PMP-0017 | 1 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.2089 | 74.8182 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-18 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Ranasar |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-METR-ENB-9006 | I-RJ-METR-PMP-0003 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Dileep & team |  | Done | 26.7279 | 73.9103 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-18 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 15 | 0 | Merta |  | Arif Khan | 6367853630 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MRTA-ENB-6005 | I-RJ-MRTA-PMP-0003 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Dileep & team |  | Done | 26.4536 | 74.0876 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-18 | 2025-05-18 | 2025-05-18 | 2025-05-18 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | JASNAGAR |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-I019 | I-RJ-JAAL-PMP-0026 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Hanuman & Team |  | Done | 27.2209 | 74.1826 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-16 | 2025-05-16 | 2025-05-16 | 2025-05-16 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Lomrodon Ka Mohalla |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-NGUR-ENB-9072 | I-RJ-NGUR-PMP-0047 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Rajkumar & team |  | Done | 27.0512 | 73.8675 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Bhadana |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 8696050229 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-KSTN-ENB-9005 | I-RJ-KSTN-PMP-0003 |  | 1 | CPRI MIGRATION | Bundi | Kota | OUTSOURCE |  | Done | 25.3254 | 75.9366 | GBT | 0 | CPRI INSTALLATION FOR CASCADING |  |  | Allotment- AIR25 | 2025-05-05 | 2025-05-20 | 2025-05-20 | 2025-05-20 | NA | NR | NA | NR |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 0 | 0 | 0 |  |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KOTA-ENB-6005 | I-RJ-KOTA-PMP-0249 |  | 1 | CPRI MIGRATION | Kota | Kota | OUTSOURCE |  | Done | 24.9839 | 75.9289 | GBT | 0 | CPRI INSTALLATION FOR CASCADING |  |  | Allotment- AIR25 | 2025-05-05 | 2025-05-20 | 2025-05-22 | 2025-05-22 | NA | NR | NA | NR |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 0 | 0 | 0 |  |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-MKRN-ENB-A001 | I-RJ-MKRN-PMP-0035 | 3 | 1 | A6 I&C | Makrana | Nagaur | Dileep & team |  | Done | 26.9941 | 74.5598 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR27 | 2025-05-15 | 2025-05-15 | 2025-05-24 | 2025-05-24 | 2025-05-24 | 2025-05-24 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Basroli |  | JITENDRA PATIDAR | 6350491976 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DDWN-ENB-I037 | I-RJ-DDWN-PMP-0034 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.4048 | 74.5702 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR26 | 2025-05-09 | 2025-05-09 | 2025-05-25 | 2025-05-25 | 2025-05-25 | 2025-05-25 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Gadadham |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | VACANT | OM PRAKASH | 6350491377 | JLJH
I-RJ-SRWR-ENB-A001 | I-RJ-SRWR-PMP-0009 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.0569 | 75.0091 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR19 | 2025-04-11 | 2025-04-11 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-05 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  | Re-visit Reqd | 50 | 50 | 0 | Sarwar |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-KOTA-ENB-6029 | I-RJ-KOTA-PMP-0054 | 2 | 1 | CPRI MIGRATION | Kota | Kota | OUTSOURCE |  | Done | 25.1795 | 75.8614 | RTT | 0 | CPRI INSTALLATION FOR CASCADING |  |  | Allotment- AIR20 | 2025-04-16 | 2025-04-16 | 2025-05-20 | 2025-05-20 | NA | NA | NA | [5 empty] | NO | NO | NA |  |  | Ready |  | 2 RE-VISIT ONLY IN BILL | 0 | 0 | 0 | Bajrang Nagar |  | SHIV SINGH | 6377201496 | NARENDRA KUMAR | 9636163665 | BANTI CHAUTHWANI | 6350491169 | JLKD
I-RJ-AJMR-ENB-0057 | I-RJ-AJMR-PMP-0006 | 2 | 1 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | 26.4522 | 74.5931 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-20 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | FOY SAGAR ROAD |  | KISHANA RAM JAT | 6376917711 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-NSRB-ENB-9047 | I-RJ-NSRB-PMP-0011 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.3218 | 74.6714 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-20 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Rajosi |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-S001 | I-RJ-DOLI-PMP-0011 | 2 | 1 | A6 I&C | Tonk | Ajmer | Rohit & team |  | Done | 25.8212 | 75.4681 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-20 | 2025-05-21 | 2025-05-21 | 2025-05-21 | 2025-05-21 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 50 | 0 | Sirohi |  | Chetan Prakash Jat | 6350491764 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DENA-ENB-9082 | I-RJ-DENA-PMP-0017 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Dileep & team |  | Done | 26.7078 | 74.4631 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 80 | 0 | Degana |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9079 | I-RJ-DENA-PMP-0014 | 1 | 1 | A6 I&C | Makrana | Nagaur | Rajkumar & team |  | Done | 26.9503 | 74.1475 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Kherwa |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9088 | I-RJ-DENA-PMP-0020 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.9284 | 74.1158 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-22 | 2025-05-22 | 2025-05-22 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 80 | 0 | Bhadwasi |  | IMARAN KHAN | 9887333514 | RAJESH KASWAN | 9509617574 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MKRN-ENB-I001 | I-RJ-MKRN-PMP-0071 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Rajkumar & team |  | Done | 27.032 | 74.7203 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-21 | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Makrana |  | JITENDRA PATIDAR | 6350491976 | Devilal Gurjar | 8078699370 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9060 | I-RJ-NAWW-PMP-0007 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 27.0266 | 75.1427 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR28 | 2025-05-20 | 2025-05-21 | 2025-05-23 | 2025-05-23 | 2025-05-23 | 2025-05-23 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 80 | 0 | lohrana |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-TONK-ENB-0022 | I-RJ-TONK-PMP-0013 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 26.1693 | 75.7871 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR29 | 2025-05-31 | 2025-05-31 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  | 10kms will be adjusted in dc25 | 90 | 40 | 0 | Panch Batti |  | Mukesh Kumar Jat | 6350491773 | SATYANARAYAN BAIRWA | 9509017588 | VACANT | VACANT | JLKD
I-RJ-GAEC-ENB-9000 | I-RJ-GAEC-PMP-0001 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 26.518 | 74.684 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR29 | 2025-05-31 | 2025-05-31 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  | 12 km adjusted | 90 | 40 | 0 | Ghoogra |  | GYAN SINGH RAWAT | 7014970918 | JITENDRA KANOJIYA | 6375556812 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-AJMR-ENB-I054 | I-RJ-AJMR-PMP-0202 | 3 | 1 | A6 I&C | Ajmer | Ajmer | Dileep & team |  | Done | 26.4584 | 74.6245 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR29 | 2025-05-31 | 2025-05-31 | 2025-06-03 | 2025-06-03 | 2025-06-03 | 2025-06-03 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | LONGIYA |  | Abdullah Khan | 6350491827 | VACANT | VACANT | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-JAAL-ENB-G003 | I-RJ-JAAL-PMP-0019 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.0052 | 74.037 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Loonsara |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SRWR-ENB-9032 | I-RJ-SRWR-PMP-0027 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.2169 | 75.0046 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-04 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Fathegarh |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-MRTA-ENB-9012 | I-RJ-MRTA-PMP-0010 | 1/2 | 2 | A6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.6508 | 74.1166 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Netadiya |  | IMARAN KHAN | 9887333514 | SALEEM MOHAMMAD DESHWALI | 7891896395 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SRWR-ENB-9005 | I-RJ-SRWR-PMP-0002 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.0146 | 75.1008 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Ajgra |  | SAURABH GAUTTAM | 8947973523 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-MPUR-ENB-H003 | I-RJ-MPUR-PMP-0028 | 1/2 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4579 | 75.5434 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR32 | 2025-06-04 | 2025-06-04 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | Hanuman | [5 empty] | NO | NO | NA |  |  | Ready |  | 16km will be adjusted in dc 30 | 120 | 65 | 0 | Soda Baori |  | SUNIL KUMAR PAREWA | 6350491792 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-MPUR-ENB-9034 | I-RJ-MPUR-PMP-0004 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4425 | 75.4829 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | Hanuman | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Choasla |  | SATYANARAYAN SINGH | 7665666391 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-DENA-ENB-A001 | I-RJ-DENA-PMP-0023 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.849 | 74.1921 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-05 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | AANTROLI KALAN |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PASS-ENB-G001 | I-RJ-PASS-PMP-0019 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.9063 | 74.5944 | GBT | 0 | A6 I&C , ATP11A & 11C |  | TWO SECTOR WILL BE CLAIMED IN NEXT INVOICE WO ISSUE | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  | only single sector can be claimed due to work order issue | 180 | 70 | 0 | Badoo |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-TDRS-ENB-9045 | I-RJ-TDRS-PMP-0004 | 3 | 1 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 26.1024 | 75.4943 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Bawari |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-TOON-ENB-G003 | I-RJ-TOON-PMP-0005 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.3283 | 75.606 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR32 | 2025-06-04 | 2025-06-04 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Borkhandi |  | Brij Mohan Gurjar | 9024462337 | VACANT | VACANT | VACANT | VACANT | JLKD
I-RJ-MKRN-ENB-I006 | I-RJ-MKRN-PMP-0040 | 2 | 1 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.9654 | 74.5776 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | NANDOLI MERTIYA |  | JITENDRA PATIDAR | 6350491976 | RICHHPAL GURJAR | 8441931031 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-TOON-ENB-9033 | I-RJ-TOON-PMP-0003 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.2952 | 75.8215 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-06 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Peeplu |  | HAJARI LAL BAIRWA | 9982083115 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-DDWN-ENB-G007 | I-RJ-DDWN-PMP-0015 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.3792 | 74.6438 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-07 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Daulatpura |  | BALDEWA RAM | 8058503498 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-LDNU-ENB-I015 | I-RJ-LDNU-PMP-0029 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.6414 | 74.6837 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-07 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Kushalpura |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DOLI-ENB-I001 | I-RJ-DOLI-PMP-0010 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 25.9205 | 75.5912 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR32 | 2025-06-04 | 2025-06-04 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-07 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  | 17kms will be adjusted in dc25 | 120 | 65 | 0 | JOONIYA |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-9065 | I-RJ-DOLI-PMP-0022 | 3 | 1 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 25.8565 | 75.6329 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-07 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Duni |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-I005 | I-RJ-DOLI-PMP-0020 | 1 | 1 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 25.8451 | 75.7789 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-07 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | GURAI |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-AJMR-ENB-I004 | I-RJ-AJMR-PMP-0269 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4609 | 74.6165 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-06 | 2025-06-07 | 2025-06-07 | 2025-06-08 | RAHUL O | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Prakash Nagar |  | Abdullah Khan | 6350491827 | VACANT | VACANT | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-DDWN-ENB-I020 | I-RJ-DDWN-PMP-0023 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.3587 | 74.7346 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-08 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Khakholi |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-G003 | I-RJ-DDWN-PMP-0013 | 1/2 | 2 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.2501 | 74.7834 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-08 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Nimod |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-AJMR-ENB-9054 | I-RJ-AJMR-PMP-0264 | 1 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.6298 | 74.7242 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-08 | RAHUL O | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Ajmer |  | KAILASH CHAND RAIGER | 7014767214 | RAVIRAJ MEGHWAL | 9783998177 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-AJMR-ENB-9034 | I-RJ-AJMR-PMP-0239 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.5687 | 74.6762 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-08 | RAHUL O | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | chachiyawas |  | GYAN SINGH RAWAT | 7014970918 | JITENDRA KANOJIYA | 6375556812 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-MPUR-ENB-9040 | I-RJ-MPUR-PMP-0007 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.5472 | 75.3068 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-08 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Parli |  | SUNIL KUMAR PAREWA | 6350491792 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-BDLW-ENB-I001 | I-RJ-BDLW-PMP-0002 | 3 | 1 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.9873 | 74.6939 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR29 | 2025-05-31 | 2025-05-31 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-09 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Bidiyad infill |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MPUR-ENB-9046 | I-RJ-MPUR-PMP-0025 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4293 | 75.4134 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-08 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | VPO-Peepliya |  | SUNIL KUMAR PAREWA | 6350491792 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-SRWR-ENB-I008 | I-RJ-SRWR-PMP-0013 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.2817 | 75.0477 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Kasheer |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-SRWR-ENB-6002 | I-RJ-SRWR-PMP-0028 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.18 | 74.9742 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Shergarh |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-9007 | I-RJ-UNRA-PMP-0006 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.9684 | 75.9658 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Dhikoliya |  | Anil Kumar Chouhan | 6350491771 | Hansraj Gurjar | 6376917825 | VACANT | VACANT | JLKD
I-RJ-NGUR-ENB-G004 | I-RJ-NGUR-PMP-0060 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9043 | 73.7446 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-05 | 2025-06-09 | 2025-06-09 | 2025-06-09 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Gwaloo |  | DHARMARAM JAJRA | 6376202299 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-AJMR-ENB-I017 | I-RJ-AJMR-PMP-0272 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4784 | 74.6385 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-06 | 2025-06-06 | 2025-06-06 | 2025-06-09 | RAHUL O | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Lohargarh Road |  | Abdullah Khan | 6350491827 | JITENDRA KANOJIYA | 9024462441 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-MRTA-ENB-9014 | I-RJ-MRTA-PMP-0012 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.6985 | 74.2279 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-09 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Bagad |  | IMARAN KHAN | 9887333514 | SALEEM MOHAMMAD DESHWALI | 7891896395 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SRWR-ENB-9036 | I-RJ-SRWR-PMP-0006 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.1585 | 74.9359 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-04 | 2025-06-06 | 2025-06-06 | 2025-06-10 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Sarwar |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-JAAL-ENB-G006 | I-RJ-JAAL-PMP-0021 | 1/3 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1391 | 74.1269 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-10 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Tarnau |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-G005 | I-RJ-JAAL-PMP-0020 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.136 | 74.0679 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-04 | 2025-06-04 | 2025-06-04 | 2025-06-10 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Fardod |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NGUR-ENB-9038 | I-RJ-NGUR-PMP-0045 | 1/3 | 2 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 26.8631 | 73.6338 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | SURESH OUT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | kankdai |  | DHARMARAM JAJRA | 6376202299 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-9082 | I-RJ-JAAL-PMP-0013 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.3069 | 73.9041 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Jayal |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-H001 | I-RJ-JAAL-PMP-0022 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.4563 | 73.9138 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-11 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Jalniyasar |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-9087 | I-RJ-JAAL-PMP-0015 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.4751 | 73.9526 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-05 | 2025-06-05 | 2025-06-05 | 2025-06-11 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Jayal |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NSRB-ENB-G002 | I-RJ-NSRB-PMP-0028 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.2225 | 74.6457 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Baaghsuri |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-G003 | I-RJ-NSRB-PMP-0013 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.2518 | 74.793 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-11 | DILEEP | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Loharwada |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-I004 | I-RJ-NSRB-PMP-0024 | 1/3 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.2687 | 74.6243 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-11 | RAJKUMAR | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Bithoor |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-TONK-ENB-I004 | I-RJ-TONK-PMP-0039 | 2 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0601 | 75.8056 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-11 | Hanuman | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Arniyamal |  | Anil Kumar Chouhan | 6350491771 | Hansraj Gurjar | 6376917825 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-9038 | I-RJ-UNRA-PMP-0009 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0958 | 76.0391 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Khadon Ki Jhodiya |  | MAHENDRA KUMAR | 9799049201 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-CERV-ENB-9001 | I-RJ-CERV-PMP-0001 | 2/3 | 2 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2032 | 73.7949 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Phagli |  | SUNIL KUMAR | 9412607678 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-PSKR-ENB-V001 | I-RJ-PSKR-PMP-0010 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4862 | 74.551 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | RAHUL O | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 85 | 0 | Badi Basti |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-TONK-ENB-9005 | I-RJ-TONK-PMP-0025 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.1108 | 75.818 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-12 | HANUMAN | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Chandlai | [7 empty] | JLKD
I-RJ-NSRB-ENB-9031 | I-RJ-NSRB-PMP-0007 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.2975 | 74.6222 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-12 | Manout Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Nasirabad |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-I003 | I-RJ-NSRB-PMP-0023 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.3258 | 74.6732 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-12 | Manout Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Rajosi |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-SRWR-ENB-9033 | I-RJ-SRWR-PMP-0005 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.1963 | 74.9049 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-12 | Manout Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Kotdi |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-JAAL-ENB-G002 | I-RJ-JAAL-PMP-0018 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.1038 | 74.1679 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | Rohina |  | BHAGIRATH PAREEK | 6350492228 | JAGDEV RAM BHAKAR | 6350616501 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-KSGR-ENB-I011 | I-RJ-KSGR-PMP-0059 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.4354 | 74.9008 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-13 | RAHUL O | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | MOONDOLAO |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-TONK-ENB-G002 | I-RJ-TONK-PMP-0036 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0965 | 75.7832 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-12 | 2025-06-12 | Hanuman & Team | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Sonwa | [7 empty] | JLKD
I-RJ-JAAL-ENB-I020 | I-RJ-JAAL-PMP-0027 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Suresh Outsource |  | Done | 27.0456 | 74.1687 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | Suresh Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Dotina |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-9063 | I-RJ-JAAL-PMP-0011 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Suresh Outsource |  | Done | 27.0766 | 74.1264 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | Suresh Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 80 | 0 | Silariya |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-TONK-ENB-6001 | I-RJ-TONK-PMP-0021 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0619 | 75.8679 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Ghas | [7 empty] | JLKD
I-RJ-TONK-ENB-I006 | I-RJ-TONK-PMP-0040 | 1/2 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.0167 | 75.8225 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-12 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | UM | [7 empty] | JLKD
I-RJ-JAAL-ENB-9090 | I-RJ-JAAL-PMP-0031 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Suresh Outsource |  | Done | 27.2251 | 74.1952 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-12 | suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Jayal |  | BHAGIRATH PAREEK | 6350492228 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-UNRA-ENB-9048 | I-RJ-UNRA-PMP-0013 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.9443 | 75.9905 | GBT | 0 | A6 I&C , ATP11A & 11C |  | Done | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-13 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Khelniya |  | MAHENDRA KUMAR | 9799049201 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-6001 | I-RJ-UNRA-PMP-0002 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.8321 | 76.2871 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-13 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Kolaspura |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-NSRB-ENB-6003 | I-RJ-NSRB-PMP-0002 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Rahul Outsource |  | Done | 26.4333 | 74.7773 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-13 | RAHUL O | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | SRINAGAR |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-KESR-ENB-G002 | I-RJ-KESR-PMP-0012 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 27.0658 | 73.379 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | Suresh Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Berathal Kalan |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-NGUR-ENB-9020 | I-RJ-NGUR-PMP-0042 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 27.0032 | 73.4805 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-13 | Suresh Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Gudiya |  | DHARMARAM JAJRA | 6376202299 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SRGR-ENB-I014 | I-RJ-SRGR-PMP-0066 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.2447 | 74.1266 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | 165RD/(3TTDD) |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-LDNU-ENB-9039 | I-RJ-LDNU-PMP-0016 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3013 | 74.307 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-13 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Titri |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-I029 | I-RJ-DDWN-PMP-0029 | 1/2 | 2 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3597 | 74.5841 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-11 | 2025-06-11 | 2025-06-13 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Ramsabas |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KESR-ENB-9067 | I-RJ-KESR-PMP-0021 | 1/2 | 2 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 27.1902 | 73.3834 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-10 | 2025-06-11 | 2025-06-10 | 2025-06-13 | suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | BHUNDEL |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLJH
I-RJ-DDWN-ENB-I008 | I-RJ-DDWN-PMP-0020 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.3009 | 74.5635 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-07 | 2025-06-08 | 2025-06-08 | 2025-06-13 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Singrawat-Kala |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SRGR-ENB-9069 | I-RJ-SRGR-PMP-0044 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.2071 | 74.142 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-13 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Suratgarh |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-DDWN-ENB-9063 | I-RJ-DDWN-PMP-0008 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3415 | 74.683 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-13 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | in front of Water tank |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-TONK-ENB-9023 | I-RJ-TONK-PMP-0030 | 2 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & team |  | Done | 26.0858 | 75.9255 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR35 | 2025-06-13 | 2025-06-13 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | HANUMAN | 2025-06-14 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Sadagaon |  | Anil Kumar Chouhan | 6350491771 | Hansraj Gurjar | 6376917825 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-G001 | I-RJ-UNRA-PMP-0015 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.8774 | 75.9397 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-13 | 2025-06-14 | 2025-06-14 | 2025-06-14 | HANUMAN | 2025-06-14 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Palai | [7 empty] | JLKD
I-RJ-UNRA-ENB-H001 | I-RJ-UNRA-PMP-0028 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.8688 | 76.0703 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-13 | 2025-06-14 | 2025-06-14 | 2025-06-14 | HANUMAN | 2025-06-14 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Khatoli | [7 empty] | JLKD
I-RJ-SRGR-ENB-I016 | I-RJ-SRGR-PMP-0101 | 2/3 | 2 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.1965 | 74.0641 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | Rohit & Team | 2025-06-14 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | SOMANSAR |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-G002 | I-RJ-SRGR-PMP-0058 | 1/2 | 2 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.1841 | 73.9427 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-14 | Rohit & Team | 2025-06-14 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | RAYANWALI |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-NWAI-ENB-G001 | I-RJ-NWAI-PMP-0021 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.2943 | 76.1129 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR32 | 2025-06-04 | 2025-06-04 | 2025-06-07 | 2025-06-07 | 2025-06-07 | 2025-06-15 | Hanuman & Team | 2025-06-15 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Jaamoli |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-NWAI-ENB-9064 | I-RJ-NWAI-PMP-0018 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.5147 | 76.1101 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-07 | 2025-06-15 | 2025-06-15 | 2025-06-15 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Hingoniya |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-NWAI-ENB-9055 | I-RJ-NWAI-PMP-0014 | 2 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4995 | 75.9769 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | Hanuman & Team | 2025-06-15 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Luhara |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-PASS-ENB-9043 | I-RJ-PASS-PMP-0012 | 1 | 1 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.8165 | 74.4067 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-10 | 2025-06-09 | 2025-06-15 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Merasi |  | JITENDRA PATIDAR | 6350491976 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-SRGR-ENB-I027 | I-RJ-SRGR-PMP-0073 | 1/3 | 2 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.3214 | 73.9138 | COW(GBT) | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 0 | Lajpat Nagar |  | DINESH KUMAR | 9549866266 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-NWAI-ENB-9010 | I-RJ-NWAI-PMP-0009 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.4432 | 75.9403 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | Hanuman & Team | 2025-06-15 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Mundiya, Niwai |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-DENA-ENB-G001 | I-RJ-DENA-PMP-0027 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.8369 | 74.3346 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | Degena gao |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KCRA-ENB-G001 | I-RJ-KCRA-PMP-0003 | 1/2 | 2 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 26.9912 | 73.97 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-10 | 2025-06-10 | 2025-06-10 |  | Suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Mahio Ka Mohalla |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-NGUR-ENB-9095 | I-RJ-NGUR-PMP-0049 | 1/2 | 2 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 27.0121 | 73.9408 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-11 | 2025-06-11 |  | Suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 80 | 0 | Firozpura |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-PISN-ENB-6000 | I-RJ-PISN-PMP-0001 | 2 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.2993 | 74.5359 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-16 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Arjunpura khalsa |  | Rakesh Paroda | 6350491793 | MOHAN SINGH | 9568428114 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-MRTA-ENB-I011 | I-RJ-MRTA-PMP-0038 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.7978 | 73.8363 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-09 | 2025-06-10 | 2025-06-09 | 2025-06-16 | suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Gagura |  | Arif Khan | 6367853630 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-PISN-ENB-6002 | I-RJ-PISN-PMP-0003 | 1/3 | 2 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | DONE | 26.2847 | 74.4651 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-17 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | JETHANA |  | BHANWAR LAL SHARMA | 6350616694 | Ramchandra Jat | 6376917836 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-KEIW-ENB-9033 | I-RJ-KEIW-PMP-0004 | 3 | 1 | A6 I&C | Beawar | Ajmer | Rajkumar & team |  | Done | 25.9447 | 74.7983 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Bhinay |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-SRWR-ENB-9024 | I-RJ-SRWR-PMP-0004 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Dileep & team |  | Done | 26.0942 | 74.9673 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-09 | 2025-06-09 | 2025-06-09 | 2025-06-13 | Manout Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Sarwar |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-BEWR-ENB-9039 | I-RJ-BEWR-PMP-0029 | 1 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 25.8875 | 74.1627 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | aneesh & Team | 2025-06-17 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Kheda Danti |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-9060 | I-RJ-BEWR-PMP-0036 | 3 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 25.928 | 74.1852 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-17 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Jaliya Second Vas Rupa |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-9023 | I-RJ-BEWR-PMP-0025 | 3 | 1 | A6 I&C | Beawar | Ajmer | Rahul Outsource |  | Done | 26.0457 | 74.239 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-17 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Kishanpura |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-KKRI-ENB-9039 | I-RJ-KKRI-PMP-0006 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Hanuman & Team |  | Done | 25.9602 | 75.1026 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Hanuman & Team | 2025-06-17 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Kekri |  | SAURABH GAUTTAM | 8947973523 | MANISH MEENA | 6350491497 | VACANT | VACANT | JLKD
I-RJ-MSUD-ENB-9050 | I-RJ-MSUD-PMP-0006 | 3 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.1816 | 74.4072 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-17 | aneesh & Team | 2025-06-14 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Reliance A1 plaza |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-SRGR-ENB-9063 | I-RJ-SRGR-PMP-0041 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.1148 | 73.9216 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Birdhwal |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-BEWR-ENB-6003 | I-RJ-BEWR-PMP-0018 | 1/3 | 2 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.0572 | 74.2959 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Kesharpura |  | NEMI CHAND | 9680086665 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-JGWS-ENB-I001 | I-RJ-JGWS-PMP-0001 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9137 | 74.3131 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Jhagarwas |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KSGR-ENB-G001 | I-RJ-KSGR-PMP-0047 | 1/3 | 2 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.6833 | 74.8593 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-15 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Ralawata |  | KAILASH CHAND RAIGER | 7014767214 | RAVIRAJ MEGHWAL | 9783998177 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-BEWR-ENB-V005 | I-RJ-BEWR-PMP-0056 | 2 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.1617 | 74.2857 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-16 | aneesh & Team | 2025-06-15 |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Beawar Roopnagar |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-TDRS-ENB-G001 | I-RJ-TDRS-PMP-0005 | 3 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 26.1779 | 75.571 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR35 | 2025-06-13 | 2025-06-13 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | Hnauman & Team | OK |  |  |  |  | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Hameerpura |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-MPUR-ENB-9013 | I-RJ-MPUR-PMP-0002 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.345 | 75.5033 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-16 | Hnauman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Dholi |  | SUNIL KUMAR PAREWA | 6350491792 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-MPUR-ENB-G002 | I-RJ-MPUR-PMP-0010 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.3648 | 75.3314 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-16 | Hnauman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Ganvar |  | SATYANARAYAN SINGH | 7665666391 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-TDRS-ENB-I002 | I-RJ-TDRS-PMP-0008 | 2 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.1927 | 75.2508 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-14 | 2025-06-14 | 2025-06-16 | 2025-06-16 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Sawariya | [7 empty] | JLKD
I-RJ-MRTA-ENB-9064 | I-RJ-MRTA-PMP-0061 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 26.5303 | 74.078 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | Suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Dhaneriya Leel |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-NGUR-ENB-I021 | I-RJ-NGUR-PMP-0066 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2905 | 73.6161 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Barani |  | BHANWAR LAL LATIYAL | 8003714631 | BALU RAM | 8355811699 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-BWAR-ENB-6000 | I-RJ-BWAR-PMP-0001 | 2 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 25.8977 | 74.1748 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Lasani |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-MRTA-ENB-9056 | I-RJ-MRTA-PMP-0021 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 26.6514 | 73.9593 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | Suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Merta |  | Arif Khan | 6367853630 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-KSGR-ENB-9056 | I-RJ-KSGR-PMP-0039 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.3855 | 75.0951 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-16 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Arain |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-BHMN-ENB-9013 | I-RJ-BHMN-PMP-0007 | 1 | 1 | A6 I&C | Beawar | Ajmer | Rahul Outsource |  | Done | 25.9817 | 74.2969 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-16 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | lagetkheda |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-GGGR-ENB-G001 | I-RJ-GGGR-PMP-0081 | 3 | 1 | A6 I&C | Ganganagar | Ganganagar | Rohit & team |  | Done | 29.8018 | 73.8729 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR36 | 2025-06-15 | 2025-06-14 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Mahiyanwali |  | RAJESH KUMAR SHARMA | 6376917077 | SALIM KHAN | 6376642129 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-PISN-ENB-9028 | I-RJ-PISN-PMP-0008 | 3 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.4207 | 74.4029 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-17 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Pisangan |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-SRGR-ENB-9041 | I-RJ-SRGR-PMP-0039 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.3132 | 73.7182 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Victoria Hotel |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-KEIW-ENB-G002 | I-RJ-KEIW-PMP-0008 | 1/3 | 2 | A6 I&C | Beawar | Ajmer | Rajkumar & team |  | Done | 25.9362 | 74.715 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Badli |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-SRGR-ENB-G001 | I-RJ-SRGR-PMP-0057 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.4489 | 73.8772 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 70 | 0 | Lalpura Paliwala |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-KEIW-ENB-G001 | I-RJ-KEIW-PMP-0007 | 1/2/3 | 3 | A6 I&C | Beawar | Ajmer | Hanuman & Team |  | Done | 25.9066 | 74.7846 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | Deoliya Kalan |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-VJIG-ENB-I002 | I-RJ-VJIG-PMP-0018 | 1/3 | 2 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.3724 | 73.6244 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-17 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | BGM | [7 empty] | JLKD
I-RJ-NAWW-ENB-V001 | I-RJ-NAWW-PMP-0047 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0379 | 75.0654 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-14 | 2025-06-14 | 2025-06-14 | 2025-06-18 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Rajjas-Nagaur |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9076 | I-RJ-NAWW-PMP-0012 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0455 | 75.1031 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-18 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Govindi |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-VJNG-ENB-9010 | I-RJ-VJNG-PMP-0004 | 3 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.0229 | 74.4426 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Vijay Nagar |  | GOVIND JYOTISHI | 7891237598 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-NAWW-ENB-I010 | I-RJ-NAWW-PMP-0040 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.1124 | 75.1862 | GBT | 0 | A6 I&C , ATP11A & 11C |  | WIP | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-18 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Shimbhoopura |  | MANGEE LAL | 8078698924 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-JAAL-ENB-9014 | I-RJ-JAAL-PMP-0008 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.372 | 73.9813 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Burdi |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NAWW-ENB-H002 | I-RJ-NAWW-PMP-0030 | 1 | 1 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.1235 | 75.1475 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-18 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Sawatgarh |  | MANGEE LAL | 8078698924 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-G001 | I-RJ-NAWW-PMP-0026 | 1 | 1 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.1741 | 75.0701 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-18 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Muwana |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MSUD-ENB-I001 | I-RJ-MSUD-PMP-0018 | 3 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.0295 | 74.4791 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR32 | 2025-06-04 | 2025-06-04 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Nandwara |  | GOVIND JYOTISHI | 7891237598 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-JAAL-ENB-G004 | I-RJ-JAAL-PMP-0053 | 1/2 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2455 | 74.0929 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-18 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Dugastau |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-VJIG-ENB-9041 | I-RJ-VJIG-PMP-0010 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.362 | 73.412 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Rai Singh Nagar |  | SURENDER SINGH | 8955001723 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JLKD
I-RJ-JAAL-ENB-9062 | I-RJ-JAAL-PMP-0010 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0489 | 74.1067 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Mundi |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-VJIG-ENB-9019 | I-RJ-VJIG-PMP-0003 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.2849 | 73.5011 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Vijay Nagar | [7 empty] | JLKD
I-RJ-VJIG-ENB-9029 | I-RJ-VJIG-PMP-0007 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.3998 | 73.5892 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-18 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Shri Vijay Nagar |  | SURENDER SINGH | 8955001723 | SANTOSH KUMAR | 6350491304 | RAJA RAM | 8003992944 | JLKD
I-RJ-MKRN-ENB-I012 | I-RJ-MKRN-PMP-0041 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.165 | 74.5773 | GBT | 0 | A6 I&C , ATP11A & 11C | Doen/11C Pending |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-12 | 2025-06-12 | 2025-06-12 | 2025-06-19 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | RAITHALIYA |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-I041 | I-RJ-DDWN-PMP-0038 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.1527 | 74.4797 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-19 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | KHARWALIYA |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-AJMR-ENB-V028 | I-RJ-AJMR-PMP-0280 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | 26.4601 | 74.6545 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Kundan nagar |  | Abdullah Khan | 6350491827 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-RSNG-ENB-I003 | I-RJ-RSNG-PMP-0019 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.5943 | 73.5303 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Kikrawali |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-RSNG-ENB-9053 | I-RJ-RSNG-PMP-0013 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.5703 | 73.4473 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR36 | 2025-06-15 | 2025-06-14 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | RB Bus Stand |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-MKRN-ENB-I014 | I-RJ-MKRN-PMP-0042 | 2 | 1 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0825 | 74.4735 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-19 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Beenjari |  | JITENDRA PATIDAR | 6350491976 | SUKHDEV ROYAL | 9672742052 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DDWN-ENB-I039 | I-RJ-DDWN-PMP-0036 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.2312 | 74.5451 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-19 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | KHOJAS |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MKRN-ENB-I002 | I-RJ-MKRN-PMP-0039 | 2 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.1264 | 74.6759 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Deori |  | Prema Dahiya | 6350491992 | MAHENDRA NEHRA | 6350491087 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PASS-ENB-G005 | I-RJ-PASS-PMP-0020 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.81 | 74.5902 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Bagot |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-RSNG-ENB-9034 | I-RJ-RSNG-PMP-0009 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.5174 | 73.487 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Chak 9TK |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-DDWN-ENB-I007 | I-RJ-DDWN-PMP-0019 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.1813 | 74.5332 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | BC_Toshina infill |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DENA-ENB-9014 | I-RJ-DENA-PMP-0010 | 2 | 1 | A6 I&C | Makrana | Nagaur | Suresh Outsource |  | Done | 26.8621 | 74.039 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-15 | 2025-06-15 | 2025-06-15 | 2025-06-17 | Suresh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Chackdhani |  | IMARAN KHAN | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-PASS-ENB-9030 | I-RJ-PASS-PMP-0010 | 2 | 1 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.8219 | 74.6372 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-23 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Kanwalad |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PASS-ENB-9009 | I-RJ-PASS-PMP-0006 | 3 | 1 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.8352 | 74.6967 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-19 | 2025-06-19 | 2025-06-19 | 2025-06-19 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Rohindi |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PASS-ENB-V001 | I-RJ-PASS-PMP-0022 | 2 | 1 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.9202 | 74.7119 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-20 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Kinsreya-Nagaur |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PASS-ENB-6002 | I-RJ-PASS-PMP-0004 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.9657 | 74.6964 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | BIDIYAD | [7 empty] | JLJH
I-RJ-MKRN-ENB-9012 | I-RJ-MKRN-PMP-0029 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 26.9432 | 74.6552 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Makrana | [7 empty] | JLJH
I-RJ-DDWN-ENB-9014 | I-RJ-DDWN-PMP-0006 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.4488 | 74.523 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-20 | vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Ajawa |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-ANGR-ENB-H003 | I-RJ-ANGR-PMP-0015 | 1/2/3 | 3 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 28.9998 | 73.1731 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-20 | 2025-06-20 | 2025-06-20 | Done | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Dhapar |  | CHET RAM | 6350492121 | Vinod Kumar | 6350492215 | RAJA RAM | 8003992944 | JLKD
I-RJ-TSCC-ENB-I001 | I-RJ-TSCC-PMP-0001 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.0208 | 73.1254 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | 22AS-B |  | CHET RAM | 6350492121 | Vinod Kumar | 6350492215 | RAJA RAM | 8003992944 | JLKD
I-RJ-MENW-ENB-G001 | I-RJ-MENW-PMP-0005 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 26.6477 | 73.7405 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-18 | 2025-06-18 | 2025-06-18 | 2025-06-20 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | Sanusun Colony |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MKRN-ENB-V004 | I-RJ-MKRN-PMP-0070 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0195 | 74.7148 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-17 | 2025-06-20 | 2025-06-20 | 2025-06-20 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Makrana Parbatsar road |  | Chiranji Lal | 6350491964 | Devilal Gurjar | 8078699370 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MRTA-ENB-9115 | I-RJ-MRTA-PMP-0068 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 26.7882 | 73.8251 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-20 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | MERTA |  | Arif Khan | 6367853630 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DDWN-ENB-H002 | I-RJ-DDWN-PMP-0017 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3792 | 74.6888 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-17 | 2025-06-17 | 2025-06-17 | 2025-06-21 | Sandeep & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Phogri |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MRTA-ENB-I005 | I-RJ-MRTA-PMP-0036 | 1/3 | 2 | A6 I&C | Nagaur | Nagaur | Rajkumar & team |  | Done | 26.5368 | 74.0284 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-20 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | AAKELI |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-ANGR-ENB-I005 | I-RJ-ANGR-PMP-0017 | 1/2/3 | 3 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 28.9535 | 73.058 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | 3MLDB |  | CHET RAM | 6350492121 | Vinod Kumar | 6350492215 | RAJA RAM | 8003992944 | JLKD
I-RJ-GGGR-ENB-0009 | I-RJ-GGGR-PMP-0006 | 2/3 | 2 | A6 I&C | Ganganagar | Ganganagar | Rohit & team |  | Done | 29.9177 | 73.8881 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR36 | 2025-06-15 | 2025-06-14 | 2025-06-16 | 2025-06-16 | 2025-06-16 | 2025-06-16 | Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 10 | 0 | Meera Chowk |  | MADAN LAL | 9649987829 | SALIM KHAN | 9588220230 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-KSGR-ENB-I026 | I-RJ-KSGR-PMP-0092 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.5733 | 74.8494 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Fatehlal nagar |  | RAJU YADAV | 6376917822 | RAKESH KUMAR | 8740029627 | 6377201337 | MAHESH KUMAR | JLKD
I-RJ-KSGR-ENB-I027 | I-RJ-KSGR-PMP-0091 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.5656 | 74.8763 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Rajkumar & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Deshwali Mohalla |  | RAJU YADAV | 6376917822 | RAKESH KUMAR | 8740029627 | 6377201337 | MAHESH KUMAR | JLKD
I-RJ-PSKR-ENB-I003 | I-RJ-PSKR-PMP-0009 | 3 | 1 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | 26.4906 | 74.5517 | RTP | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Rajkumar & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Pushkar |  | Raj Kumar | 6350491825 | VACANT | VACANT | 0 | MAHESH KUMAR | JLKD
I-RJ-AJMR-ENB-G001 | I-RJ-AJMR-PMP-0176 | 1/3 | 2 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | 26.3723 | 74.5076 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR30 | 2025-06-02 | 2025-06-02 | 2025-06-13 | 2025-06-13 | 2025-06-13 | 2025-06-22 | Manaut | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Bhawta |  | Rakesh Paroda | 6350491793 | MOHAN SINGH | 9568428114 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-NAWW-ENB-G004 | I-RJ-NAWW-PMP-0028 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Hanuman & team |  | Done | 27.2312 | 74.9833 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | Kukanwali | [7 empty] | JLJH
I-RJ-DDWN-ENB-9058 | I-RJ-DDWN-PMP-0007 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3312 | 74.7711 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Sandeep Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Dabada | [7 empty] | JLJH
I-RJ-DDWN-ENB-I021 | I-RJ-DDWN-PMP-0024 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.2999 | 74.7868 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Sandeep Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Baori | [7 empty] | JLJH
I-RJ-PASS-ENB-9047 | I-RJ-PASS-PMP-0014 | 1 | 1 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.993 | 74.771 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | parbatsar | [7 empty] | JLJH
I-RJ-NAWW-ENB-I001 | I-RJ-NAWW-PMP-0032 | 2 | 1 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 27.0117 | 74.8031 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Maglana |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I021 | I-RJ-NAWW-PMP-0045 | 3 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & team |  | Done | 27.2584 | 75.0408 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Nalot | [7 empty] | JLJH
I-RJ-NGUR-ENB-9009 | I-RJ-NGUR-PMP-0037 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1767 | 73.7689 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | vikram & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Mundwa | [7 empty] | JLJH
I-RJ-PASS-ENB-A001 | I-RJ-PASS-PMP-0015 | 1 | 1 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.9553 | 74.768 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Khokhar | [7 empty] | JLJH
I-RJ-NGUR-ENB-6004 | I-RJ-NGUR-PMP-0025 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1323 | 73.821 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | vikram & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | INANA | [7 empty] | JLJH
I-RJ-SRGR-ENB-9012 | I-RJ-SRGR-PMP-0029 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.2329 | 73.9086 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Rajpura Piparan |  | DINESH KUMAR | 9549866266 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-NAWW-ENB-H001 | I-RJ-NAWW-PMP-0029 | 1 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & team |  | Done | 27.3178 | 75.0336 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-21 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 70 | 0 | Todas | [7 empty] | JLJH
I-RJ-AJMR-ENB-I050 | I-RJ-AJMR-PMP-0297 | 1/2 | 2 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | 26.608 | 74.6907 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-22 | Manaut | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | NARWAR |  | GYAN SINGH RAWAT | 7014970918 | JITENDRA KANOJIYA | 6375556812 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KESR-ENB-9028 | I-RJ-KESR-PMP-0003 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9714 | 73.4026 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | VIKRAM & TEAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Khimsar |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DDWN-ENB-I038 | I-RJ-DDWN-PMP-0035 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3604 | 74.8526 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | sandeep & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Dausar | [7 empty] | JLJH
I-RJ-NAWW-ENB-Y001 | I-RJ-NAWW-PMP-0049 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 27.0571 | 74.8493 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  | only two sectors can be claimed due to work order issue | 150 | 105 | 0 | Kuchaman City | [7 empty] | JLJH
I-RJ-NAWW-ENB-9045 | I-RJ-NAWW-PMP-0002 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 27.0984 | 74.849 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Kuchaman city, | [7 empty] | JLJH
I-RJ-KCMC-ENB-9001 | I-RJ-KCMC-PMP-0012 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 27.1589 | 74.8343 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | kuchaman city | [7 empty] | JLJH
I-RJ-NAWW-ENB-I002 | I-RJ-NAWW-PMP-0033 | 1 | 1 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 27.1651 | 74.7827 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | RANWA | [7 empty] | JLJH
I-RJ-NAWW-ENB-9055 | I-RJ-NAWW-PMP-0004 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.1759 | 74.9016 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Deep Pura | [7 empty] | JLJH
I-RJ-NAWW-ENB-9073 | I-RJ-NAWW-PMP-0010 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.1436 | 74.9057 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Hurani | [7 empty] | JLJH
I-RJ-NAWW-ENB-G002 | I-RJ-NAWW-PMP-0027 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.3455 | 75.0834 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Lalas |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I006 | I-RJ-NAWW-PMP-0036 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.1852 | 75.1064 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-22 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | RAJLIYA | [7 empty] | JLJH
I-RJ-LDNU-ENB-I017 | I-RJ-LDNU-PMP-0030 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.6049 | 74.6521 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-23 | 2025-06-23 | 2025-06-23 | sandeep & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Reengan | [7 empty] | JLJH
I-RJ-AJMR-ENB-0384 | I-RJ-AJMR-PMP-0266 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | 0 | 0 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | opposite PNB bank main Vaishali nagar road |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-KSGR-ENB-I025 | I-RJ-KSGR-PMP-0063 | 1/3 | 2 | A6 I&C | Kishangarh | Ajmer | Rahul Outsource |  | Done | 26.6149 | 74.8527 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Paryavaran Marg |  | Jaiveer Singh Rajawat | 6350491819 | CHANDRA PRAKASH | 8432556352 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-PASS-ENB-9032 | I-RJ-PASS-PMP-0011 | 1 | 1 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.7866 | 74.5633 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR37 | 2025-06-15 | 2025-06-14 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Parbatsar |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DDWN-ENB-9090 | I-RJ-DDWN-PMP-0010 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.413 | 74.598 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | sandeep & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Didwana | [7 empty] | JLJH
I-RJ-DDWN-ENB-H001 | I-RJ-DDWN-PMP-0016 | 1/3 | 2 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.4705 | 74.5126 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | inghana,Singhana | [7 empty] | JLJH
I-RJ-DENA-ENB-9085 | I-RJ-DENA-PMP-0018 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.8809 | 74.2486 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-24 | 2025-06-24 | 2025-06-24 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Jalsu | [7 empty] | JLJH
I-RJ-LDNU-ENB-9011 | I-RJ-LDNU-PMP-0015 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.569 | 74.435 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-23 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Bakliya | [7 empty] | JLJH
I-RJ-NAWW-ENB-I019 | I-RJ-NAWW-PMP-0044 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.0342 | 74.9398 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-24 | 2025-06-24 | 2025-06-24 | hanman & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Khairdya | [7 empty] | JLJH
I-RJ-DENA-ENB-A004 | I-RJ-DENA-PMP-0024 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 26.8608 | 74.234 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR41 | 2025-06-21 | 2025-06-21 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Jalsu Kalan |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-6005 | I-RJ-NAWW-PMP-0053 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.0189 | 74.9984 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | NAWA |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I008 | I-RJ-NAWW-PMP-0038 | 1 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 26.9875 | 75.1607 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | Hanuman & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | CHOSLA | [7 empty] | JLJH
I-RJ-BEWR-ENB-A007 | I-RJ-BEWR-PMP-0040 | 1/2 | 2 | A6 I&C | Beawar | Ajmer | Rajkumar & team |  | Done | 25.9632 | 74.2294 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  | only single sector can be claimed due to work order issue | 100 | 55 | 0 | Bhambipura |  | SHAITAN SINGH RAJPUT | 9783012110 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BEWR-ENB-A004 | I-RJ-BEWR-PMP-0075 | 1/2/3 | 3 | A6 I&C | Beawar | Ajmer | Rajkumar & team |  | Done | 26.0959 | 74.304 | RTP | 0 | A6 I&C , ATP11A & 11C |  | pole mount inst done | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Bapu Nagar03 |  | NEMI CHAND | 9680086665 | Keshar Singh Chouhan | 6376917831 | 6376917831 | MUKESH PRAJAPAT | JLKD
I-RJ-LDNU-ENB-I021 | I-RJ-LDNU-PMP-0032 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.6075 | 74.4084 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Dujar | [7 empty] | JLJH
I-RJ-LDNU-ENB-I010 | I-RJ-LDNU-PMP-0027 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.47 | 74.3558 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-24 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | GenanaCOW NN |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-LDNU-ENB-9044 | I-RJ-LDNU-PMP-0019 | 1/2 | 2 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.3761 | 74.328 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | dhurila | [7 empty] | JLJH
I-RJ-JAAL-ENB-I004 | I-RJ-JAAL-PMP-0024 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.4102 | 74.1132 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-20 | 2025-06-20 | 2025-06-20 | 2025-06-24 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | GUGRIYALI |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-I017 | I-RJ-DDWN-PMP-0022 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.2669 | 74.5329 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | Sandeep & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | KHARESH | [7 empty] | JLJH
I-RJ-JAAL-ENB-9078 | I-RJ-JAAL-PMP-0012 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0319 | 73.9368 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-24 | 2025-06-24 | 2025-06-24 | 2025-06-24 | vikram & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Jhunjhala | [7 empty] | JLJH
I-RJ-DDWN-ENB-G006 | I-RJ-DDWN-PMP-0014 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3058 | 74.7327 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-24 | 2025-06-26 | 2025-06-24 | 2025-06-26 | Sandeep Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 210 | 80 | 0 | Molasar |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MSUD-ENB-G002 | I-RJ-MSUD-PMP-0009 | 1/2 | 2 | A6 I&C | Beawar | Ajmer | Aneesh & Team |  | Done | 25.959 | 74.5037 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR35 | 2025-06-13 | 2025-06-13 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | HANOOTIYA |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-DDWN-ENB-I043 | I-RJ-DDWN-PMP-0040 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.2714 | 74.3441 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | BANTHADI | [7 empty] | JLJH
I-RJ-DDWN-ENB-I016 | I-RJ-DDWN-PMP-0021 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Aneesh & team |  | Done | 27.1657 | 74.4475 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | Mandookara |  | OMVEER SINGH | 9887268550 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-I004 | I-RJ-DDWN-PMP-0018 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Aneesh & team |  | Done | 27.1013 | 74.361 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | PAWA | [7 empty] | JLJH
I-RJ-DDWN-ENB-G001 | I-RJ-DDWN-PMP-0012 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Rohit & team |  | Done | 27.2981 | 74.3931 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-25 | rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 210 | 80 | 0 | Keraap |  | OMVEER SINGH | 9887268550 | SUKHDEV ROYAL | 9672742052 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-TDRS-ENB-G002 | I-RJ-TDRS-PMP-0006 | 3 | 1 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 26.12 | 75.5279 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR42 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 70 | 0 | Bawdi |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-TONK-ENB-G001 | I-RJ-TONK-PMP-0035 | 2 | 1 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 26.1211 | 75.7206 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR42 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 70 | 0 | Dorda Hindi |  | Anil Kumar Chouhan | 6350491771 | SATYANARAYAN BAIRWA | 9509017588 | VACANT | VACANT | JLKD
I-RJ-DBZU-ENB-9001 | I-RJ-DBZU-PMP-0001 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.8735 | 75.6017 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Rajkumar & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Dooni |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | 7665118671 | VACANT | JLKD
I-RJ-UNRA-ENB-9006 | I-RJ-UNRA-PMP-0005 | 1 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.0132 | 75.913 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Rajkumar & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Kakor |  | Anil Kumar Chouhan | 6350491771 | Hansraj Gurjar | 6376917825 | 8104894205 | VACANT | JLKD
I-RJ-MRTA-ENB-9027 | I-RJ-MRTA-PMP-0014 | 2/3 | 2 | A6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.7442 | 73.8744 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Kumpada | [7 empty] | JLJH
I-RJ-KESR-ENB-9058 | I-RJ-KESR-PMP-0008 | 1/3 | 2 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9091 | 73.38 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | vikram & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Nagri | [7 empty] | JLJH
I-RJ-LDNU-ENB-9053 | I-RJ-LDNU-PMP-0021 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.534 | 74.456 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR42 | 2025-06-23 | 2025-06-23 | 2025-06-26 | 2025-06-26 | 2025-06-26 | 2025-06-26 | Sandeep Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Ladnu |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MPUR-ENB-9049 | I-RJ-MPUR-PMP-0008 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Dileep & team |  | Done | 26.3002 | 75.2265 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR33 | 2025-06-06 | 2025-06-06 | 2025-06-08 | 2025-06-09 | 2025-06-09 | 2025-06-27 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Malpura |  | MUKESH KUMAR GURJAR | 7850035105 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-BSTL-ENB-V001 | I-RJ-BSTL-PMP-0003 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 26.4057 | 75.8612 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR40 | 2025-06-20 | 2025-06-20 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Vanasthalivilla |  | BABU LAL GURJAR | 7976922712 | JAL SINGH KOLI | 9680431625 | 9680431625 | VACANT | JLKD
I-RJ-MRTA-ENB-I010 | I-RJ-MRTA-PMP-0037 | 1/2 | 2 | A6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.6576 | 73.862 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Lamba Jatan | [7 empty] | JLJH
I-RJ-NSRB-ENB-G001 | I-RJ-NSRB-PMP-0012 | 1/2 | 2 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.392 | 74.8506 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR43 | 2025-06-25 | 2025-06-25 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Rajkumar & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 140 | 140 | 0 | Kanpura |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 |  |  | JLKD
I-RJ-NWAI-ENB-9009 | I-RJ-NWAI-PMP-0008 | 1 | 1 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 26.4979 | 76.0257 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR35 | 2025-06-13 | 2025-06-13 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | KheredaBujurg |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-NGUR-ENB-H006 | I-RJ-NGUR-PMP-0061 | 1/3 | 2 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9612 | 73.9108 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Vikram Jangid Nagaur team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Gajoo |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-AJMR-ENB-0095 | I-RJ-AJMR-PMP-0061 | 2 | 1 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | 26.4394 | 74.6392 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR44 | 2025-06-26 | 2025-06-26 | 2025-06-27 | 2025-06-27 | 2025-06-27 | 2025-06-27 | Rajkumar & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | Near Petrol Pump |  | SURENDRA SINGH | 9929463865 | MOHAN SINGH | 9568428114 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-NGUR-ENB-9097 | I-RJ-NGUR-PMP-0051 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.162 | 73.7109 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-24 | 2025-06-24 | 2025-06-26 | [6 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Nagaur | [7 empty] | JLJH
I-RJ-NAWW-ENB-9098 | I-RJ-NAWW-PMP-0054 | 3 | 1 | A6 I&C | Makrana | Nagaur | Hanuman & Team |  | Done | 27.2697 | 75.0716 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-21 | 2025-06-21 | 2025-06-21 | 2025-06-27 | Sandeep & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | LAMBA |  | MANGEE LAL | 8078698924 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KCRA-ENB-6000 | I-RJ-KCRA-PMP-0001 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9861 | 73.9657 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-22 | 2025-06-22 | 2025-06-22 | 2025-06-28 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 105 | 0 | KUCHERA | [7 empty] | JLJH
I-RJ-MRTA-ENB-9084 | I-RJ-MRTA-PMP-0027 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.6626 | 73.7388 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Gotan | [7 empty] | JLJH
I-RJ-NGUR-ENB-0066 | I-RJ-NGUR-PMP-0082 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1862 | 73.7563 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR41 | 2025-06-21 | 2025-06-21 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-27 | vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Behind Ganga Singh Hotel |  | SUNIL KUMAR | 9412607678 | NENA RAM | 7627076857 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-G003 | I-RJ-DENA-PMP-0028 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Aneesh & team |  | Done | 27.0116 | 74.1633 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-24 | 2025-06-28 | 2025-06-24 | 2025-06-28 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 120 | 0 | Sanjoo | [7 empty] | JLJH
I-RJ-MRTA-ENB-I008 | I-RJ-MRTA-PMP-0045 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.4932 | 74.0749 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 | Rohit & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | SAMDOLAO KHURD | [7 empty] | JLJH
I-RJ-DDWN-ENB-A001 | I-RJ-DDWN-PMP-0011 | 1/3 | 2 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.4462 | 74.6463 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR44 | 2025-06-26 | 2025-06-26 | 2025-06-29 | 2025-06-29 | 2025-06-29 | 2025-06-29 | Sandeep Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 140 | 140 | 0 | Soopka |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NGUR-ENB-G001 | I-RJ-NGUR-PMP-0059 | 1/2 | 2 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2364 | 73.6515 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR44 | 2025-06-26 | 2025-06-26 | 2025-06-29 | 2025-06-30 | 2025-06-30 | 2025-06-30 | Vikram Jangid Nagaur team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 140 | 75 | 0 | Gogelao |  | BHANWAR LAL LATIYAL | 8003714631 | BALU RAM | 8355811699 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SBTE-ENB-I001 | I-RJ-SBTE-PMP-0001 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Suresh Outsource |  | Done | 27.4275 | 73.5444 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-06-23 | 2025-06-23 | 2025-06-23 | 2025-06-29 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Shribalaji | [7 empty] | JLJH
I-RJ-KEIW-ENB-I005 | I-RJ-KEIW-PMP-0011 | 2 | 1 | A6 I&C | Beawar | Ajmer | Rajkumar & team |  | Done | 25.9311 | 74.8995 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-06-25 | 2025-06-25 | 2025-06-25 | 2025-06-30 | Manaut | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | NANDSI |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-DDWN-ENB-Y001 | I-RJ-DDWN-PMP-0041 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.4747 | 74.6966 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR44 | 2025-06-26 | 2025-06-26 | 2025-06-30 | 2025-06-30 | 2025-06-30 | 2025-06-30 | sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 140 | 75 | 0 | Dearathi / Lalasari |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NAWW-ENB-I009 | I-RJ-NAWW-PMP-0039 | 3 | 1 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.3207 | 74.9203 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-07-02 | 2025-07-02 | 2025-07-02 | 2025-07-02 | sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | PAREWADI | [7 empty] | JLJH
I-RJ-NAWW-ENB-A003 | I-RJ-NAWW-PMP-0020 | 3 | 1 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.1268 | 75.023 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-07-03 | 2025-07-03 | 2025-07-03 | 2025-07-03 | sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Bhooni | [7 empty] | JLJH
I-RJ-KSGR-ENB-G003 | I-RJ-KSGR-PMP-0048 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 26.4196 | 74.9721 | GBT | 0 | A6 I&C , ATP11A & 11C |  | HONEYBEE ISSUE | Allotment- AIR34 | 2025-06-09 | 2025-06-10 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | aneesh & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 125 | 0 | Dadiya |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KSGR-ENB-G004 | I-RJ-KSGR-PMP-0049 | 1/3 | 2 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.3463 | 75.0271 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR35 | 2025-06-13 | 2025-06-13 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-07-04 | rajkumar & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 100 | 0 | Ankodiya |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-DENA-ENB-I009 | I-RJ-DENA-PMP-0034 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9057 | 74.135 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR31 | 2025-06-03 | 2025-06-03 | 2025-07-05 | 2025-07-05 | 2025-07-05 | 2025-07-05 | vikram jangid | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | BHADWASI |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-I014 | I-RJ-DENA-PMP-0035 | 2 | 1 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.8091 | 74.3607 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR39 | 2025-06-19 | 2025-06-19 | 2025-07-09 | 2025-07-09 | 2025-07-09 | 2025-07-09 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Pundlota (New) 1 | [7 empty] | JLJH
I-RJ-TOON-ENB-G001 | I-RJ-TOON-PMP-0004 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 26.2041 | 75.6106 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR42 | 2025-06-23 | 2025-06-23 | 2025-07-12 | 2025-07-12 | 2025-07-12 | 2025-07-12 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Naner |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-KKRI-ENB-6003 | I-RJ-KKRI-PMP-0002 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 25.8064 | 75.0466 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR38 | 2025-06-18 | 2025-06-18 | 2025-06-25 | 2025-07-07 | 2025-07-07 | 2025-07-11 | MANAUT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 70 | 0 | Kadera |  | Asharam Meena | 6350491763 | MANISH MEENA | 6350491497 | VACANT | VACANT | JLKD
I-RJ-NWAI-ENB-6004 | I-RJ-NWAI-PMP-0004 | 1/3 | 2 | A6 I&C | Tonk | Ajmer |  |  | MRN Done | 26.4988 | 76.0671 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR32 | 2025-06-04 | 2025-06-04 | [10 empty] | NO | YES | FINALIZED |  |  | Not Ready |  |  | 120 | 65 | 0 | Shrirajdhirajpura |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-AJMR-ENB-0388 | I-RJ-AJMR-PMP-0275 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rajkumar & team |  | Done | #N/A | #N/A | NBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR45 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | RAJKUMAR & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Kiranipura |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-BARW-ENB-6000 | I-RJ-BARW-PMP-0002 | 1/2/3 | 3 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 26.2775 | 74.8772 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR45 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | RAMSAR-RJ5NSRB002B |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-BEWR-ENB-0031 | I-RJ-BEWR-PMP-0008 | 3 | 1 | A6 I&C | Beawar | Ajmer | Rajkumar & team |  | Done | 26.0991 | 74.2799 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR45 | 2025-07-12 | 2025-07-12 | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | RAJKUMAR & Team | [5 empty] | NO | NO | NA |  |  | Ready |  | rajkumar and aneesh done this site jointly | 30 | 30 | 0 | Senadera Road |  | NEMI CHAND | 9680086665 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-DDWN-ENB-I036 | I-RJ-DDWN-PMP-0033 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.4036 | 74.7491 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR45 | 2025-07-12 | 2025-07-12 | 2025-07-14 | 2025-07-14 | 2025-07-14 | 2025-07-14 | Sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 0 | Deedarpura |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SRWR-ENB-9041 | I-RJ-SRWR-PMP-0019 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rajkumar & team |  | Done | 26.1284 | 74.8654 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR45 | 2025-07-12 | 2025-07-12 | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | RAJKUMAR & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Sarwar |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-SRWR-ENB-X001 | I-RJ-SRWR-PMP-0014 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 25.9559 | 75.0276 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR45 | 2025-07-12 | 2025-07-12 | 2025-07-15 | 2025-07-15 | 2025-07-15 | 2025-07-15 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Jaliya III |  | Bhagchand Saini | 6350491762 | MAHENDRA KUMAR GURJAR | 7665768296 | VACANT | VACANT | JLKD
I-RJ-NWAI-ENB-G001 | I-RJ-NWAI-PMP-0021 | 2 | 1 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 26.2943 | 76.1129 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR46 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Jaamoli |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-TDRS-ENB-9024 | I-RJ-TDRS-PMP-0002 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 26.0372 | 75.3623 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR46 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-18 | Aneesh & Team | [5 empty] | NO | NO | NA |  |  | Ready |  | 11A DONE BY RAJKUMAR DATED 21 JULY | 100 | 55 | 0 | Dumba |  | Kaluram Saini | 9024462428 | DIYARAM GURJAR | 9509017588 | VACANT | VACANT | JLKD
I-RJ-JAAL-ENB-G006 | I-RJ-JAAL-PMP-0021 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1391 | 74.1269 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR45 | 2025-07-12 | 2025-07-12 | 2025-07-18 | 2025-07-18 | 2025-07-18 | 2025-07-21 | Sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Tarnau |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KSGR-ENB-9063 | I-RJ-KSGR-PMP-0100 | 1/3 | 2 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 26.7485 | 74.9782 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-20 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 45 | 0 | Narena |  | KAILASH CHAND RAIGER | 7014767214 | RAVIRAJ MEGHWAL | 9783998177 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-TOON-ENB-9035 | I-RJ-TOON-PMP-0018 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.3836 | 75.6432 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-20 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Piplu |  | Brij Mohan Gurjar | 9024462337 | VACANT | VACANT | VACANT | VACANT | JLKD
I-RJ-TOON-ENB-H002 | I-RJ-TOON-PMP-0019 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.3273 | 75.6706 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-20 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Sandera |  | Brij Mohan Gurjar | 9024462337 | VACANT | VACANT | VACANT | VACANT | JLKD
I-RJ-BEWR-ENB-V006 | I-RJ-BEWR-PMP-0057 | 3 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.0969 | 74.2708 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR46 | 2025-07-16 | 2025-07-17 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Ramsar Balaiyan(Ajm-Jdp Hwy) |  | NEMI CHAND | 9680086665 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-DOLI-ENB-9043 | I-RJ-DOLI-PMP-0032 | 1/3 | 2 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.9813 | 75.3211 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 55 | 0 | deoli |  | SAURABH GAUTTAM | 8947973523 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-I007 | I-RJ-DOLI-PMP-0034 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.9131 | 75.3358 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-21 | 2025-07-21 | 2025-07-21 | 2025-07-21 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Thanwala |  | Chetan Prakash Jat | 6350491764 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DBZU-ENB-9001 | I-RJ-DBZU-PMP-0001 | 1/2 | 2 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.8735 | 75.6017 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR46 | 2025-07-16 | 2025-07-17 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Dooni |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-9045 | I-RJ-DOLI-PMP-0031 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.895 | 75.7424 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Dooni |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-9049 | I-RJ-DOLI-PMP-0037 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.9078 | 75.7817 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-22 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Getota |  | BHANWAR SINGH HADDA | 8905736454 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-TONK-ENB-9038 | I-RJ-TONK-PMP-0054 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.9752 | 75.6679 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Bharni |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-DOLI-ENB-H003 | I-RJ-DOLI-PMP-0030 | 3 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 25.9251 | 75.2741 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Beejwar |  | Chetan Prakash Jat | 6350491764 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-KSGR-ENB-9017 | I-RJ-KSGR-PMP-0037 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 26.5137 | 74.9543 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR46 | 2025-07-16 | 2025-07-17 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-24 | Manaut Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Arain |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-KEIW-ENB-9017 | I-RJ-KEIW-PMP-0023 | 3 | 1 | A6 I&C | Beawar | Ajmer | Rajkumar & team |  | Done | 26.0999 | 74.7363 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR48 | 2025-07-21 | 2025-07-22 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Bhinay |  | GOVIND JYOTISHI | 7891237598 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-PASS-ENB-0003 | I-RJ-PASS-PMP-0003 | 2 | 1 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 26.9908 | 74.6957 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-18 | 2025-07-24 | 2025-07-24 | 2025-07-24 | 2025-07-24 | Sandeep | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 30 | 0 | Milan Marble Traders |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-SRGR-ENB-0003 | I-RJ-SRGR-PMP-0003 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.3285 | 73.9064 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-23 | 2025-07-23 | 2025-07-23 | 2025-07-23 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Charan Singh Chowk |  | DINESH KUMAR | 9549866266 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-AJMR-ENB-0385 | I-RJ-AJMR-PMP-0299 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4088 | 74.6592 | NBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-24 | Manaut Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Parbatpura bypass |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-NSRB-ENB-G003 | I-RJ-NSRB-PMP-0013 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 26.2518 | 74.793 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR46 | 2025-07-16 | 2025-07-17 | 2025-07-21 | 2025-07-24 | 2025-07-24 | 2025-07-24 | Rajkumar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | Loharwada |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-NGUR-ENB-0065 | I-RJ-NGUR-PMP-0110 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 27.2083 | 73.7361 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-18 | 2025-07-22 | 2025-07-22 | 2025-07-22 | 2025-07-25 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 40 | 0 | Near Bakhat sagar park |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLJH
I-RJ-KKRI-ENB-I016 | I-RJ-KKRI-PMP-0026 | 2/3 | 2 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 25.9022 | 75.2221 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR49 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 65 | 0 | Kaleda | [7 empty] | JLKD
I-RJ-KKRI-ENB-9043 | I-RJ-KKRI-PMP-0024 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 25.9302 | 75.1354 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Ugai |  | Asharam Meena | 6350491763 | MANISH MEENA | 6350491497 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-I006 | I-RJ-DOLI-PMP-0033 | 2 | 1 | A6 I&C | Tonk | Ajmer | Aneesh & team |  | Done | 25.8935 | 75.2879 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-25 | 2025-07-25 | 2025-07-25 | 2025-07-25 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | MLR 0011 (Barla) |  | Chetan Prakash Jat | 6350491764 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-MNDW-ENB-9014 | I-RJ-MNDW-PMP-0006 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Sandeep Outsource |  | Done | 27.0657 | 73.8233 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR48 | 2025-07-21 | 2025-07-22 | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-07-27 | Sanddep | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Village Post Mundwa |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-UNRA-ENB-I003 | I-RJ-UNRA-PMP-0030 | 3 | 1 | A6 I&C | Tonk | Ajmer | Aneesh & Team |  | Done | 25.9671 | 75.8192 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR49 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-07-27 | Aneees | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | BINJARI | [7 empty] | JLKD
I-RJ-MPUR-ENB-I002 | I-RJ-MPUR-PMP-0011 | 1 | 1 | A6 I&C | Tonk | Ajmer | Aneesh & Team |  | Done | 26.3048 | 75.2877 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR49 | 2025-07-23 | 2025-07-24 | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-07-27 | Aneees | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | ROOPAHELI | [7 empty] | JLKD
I-RJ-NSRB-ENB-9036 | I-RJ-NSRB-PMP-0029 | 1 | 1 | A6 I&C | Kishangarh | Ajmer | Aneesh & team |  | Done | 26.3256 | 74.9611 | GBT | 0 | A6 I&C , ATP11A & 11C | sfp faulty |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-20 | 2025-07-20 | 2025-07-28 | Aneees | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 40 | 0 | Nasirabad |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-MPUR-ENB-H004 | I-RJ-MPUR-PMP-0036 | 2 | 1 | A6 I&C | Tonk | Ajmer | Rajkumar & team |  | Done | 26.4257 | 75.6021 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR48 | 2025-07-21 | 2025-07-22 | 2025-07-27 | 2025-07-27 | 2025-07-27 | 2025-07-27 | Rajkkuar | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Arniya Kanker |  | SUNIL KUMAR PAREWA | 6350491792 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JLKD
I-RJ-MSUD-ENB-I006 | I-RJ-MSUD-PMP-0022 | 2 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & Team |  | Done | 26.1754 | 74.5995 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR49 | 2025-07-23 | 2025-07-24 | 2025-07-28 | 2025-07-28 | 2025-07-29 | 2025-08-13 | Manaut Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | KERIA/DAULATPURA | [7 empty] | JLKD
I-RJ-DENA-ENB-9008 | I-RJ-DENA-PMP-0007 | 2 | 1 | A6 I&C | Makrana | Nagaur | Rahul Outsource |  | Done | 26.544 | 74.5087 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-18 | 2025-07-26 | 2025-07-26 | 2025-07-27 | 2025-07-30 | Rahul Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Badi Ghati |  | NATHU RAM | 9664263744 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KCMC-ENB-9006 | I-RJ-KCMC-PMP-0020 | 1/2 | 2 | A6+B6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 27.2646 | 74.8907 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR50 | 2025-07-25 | 2025-07-25 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 10 | 0 | Sabalpura | [7 empty] | JLJH
I-RJ-NGUR-ENB-9074 | I-RJ-NGUR-PMP-0081 | 1/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0786 | 73.574 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR48 | 2025-07-21 | 2025-07-21 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 10 | 0 | Sinod |  | PREMA RAM | 6350431991 | BALU RAM | 8355811699 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-LDNU-ENB-6001 | I-RJ-LDNU-PMP-0052 | 1/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.4902 | 74.459 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR50 | 2025-07-25 | 2025-07-25 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-07-30 | Sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Datau | [7 empty] | JLJH
I-RJ-NGUR-ENB-0032 | I-RJ-NGUR-PMP-0083 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.213 | 73.7363 | RTT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-18 | 2025-07-21 | 2025-07-28 | 2025-07-30 | 2025-07-30 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 90 | 15 | 0 | Mohammadpura |  | SUNIL KUMAR | 9412607678 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DDWN-ENB-9104 | I-RJ-DDWN-PMP-0051 | 3 | 1 | A6+B6 I&C | Ladnu | Nagaur | Rohit & Team |  | Done | 27.4399 | 74.6807 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR50 | 2025-07-25 | 2025-07-25 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Didwana | [7 empty] | JLJH
I-RJ-LDNU-ENB-9060 | I-RJ-LDNU-PMP-0040 | 1 | 1 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.5492 | 74.6941 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR48 | 2025-07-21 | 2025-07-21 | 2025-07-28 | 2025-07-28 | 2025-07-28 | 2025-07-28 | Sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 10 | 0 | Lachhri |  | BALDEWA RAM | 8058503498 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MKRN-ENB-9042 | I-RJ-MKRN-PMP-0057 | 1/2/3 | 3 | A6+B6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1287 | 74.4169 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-18 | 2025-07-24 | 2025-07-25 | 2025-07-25 | 2025-07-25 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 15 | 0 | Makrana |  | OMVEER SINGH | 9887268550 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MKRN-ENB-9046 | I-RJ-MKRN-PMP-0054 | 1/2/3 | 3 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.132 | 74.4538 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-18 | 2025-07-22 | 2025-07-24 | 2025-07-24 | 2025-07-24 | Sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 15 | 0 | Makrana |  | OMVEER SINGH | 9887268550 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DENA-ENB-9068 | I-RJ-DENA-PMP-0047 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Rohit & Team |  | Done | 26.9495 | 74.3016 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR50 | 2025-07-25 | 2025-07-25 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | ROHIT | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Noond | [7 empty] | JLJH
I-RJ-AJMR-ENB-V032 | I-RJ-AJMR-PMP-0290 | 1/2/3 | 3 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4175 | 74.6183 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR51 | 2025-07-29 | 2025-07-29 | 2025-07-30 | 2025-07-30 | 2025-07-30 | 2025-08-02 | Rahul outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Near Shiv temple | [7 empty] | JLKD
I-RJ-JAAL-ENB-9088 | I-RJ-JAAL-PMP-0035 | 2/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0625 | 74.0248 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR48 | 2025-07-21 | 2025-07-21 | 2025-08-04 | 2025-08-04 | 2025-08-04 | 2025-08-04 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 10 | 0 | Jayal |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DDWN-ENB-6011 | I-RJ-DDWN-PMP-0052 | 2 | 1 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.2016 | 74.5664 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR50 | 2025-07-25 | 2025-07-25 | 2025-08-07 | 2025-08-08 | 2025-08-08 | 2025-08-08 | Sandeep outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Ganwari | [7 empty] | JLJH
I-RJ-JAAL-ENB-I015 | I-RJ-JAAL-PMP-0048 | 3 | 1 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3738 | 74.0807 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR50 | 2025-07-25 | 2025-07-25 | 2025-08-03 | 2025-08-03 | 2025-08-03 | 2025-08-19 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | TANWARA | [7 empty] | JLJH
I-RJ-NGUR-ENB-9081 | I-RJ-NGUR-PMP-0086 | 2/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.9768 | 73.5267 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR50 | 2025-07-25 | 2025-07-25 | 2025-08-01 | 2025-08-01 | 2025-08-01 | 2025-08-01 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Khimsar | [7 empty] | JLJH
I-RJ-MKRN-ENB-9043 | I-RJ-MKRN-PMP-0064 | 2 | 1 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0966 | 74.7289 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR51 | 2025-08-04 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-06 | 2025-08-06 | sandeep | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | makrana | [7 empty] | JLJH
I-RJ-DDWN-ENB-9017 | I-RJ-DDWN-PMP-0062 | 1/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.1821 | 74.4049 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-11 | 2025-08-18 | 2025-08-18 | 2025-08-20 | 2025-08-20 | Sandeep | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Badbara |  | OMVEER SINGH | 9887268550 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DENA-ENB-H001 | I-RJ-DENA-PMP-0063 | 1/2 | 2 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0474 | 74.2459 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | Sandeep | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 10 | 0 | Chua |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-I002 | I-RJ-DENA-PMP-0054 | 1/2 | 2 | A6+B6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.8338 | 74.2773 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-11 | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2025-08-17 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 10 | 0 | TILANESH |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-9075 | I-RJ-JAAL-PMP-0042 | 2 | 1 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2563 | 74.2238 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-11 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Janwas |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-I013 | I-RJ-JAAL-PMP-0043 | 2 | 1 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.3991 | 73.9538 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-11 | 2025-08-15 | 2025-08-19 | 2025-08-19 | 2025-08-19 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | Gardiya |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-GRCN-ENB-6001 | I-RJ-GRCN-PMP-0006 | 1/2/3 | 3 | A6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 26.8946 | 74.3204 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR53 | 2025-08-13 | 2025-08-13 | 2025-08-16 | 2025-08-16 | 2025-08-16 | 2025-08-16 | Sandeep Outsource | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Bajoli |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DOLI-ENB-V002 | I-RJ-DOLI-PMP-0035 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Rohit & team |  | Done | 25.9451 | 75.3675 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR53 | 2025-08-13 | 2025-08-14 | 2025-08-19 | 2025-08-19 | 2025-08-19 | 2025-08-19 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 60 | 0 | Nasirda |  | SAURABH GAUTTAM | 6350492184 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-DOLI-ENB-V003 | I-RJ-DOLI-PMP-0036 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Rohit & team |  | Done | 25.7916 | 75.4102 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR53 | 2025-08-13 | 2025-08-14 | 2025-08-18 | 2025-08-18 | 2025-08-18 | 2025-08-18 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 180 | 70 | 0 | Boyara |  | Chetan Prakash Jat | 6350491764 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JLKD
I-RJ-SRGR-ENB-9091 | I-RJ-SRGR-PMP-0082 | 1/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.0562 | 73.6532 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR54 | 2025-08-19 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-21 | 2025-08-21 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-RAFS-ENB-9009 | I-RJ-RAFS-PMP-0003 | 2 | 1 | A6+B6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.4909 | 74.1101 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR51 | 2025-08-04 | 2025-08-04 | 2025-08-06 | 2025-08-06 | 2025-08-06 | 2025-08-06 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Riyanbadi | [7 empty] | JLJH
I-RJ-NAWW-ENB-I020 | I-RJ-NAWW-PMP-0065 | 1/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.1993 | 74.7925 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-11 | 2025-08-13 | 2025-08-13 | 2025-08-13 | 2025-08-13 | Sandeep | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 10 | 0 | RASAL |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NGUR-ENB-9089 | I-RJ-NGUR-PMP-0094 | 3 | 1 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9077 | 73.6122 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-11 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Kaliyas |  | DHARMARAM JAJRA | 6376202299 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SRGR-ENB-9080 | I-RJ-SRGR-PMP-0080 | 2/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 28.9648 | 73.9869 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-18 | 2025-08-19 | 2025-08-19 | 2025-08-19 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | Mokalsar |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-LKNR-ENB-9092 | I-RJ-LKNR-PMP-0063 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 28.9817 | 73.8145 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-17 | 2025-08-17 | 2025-08-17 | 2025-08-22 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Lunkarnasar |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-9094 | I-RJ-SRGR-PMP-0083 | 1/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 28.9987 | 73.9021 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-16 | 2025-08-19 | 2025-08-19 | 2025-08-22 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 10 | 0 | Suratgarh |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-I010 | I-RJ-SRGR-PMP-0106 | 1/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.0692 | 74.0404 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-20 | 2025-08-21 | 2025-08-21 | 2025-08-21 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 100 | 10 | 0 | RATTASAR |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-9082 | I-RJ-SRGR-PMP-0081 | 1/2/3 | 3 | A6+B6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.0981 | 73.7143 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 150 | 15 | 0 | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-9062 | I-RJ-SRGR-PMP-0102 | 1 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.1339 | 73.996 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR54 | 2025-08-19 | 2025-08-19 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 5 | 0 | Ganganagar |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-MRTA-ENB-9036 | I-RJ-MRTA-PMP-0053 | 1/2 | 2 | A6+B6 I&C | Nagaur | Nagaur | Rohit & team |  | Done | 26.5091 | 73.945 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR51 | 2025-08-04 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-06 | 2025-08-28 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  | 400 need to pay to vikram | 100 | 10 | 0 | Badgaon | [7 empty] | JLJH
I-RJ-ANUG-ENB-I011 | I-RJ-ANUG-PMP-0037 | 1/2 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.0613 | 73.1395 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR54 | 2025-08-19 | 2025-08-19 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 140 | 10 | 0 | 6 P |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-I017 | I-RJ-SRGR-PMP-0103 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.1619 | 73.6568 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR54 | 2025-08-19 | 2025-08-19 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 5 | 0 | 3 BMM |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-NGUR-ENB-I014 | I-RJ-NGUR-PMP-0091 | 1/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1917 | 73.8861 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-27 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | GAGWANA |  | BHARAT THALOR | 8078698860 | MAHENDRA DHUNDHWAL | 9057571856 | OM PRAKASH | 6350491377 | JLJH
I-RJ-ANGR-ENB-9048 | I-RJ-ANGR-PMP-0028 | 1/2 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 28.9336 | 73.0121 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-23 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 80 | 10 | 0 | Gharsana |  | CHET RAM | 6350492121 | Vinod Kumar | 6350492215 | RAJA RAM | 8003992944 | JLKD
I-RJ-ANUG-ENB-I003 | I-RJ-ANUG-PMP-0025 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.0992 | 73.2132 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | Rohit | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 5 | 0 | 1 NWM |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-ANUG-ENB-I010 | I-RJ-ANUG-PMP-0036 | 2/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.3241 | 73.2807 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  | mcb connection done by local tech amount deducted | Allotment- AIR52 | 2025-08-11 | 2025-08-12 | 2025-08-24 | 2025-08-24 | 2025-08-24 | 2025-08-24 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 10 | 0 | 11SJM |  | DAULAT RAM | 6350492122 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JLKD
I-RJ-VJIG-ENB-9045 | I-RJ-VJIG-PMP-0011 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.1982 | 73.4336 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR53 | 2025-08-13 | 2025-08-14 | 2025-08-23 | 2025-08-23 | 2025-08-23 | 2025-08-23 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 50 | 50 | 0 | Vill-49 GB |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-KESR-ENB-9038 | I-RJ-KESR-PMP-0025 | 1/2 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9426 | 73.4415 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-31 | 2025-08-31 | 2025-08-31 | 2025-09-02 | Vikram | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | Tadawas |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MKRN-ENB-9050 | I-RJ-MKRN-PMP-0068 | 2/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 26.9069 | 74.3919 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-29 | 2025-08-29 | 2025-08-29 | 2025-08-29 | Sandeep | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | Bajoli |  | JITENDRA PATIDAR | 6350491976 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DDWN-ENB-9105 | I-RJ-DDWN-PMP-0047 | 1/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.449 | 74.4147 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-30 | 2025-08-30 | 2025-08-30 | 2025-08-30 | Sandeep | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | Doodoli, |  | BALDEWA RAM | 8058503498 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-9049 | I-RJ-JAAL-PMP-0045 | 2/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2665 | 73.9179 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | VIKRAM | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | Sarasani |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KESR-ENB-9039 | I-RJ-KESR-PMP-0026 | 1/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Aneesh & team |  | Done | 26.9526 | 73.5083 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-31 | 2025-08-31 | 2025-09-03 | 2025-09-03 | [6 empty] | NO | NO | NA |  |  | Ready |  | 1000 paid to vikram for 11a/11c/ cable routing and fatp |  |  |  | Khinwasar |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MKRN-ENB-9037 | I-RJ-MKRN-PMP-0069 | 2 | 1 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0936 | 74.6068 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-26 | SANDEEP | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | Altawa |  | Chiranji Lal | 6350491964 | RICHHPAL GURJAR | 8441931031 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MKRN-ENB-9061 | I-RJ-MKRN-PMP-0052 | 2 | 1 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.1518 | 74.5506 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-08-25 | sandeep | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | Makrana |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NAWW-ENB-I003 | I-RJ-NAWW-PMP-0056 | 2 | 1 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.119 | 74.9783 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR55 | 2025-08-20 | 2025-08-21 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | sandeep | [5 empty] | NO | NO | NA |  |  | Ready | [5 empty] | Gogor |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-AJMR-ENB-0185 | I-RJ-AJMR-PMP-0094 | 1 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.5116 | 74.6331 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR47 | 2025-07-18 | 2025-07-19 | 2025-08-26 | 2025-08-26 | 2025-08-26 | 2025-08-29 | Rawat Rahul | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 30 | 5 | 0 | panchsheel housing board colony |  | KISHANA RAM JAT | 6376917711 | JITENDRA KANOJIYA | 6375556812 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-MSUD-ENB-V003 | I-RJ-MSUD-PMP-0020 | 1/2/3 | 3 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 25.9269 | 74.6481 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR56 | 2025-08-24 | 2025-08-24 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 120 | 50 | 0 | Bijaynagar Main Sabzi Mandi |  | NORAT MAL GURJAR | 6350491767 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT | JLKD
I-RJ-BEWR-ENB-I007 | I-RJ-BEWR-PMP-0050 | 1 | 1 | A6 I&C | Beawar | Ajmer | Aneesh & team |  | Done | 26.0846 | 74.3112 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR56 | 2025-08-24 | 2025-08-24 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 40 | 5 | 0 | Saket Nagar |  | NEMI CHAND | 9680086665 | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-MRTA-ENB-I019 | I-RJ-MRTA-PMP-0040 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Aneesh & team |  | Done | 26.6034 | 73.7219 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR56 | 2025-08-24 | 2025-08-26 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-08-28 | Aneesh | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 70 | 0 | Talanpur |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SRGR-ENB-I008 | I-RJ-SRGR-PMP-0065 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rohit & team |  | Done | 29.4465 | 73.7284 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR57 | 2025-08-26 | 2025-08-26 | 2025-08-27 | 2025-08-27 | 2025-08-27 | 2025-08-27 | Rohit & team | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 60 | 60 | 0 | 2MNWM |  | Deepak Sharma | 8078698950 | 8078698950 |  |  |  | JLKD
I-RJ-JPUR-ENB-1425 | I-RJ-JPUR-LBR-0057 | 3 | 1 | MM WAVE | Jaipur - Rajapark | Jaipur-2 | Aneesh & team |  | Done | 26.9015 | 75.89 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR58 | 2025-09-06 | 2025-09-06 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2025-09-08 | in house | [13 empty] | 30 | 30 |  | Jaipur |  | Shambhu Dayal Bohara | 9057531898 | Roop Narayan Gurjar | 9057531896 | SANTOSH SHARMA | 9251637621 | JLKD
I-RJ-JPUR-ENB-0560 | I-RJ-JPUR-LBR-0054 | 2 | 1 | MM WAVE | Jaipur - Rajapark | Jaipur-2 | Dileep & Team |  | Done | 26.8904 | 75.8256 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR58 | 2025-09-06 | 2025-09-06 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | in house | [13 empty] | 30 | 30 |  | Samudaik Kendra Back side, Tilak Nagar |  | BRIJ MOHAN SHARMA | 8955001716 | SHYAMU SAINI | 8955937634 | SANTOSH SHARMA | 9251637621 | JLKD
I-RJ-SRGR-ENB-9096 | I-RJ-SRGR-PMP-0093 | 1/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.1283 | 73.788 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-08 | 2025-09-08 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | Aneesh | [16 empty] | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-9070 | I-RJ-SRGR-PMP-0088 | 1/2 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.0941 | 73.5868 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | 2025-09-11 | aneesh | [16 empty] | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-AHOR-ENB-9048 | I-RJ-AHOR-PMP-0028 | 1/2 | 2 | A6+B6 I&C | Jalor | Sirohi | Rohit & team |  | Done | 25.4069 | 72.8204 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | Rohit & team | [16 empty] | Ahore |  | SANJAY KUMAR MEENA | 9024489656 | Shankar Lal | 6350491316 | 8239210103 | JEETENDRA KUMAWAT | JLJH
I-RJ-MRTA-ENB-9057 | I-RJ-MRTA-PMP-0058 | 2/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Dileep & Team |  | Done | 26.6115 | 74.1023 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | Dileep & Rajkumar team | [16 empty] | merta city |  | IMARAN KHAN | 9887333514 | Ramdev Choudhary | 9414892394 | 9414892394 | DHARMENDRA SINGH | JLJH
I-RJ-SRGR-ENB-9097 | I-RJ-SRGR-PMP-0089 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.142 | 73.5912 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-08 | 2025-09-08 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | Aneesh & team | [16 empty] | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-DENA-ENB-I021 | I-RJ-DENA-PMP-0053 | 1/2/3 | 3 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0108 | 74.3449 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-12 | Sandeep Outsource | [16 empty] | Jakhera |  | JITENDRA PATIDAR | 6350491976 | RAJESH KASWAN | 9509617574 | 9509617574 | RAJENDRA SINGH RATHORE | JLJH
I-RJ-AJMR-ENB-0189 | I-RJ-AJMR-PMP-0097 | 2 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.3344 | 74.5663 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR60 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-12 | 2025-09-12 | 2025-09-13 | RAWAT RAHUL | [13 empty] | 50 | 50 |  | Sardhana |  | Rakesh Paroda | 6350491793 | MOHAN SINGH | 9568428114 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-BNML-ENB-9046 | I-RJ-BNML-PMP-0027 | 1/2/3 | 3 | A6+B6 I&C | Jalor | Sirohi | Rohit & team |  | Done | 25.016 | 72.6078 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 | [17 empty] | JHAK |  | Jagdish Kumar | 6350491299 | VACANT | VACANT | 0 | LAKSHYADEEP SINGH GEHLOT | JLJH
I-RJ-MRTA-ENB-9077 | I-RJ-MRTA-PMP-0060 | 2 | 1 | A6+B6 I&C | Nagaur | Nagaur | Dileep & Team |  | Done | 26.6023 | 74.1478 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-13 | 2025-09-13 | rajkumar | [16 empty] | Jodhras |  | IMARAN KHAN | 9887333514 | SALEEM MOHAMMAD DESHWALI | 7891896395 | 7891896395 | DHARMENDRA SINGH | JLJH
I-RJ-NGUR-ENB-A004 | I-RJ-NGUR-PMP-0109 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2043 | 73.7373 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-21 | 2025-09-21 | 2025-09-21 | vikram | [16 empty] | Mohalla Kalipole |  | MAHENDRA JAT | 8290502749 | NENA RAM | 7627076857 | 7627076857 | DHARMENDRA SINGH | JLJH
I-RJ-JAAL-ENB-I008 | I-RJ-JAAL-PMP-0039 | 1/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Mahendra Outsource |  | Done | 27.1911 | 74.0986 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-14 | 2025-09-19 | Pawan | [16 empty] | Merwas (JHALALAR) |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-I014 | I-RJ-JAAL-PMP-0040 | 2/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0848 | 73.8991 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-09-19 | Vikram | [16 empty] | Naradhana |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-9073 | I-RJ-JAAL-PMP-0049 | 3 | 1 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.1501 | 74.2953 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-09-14 | SANDEEP | [16 empty] | Khatu bari |  | RATNA RAM | 6350492259 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SNCE-ENB-9095 | I-RJ-SNCE-PMP-0060 | 2 | 1 | A6+B6 I&C | Jalor | Sirohi | Rohit & team |  | Done | 24.8355 | 71.5602 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-09-14 | Rohit | [16 empty] | Sanchor |  | JETMAL SINGH | 7014142932 | BHAGA RAM | 9024465772 | 9024465772 | Sharwan Bhati | JLJH
I-RJ-DENA-ENB-I020 | I-RJ-DENA-PMP-0057 | 1/2 | 2 | A6+B6 I&C | Makrana | Nagaur | Rajkumar & team |  | Done | 26.7651 | 74.1758 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-09-14 | rajkumar | [16 empty] | Sirasana |  | IMARAN KHAN | 9887333514 | SALEEM MOHAMMAD DESHWALI | 7891896395 | 7891896395 | DHARMENDRA SINGH | JLJH
I-RJ-SNCE-ENB-9104 | I-RJ-SNCE-PMP-0057 | 2 | 1 | A6+B6 I&C | Jalor | Sirohi | Rohit & team |  | Done | 24.8814 | 71.606 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | Rohit | [16 empty] | Ratora |  | RAM GOPAL | 9571316104 | BHAGA RAM | 9024465772 | 9024465772 | Sharwan Bhati | JLJH
I-RJ-DENA-ENB-9100 | I-RJ-DENA-PMP-0059 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Rajkumar & team |  | Done | 26.7406 | 74.4152 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | rajkumar | [16 empty] | Rajlota |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | 8209549364 | RAJENDRA SINGH RATHORE | JLJH
I-RJ-SRGR-ENB-9075 | I-RJ-SRGR-PMP-0095 | 1 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.268 | 73.7796 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-15 | 2025-09-15 | 2025-09-15 | Aneesh | [16 empty] | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-CWAN-ENB-9008 | I-RJ-CWAN-PMP-0003 | 2 | 1 | A6+B6 I&C | Jalor | Sirohi | Rohit & team |  | Done | 24.9605 | 71.6734 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | Rohit | [16 empty] | Ranodar |  | DHANESH KUMAR | 9772728785 | BHAGA RAM | 9024465772 | 9024465772 | Sharwan Bhati | JLJH
I-RJ-DENA-ENB-9053 | I-RJ-DENA-PMP-0055 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Dileep & Team |  | Done | 26.9251 | 74.2508 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-16 | 2025-09-16 | 2025-09-16 | 2025-09-16 | rajkumar | [12 empty] | A6 DOWN/ RESTORED BY SANDEEP ON 21 SEPT |  |  |  | Gundisar |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | 9509617574 | RAJENDRA SINGH RATHORE | JLJH
I-RJ-SNCE-ENB-I030 | I-RJ-SNCE-PMP-0056 | 1/3 | 2 | A6+B6 I&C | Jalor | Sirohi | Rohit & team |  | Done | 25.0405 | 71.7537 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-17 | Rohit | [16 empty] | GURHA HEMA |  | DHANESH KUMAR | 9772728785 | DAMA RAM | 6350491610 | 6350491610 | Sharwan Bhati | JLJH
I-RJ-JAAL-ENB-I002 | I-RJ-JAAL-PMP-0044 | 3 | 1 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.4906 | 74.0055 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-20 | Vikram | [16 empty] | Kangasiya |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KCRA-ENB-9003 | I-RJ-KCRA-PMP-0004 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.986 | 73.9718 | RTT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-09 | 2025-09-10 | 2025-09-15 | 2025-09-16 | 2025-09-16 | 2025-09-19 | VIKRAM | [12 empty] | 4 POLE MOUNT INSTALLED BY VIKRAM |  |  |  | Mundwa |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | 9057571856 | DHARMENDRA SINGH | JLJH
I-RJ-SRGR-ENB-9072 | I-RJ-SRGR-PMP-0094 | 1/2 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.2089 | 73.7261 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR59 | 2025-09-08 | 2025-09-08 | 2025-09-14 | 2025-09-14 | 2025-09-14 | 2025-09-16 | ANEESH | [16 empty] | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SOJT-ENB-9048 | I-RJ-SOJT-PMP-0041 | 3 | 1 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 26.0218 | 73.4413 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-17 | 2025-09-17 | 2025-09-17 | 2025-09-19 | RAJKUMAR | [16 empty] | Jhupelav |  | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SOJT-ENB-9054 | I-RJ-SOJT-PMP-0040 | 3 | 1 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 26.0629 | 73.7812 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-21 | 2025-09-21 | 2025-09-21 | 2025-09-21 | RAJKUMAR | [16 empty] | Sojat |  | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SOJT-ENB-9056 | I-RJ-SOJT-PMP-0036 | 3 | 1 | A6+B6 I&C | Pali | Sirohi | Rajkumar & team |  | Done | 26.0662 | 73.6192 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | RAJKUMAR | [16 empty] | Meo |  | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SOJT-ENB-I008 | I-RJ-SOJT-PMP-0037 | 3 | 1 | A6+B6 I&C | Pali | Sirohi | Rajkumar & team |  | Done | 25.9805 | 73.5348 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR61 | 2025-09-12 | 2025-09-12 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | RAJKUMAR | [16 empty] | GaguraPLI U |  | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-JPUR-ENB-0400 | I-RJ-ABER-LBR-0004 | 2 | 1 | MM WAVE | Jaipur - Rajapark | Jaipur-2 |  |  | MRN Done | 26.9746 | 75.8691 | GBT | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR58 | 2025-09-06 | 2025-09-06 | [18 empty] | 40 | 40 |  | Kheera Walon ki Dhani |  | Pukhraj saini | 8078699712 | MANISH KUMAR SHARMA | 9509026405 | SANTOSH SHARMA | 9251637621 | JLKD
I-RJ-JPUR-ENB-0715 | I-RJ-JPUR-LBR-0090 | 1 | 1 | MM WAVE | Jaipur - Rajapark | Jaipur-2 |  |  | MRN Done | 26.9618 | 75.8455 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR58 | 2025-09-06 | 2025-09-06 | [18 empty] | 30 | 30 |  | Amer Road Opp Air Force Station |  | Pukhraj saini | 8078699712 | MANISH KUMAR SHARMA | 9509026405 | SANTOSH SHARMA | 9251637621 | JLKD
I-RJ-SRGR-ENB-I009 | I-RJ-SRGR-PMP-0091 | 3 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.3735 | 73.8163 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-18 | 2025-09-18 | 2025-09-18 | 2025-09-18 | Aneesh & team | [16 empty] | 1 SGM |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-H002 | I-RJ-SRGR-PMP-0092 | 1/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.4023 | 73.7975 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-19 | 2025-09-19 | 2025-09-19 | 2025-09-19 | Aneesh & team | [16 empty] | 10Shpd A |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-BALI-ENB-9050 | I-RJ-BALI-PMP-0021 | 2/3 | 2 | A6+B6 I&C | Pali | Sirohi | Rohit & team |  | Done | 25.0833 | 73.2172 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | Rohit & team | [16 empty] | JIVDA |  | BHARAT SINGH | 7725999422 | Rajendra Kumar | 9413139121 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-SRGR-ENB-9124 | I-RJ-SRGR-PMP-0086 | 1/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.155 | 73.8675 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | Aneesh & team | [16 empty] | Suratgarh |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLKD
I-RJ-NAWW-ENB-9052 | I-RJ-NAWW-PMP-0055 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.046 | 74.8115 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-20 | 2025-09-20 | 2025-09-20 | 2025-09-20 | Sandeep Outsource | [16 empty] | Narayanpura |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-SRGR-ENB-I013 | I-RJ-SRGR-PMP-0104 | 1/2/3 | 3 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.1496 | 73.8386 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-21 | 2025-09-21 | 2025-09-21 | 2025-09-21 | Aneesh & team | [16 empty] | 2AP |  | ASHOK SHARMA | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-BALI-ENB-I004 | I-RJ-BALI-PMP-0026 | 3 | 1 | A6+B6 I&C | Pali | Sirohi | Rohit & team |  | Done | 24.8881 | 73.1328 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2025-09-21 | 2025-09-21 | 2025-09-21 | Rohit & team | [16 empty] | Kagdara |  | BHARAT SINGH | 7725999422 | Rajendra Kumar | 9413139121 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-MKRN-ENB-9031 | I-RJ-MKRN-PMP-0065 | 2 | 1 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 26.9652 | 74.5355 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-21 | 2025-09-21 | 2025-09-21 | 2025-09-21 | Sandeep Outsource | [16 empty] | Gingaliya |  | JITENDRA PATIDAR | 6350491976 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DDWN-ENB-9076 | I-RJ-DDWN-PMP-0057 | 2 | 1 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.2388 | 74.5941 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | sandeep | [16 empty] | Didwana |  | Prema Dahiya | 6350491992 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAN-ENB-9046 | I-RJ-JAAN-PMP-0037 | 1 | 1 | A6+B6 I&C | Pali | Sirohi | Rajkumar & team |  | Done | 26.2209 | 73.9846 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | rajkumar | [16 empty] | Jaitaran |  | Nathu Singh | 9660202162 | DURGARAM HARSALIYA | 8529607895 | VACANT | VACANT | JLJH
I-RJ-SRGR-ENB-H003 | I-RJ-SRGR-PMP-0099 | 1/2/3 | 3 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.0866 | 73.7849 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-22 | 2025-09-22 | 2025-09-22 | 2025-09-22 | aneesh | [16 empty] | Maler |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-JAAN-ENB-9052 | I-RJ-JAAN-PMP-0034 | 1 | 1 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 26.2725 | 74.1492 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | RAJKUMAR | [16 empty] | Jaitaran |  | SIKANDAR KHAN | 6350491317 | INDRAJEET HARSHALIYA | 8875202884 | VACANT | VACANT | JLJH
I-RJ-MOSR-ENB-9003 | I-RJ-MOSR-PMP-0004 | 2/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3176 | 74.6721 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | sandeep | [16 empty] | Didwana |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-RSNG-ENB-9049 | I-RJ-RSNG-PMP-0043 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.3231 | 73.53 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-23 | 2025-09-23 | 2025-09-23 | 2025-09-23 | ANEESH | [16 empty] | J.K.M Panchyat Samiti |  | LAL CHAND | 9672526292 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JLKD
I-RJ-ANUG-ENB-9056 | I-RJ-ANUG-PMP-0028 | 1/2/3 | 3 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.3364 | 73.3351 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | ANEESH | [16 empty] | Anupgarh |  | DAULAT RAM | 6350492122 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JLKD
I-RJ-DDWN-ENB-9068 | I-RJ-DDWN-PMP-0053 | 1/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.4411 | 74.4583 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | SANDEEP | [16 empty] | dudoli |  | BALDEWA RAM | 8058503498 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAN-ENB-9059 | I-RJ-JAAN-PMP-0031 | 2 | 1 | A6+B6 I&C | Pali | Sirohi | Rajkumar & team |  | Done | 26.2928 | 74.2472 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | DILIP | [16 empty] | Jaitaran |  | SIKANDAR KHAN | 6350491317 | INDRAJEET HARSHALIYA | 8875202884 | VACANT | VACANT | JLJH
I-RJ-KKNI-ENB-9046 | I-RJ-KKNI-PMP-0024 | 2 | 1 | A6+B6 I&C | Pali | Sirohi | Rohit & team |  | Done | 25.8226 | 73.2047 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-24 | 2025-09-24 | 2025-09-24 | 2025-09-24 | ROHIT | [16 empty] | Chothi Devi, Kakani |  | KUNDAN LAL | 8005566207 | AAKASH CHOUHAN | 9664393427 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-MKRN-ENB-G001 | I-RJ-MKRN-PMP-0072 | 1/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.107 | 74.5029 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-26 | vikram | [16 empty] | Indokha |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-G005 | I-RJ-DDWN-PMP-0064 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3892 | 74.7748 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-09-26 | 2025-09-25 | SANDEEP | [16 empty] | Beri Chhoti |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PALI-ENB-I007 | I-RJ-PALI-PMP-0086 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Rohit & team |  | Done | 25.6972 | 73.389 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | ROHIT | [16 empty] | AAICHIYA |  | MAHENDRA CHOUDHARY | 9982683598 | RAVINDRA SINGH | 9079623229 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-PALI-ENB-I012 | I-RJ-PALI-PMP-0085 | 1/2 | 2 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 25.6231 | 73.3824 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | RAJKUMAR | [16 empty] | Sapooni |  | MAHENDRA CHOUDHARY | 9982683598 | RAVINDRA SINGH | 9079623229 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-MKRN-ENB-I005 | I-RJ-MKRN-PMP-0066 | 2/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.047 | 74.3937 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR63 | 2025-09-17 | 2025-09-18 | 2025-09-24 | 2025-09-24 | 2025-09-25 | 2025-09-26 | Vikram | [16 empty] | KHARDIYA |  | JITENDRA PATIDAR | 6350491976 | SUKHDEV ROYAL | 9672742052 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MAJN-ENB-I005 | I-RJ-MAJN-PMP-0043 | 2 | 1 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 25.6037 | 73.6894 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | DILIP | [16 empty] | Gura Keshar Singh |  | NARENDRA KUMAR GURJAR | 6376917827 | BHAWANI SINGH | 9799650934 | VACANT | VACANT | JLJH
I-RJ-KKNI-ENB-9038 | I-RJ-KKNI-PMP-0036 | 2 | 1 | A6+B6 I&C | Pali | Sirohi | Rohit & team |  | Done | 25.7549 | 73.1108 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-26 | 2025-09-26 | 2025-09-26 | 2025-09-26 | Rohit | [16 empty] | khundawas |  | JITENDRA KUMAR RANA | 7742021345 | AAKASH CHOUHAN | 9664393427 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-RSNG-ENB-I007 | I-RJ-RSNG-PMP-0046 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.3912 | 73.3993 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-25 | ANEESH | [16 empty] | 57NP infill |  | RAM KUMAR | 7849824285 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JLKD
I-RJ-ANUG-ENB-9053 | I-RJ-ANUG-PMP-0033 | 1/2 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1373 | 73.3585 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-26 | 2025-09-28 | 2025-09-28 | 2025-09-30 | Aneesh | [16 empty] | Anupgarh |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-SOJT-ENB-I012 | I-RJ-SOJT-PMP-0039 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 26.0085 | 73.4779 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-09-27 | Dilip | [16 empty] | Jhupelao |  | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-ANUG-ENB-H002 | I-RJ-ANUG-PMP-0030 | 1/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1325 | 73.2882 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-09-27 | Aneesh | [16 empty] | 5 A-B |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-DDWN-ENB-I018 | I-RJ-DDWN-PMP-0070 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Sandeep Outsource |  | Done | 27.3587 | 74.5436 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR65 | 2025-09-25 | 2025-09-25 | 2025-09-27 | 2025-09-27 | 2025-09-27 | 2025-09-27 | Sandeep | [16 empty] | Baliya |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-AHOR-ENB-9054 | I-RJ-AHOR-PMP-0030 | 1/2/3 | 3 | A6+B6 I&C | Jalor | Sirohi | Rohit & team |  | Done | 25.5113 | 72.9454 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-27 | 2025-10-04 | 2025-10-04 | 2025-10-04 | Rohit | [16 empty] | Ahore |  | VACANT | VACANT | Shankar Lal | 6350491316 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-ANUG-ENB-9063 | I-RJ-ANUG-PMP-0024 | 3 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1788 | 73.1614 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Aneesh | [16 empty] | Anupgarh |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-NAWW-ENB-I018 | I-RJ-NAWW-PMP-0058 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.1409 | 75.0583 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-28 | Sandeep | [16 empty] | Bhooni |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MRTA-ENB-I009 | I-RJ-MRTA-PMP-0063 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.7714 | 74.0424 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR65 | 2025-09-25 | 2025-09-25 | 2025-09-28 | 2025-10-02 | 2025-10-02 | 2025-10-02 | Vikram | [16 empty] | Dabriyani Khurd |  | Arif Khan | 6367853630 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-RAPR-ENB-9059 | I-RJ-RAPR-PMP-0022 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Rajkumar & team |  | Done | 26.0193 | 74.028 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Dilip | [16 empty] | Raipur |  | BARKAT MOHMMAD | 6350491310 | PINKU SINGH | 9660860336 | VACANT | VACANT | JLJH
I-RJ-RAPR-ENB-9009 | I-RJ-RAPR-PMP-0021 | 2/3 | 2 | A6+B6 I&C | Pali | Sirohi | Rajkumar & team |  | Done | 26.0147 | 74.0309 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-09-29 | rajkumar | [16 empty] | Haripur |  | BARKAT MOHMMAD | 6350491310 | PINKU SINGH | 9660860336 | VACANT | VACANT | JLJH
I-RJ-ANUG-ENB-I001 | I-RJ-ANUG-PMP-0031 | 1 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.0958 | 73.0886 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR62 | 2025-09-17 | 2025-09-17 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Aneesh | [16 empty] | 6H |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-REAR-ENB-H001 | I-RJ-REAR-PMP-0027 | 3 | 1 | A6+B6 I&C | Sirohi | Sirohi | Rohit & team |  | Done | 24.7084 | 72.7293 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-29 | Rohit | [16 empty] | Udwaria |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-PALI-ENB-9045 | I-RJ-PALI-PMP-0084 | 2 | 1 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 25.8603 | 73.3883 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-10-04 | 2025-10-04 | 2025-10-07 | 2025-10-04 | Dilip | [16 empty] | Pali |  | KUNDAN LAL | 8005566207 | RAVINDRA SINGH | 9079623229 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-REAR-ENB-9039 | I-RJ-REAR-PMP-0025 | 1/2 | 2 | A6+B6 I&C | Sirohi | Sirohi | Rohit & team |  | Done | 24.5572 | 72.4657 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR65 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-09-29 | 2025-09-30 | Rohit & team | [16 empty] | Jawal |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-SRHI-ENB-9055 | I-RJ-SRHI-PMP-0041 | 1 | 1 | A6+B6 I&C | Sirohi | Sirohi | Rohit & team |  | Done | 24.9102 | 72.5279 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR64 | 2025-09-23 | 2025-09-23 | 2025-10-01 | 2025-10-01 | 2025-10-02 | 2025-10-02 | Rohit | [16 empty] | Akoona |  | Jagdish Kumar | 6350491299 | VACANT | VACANT | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-MRTA-ENB-9093 | I-RJ-MRTA-PMP-0048 | 2/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.5184 | 73.9135 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR65 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-01 | 2025-10-01 | Vikram | [16 empty] | Looniyas |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAN-ENB-A001 | I-RJ-JAAN-PMP-0041 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Rohit & team |  | Done | 26.364 | 73.9895 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR66 | 2025-09-30 | 2025-09-30 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | Rohit & team | [16 empty] | Anandpur Kalu with Chak |  | SIKANDAR KHAN | 6350491317 | INDRAJEET HARSHALIYA | 8875202884 | VACANT | VACANT | JLJH
I-RJ-KKNI-ENB-I004 | I-RJ-KKNI-PMP-0031 | 1/2 | 2 | A6+B6 I&C | Pali | Sirohi |  |  | Done | 25.8714 | 72.8658 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR66 | 2025-09-30 | 2025-09-30 | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | Dilip | [16 empty] | DIWANDI |  | JITENDRA KUMAR RANA | 7742021345 | AAKASH CHOUHAN | 9664393427 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-NAWW-ENB-H005 | I-RJ-NAWW-PMP-0057 | 2/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0789 | 75.0043 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR66 | 2025-09-30 | 2025-09-30 | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | Sandeep Outsource | [16 empty] | Panchota |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MRTA-ENB-I009 | I-RJ-MRTA-PMP-0063 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.7714 | 74.0424 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR65 | 2025-09-25 | 2025-09-25 | 2025-09-28 | 2025-09-28 | 2025-10-02 | 2025-10-02 | Vikram Jangid Nagaur team | [16 empty] | Dabriyani Khurd |  | Arif Khan | 6367853630 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-NAWW-ENB-H005 | I-RJ-NAWW-PMP-0057 | 2/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Sandeep Outsource |  | Done | 27.0789 | 75.0043 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR66 | 2025-09-30 | 2025-09-30 | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | Sandeep Outsource | [16 empty] | Panchota |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KKNI-ENB-I004 | I-RJ-KKNI-PMP-0031 | 1/2 | 2 | A6+B6 I&C | Pali | Sirohi | Dileep & Team |  | Done | 25.8714 | 72.8658 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR66 | 2025-09-30 | 2025-09-30 | 2025-10-03 | 2025-10-03 | 2025-10-03 | 2025-10-03 | Dileep & Rajkumar team | [16 empty] | DIWANDI |  | JITENDRA KUMAR RANA | 7742021345 | AAKASH CHOUHAN | 9664393427 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-DENA-ENB-I010 | I-RJ-DENA-PMP-0056 | 1/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.7011 | 74.3724 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR68 | 2025-10-07 | 2025-10-08 | 2025-10-10 | 2025-10-10 | 2025-10-10 | 2025-10-10 | Rohit & team | [16 empty] | PACHRANDA |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9061 | I-RJ-DENA-PMP-0051 | 1 | 1 | A6+B6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.7815 | 74.3865 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR68 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-09 | 2025-10-09 | 2025-10-09 | Rohit & team | [16 empty] | Lawadar,Makrana |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PLBG-ENB-I002 | I-RJ-PLBG-PMP-0023 | 1 | 1 | A6 I&C | Hanumangarh | Ganganagar | Rakesh Outsource |  | Done | 29.4195 | 73.9931 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR67 | 2025-10-04 | 2025-10-07 | 2025-10-11 | 2025-10-11 | 2025-10-11 | 2025-10-11 | Rakesh | [16 empty] | 34 STG |  | KULDEEP SINGH | 9509692369 | BALVINDRA SINGH | 6377561597 | RAJA RAM | 8003992944 | JLKD
I-RJ-BNML-ENB-9051 | I-RJ-BNML-PMP-0033 | 1/3 | 2 | A6+B6 I&C | Jalor | Sirohi | Rajkumar & team |  | Done | 24.7698 | 72.4651 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR68 | 2025-10-07 | 2025-10-08 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | Dilip | [16 empty] | GAJPURA |  | KAILASH KUMAR | 8058302215 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-DENA-ENB-I012 | I-RJ-DENA-PMP-0060 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.7452 | 74.3833 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR69 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-12 | 2025-10-12 | 2025-10-12 | Rohit & team | [16 empty] | NimbriKothari |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9047 | I-RJ-NAWW-PMP-0060 | 1/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 27.1625 | 74.9828 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR69 | 2025-10-11 | 2025-10-11 | 2025-10-13 | 2025-10-13 | 2025-10-13 | 2025-10-13 | [17 empty] | Haripura |  | RAMESHWAR LAL | 6350491990 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MOSR-ENB-9001 | I-RJ-MOSR-PMP-0002 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.3804 | 74.8108 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR68 | 2025-10-07 | 2025-10-08 | 2025-10-12 | 2025-10-14 | 2025-10-14 | 2025-10-14 | Premaram | [16 empty] | Didwana |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SOJT-ENB-9064 | I-RJ-SOJT-PMP-0038 | 3 | 1 | A6+B6 I&C | Pali | Sirohi | Rajkumar & team |  | Done | 25.8842 | 73.4884 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR65 | 2025-09-25 | 2025-09-25 | 2025-09-30 | 2025-09-30 | 2025-09-30 | 2025-10-15 | rajkumar | [16 empty] | Sojat |  | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-LDNU-ENB-9048 | I-RJ-LDNU-PMP-0046 | 2 | 1 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.4458 | 74.3088 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR68 | 2025-10-07 | 2025-10-08 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | vikram | [16 empty] | sikrani |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PASS-ENB-I002 | I-RJ-PASS-PMP-0025 | 1/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Rohit & team |  | Done | 26.8843 | 74.4774 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR68 | 2025-10-07 | 2025-10-08 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | Rohit | [16 empty] | BARNEL(GUDHA-CHAK) |  | JITENDRA PATIDAR | 6350491976 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-SEGN-ENB-S001 | I-RJ-SEGN-PMP-0034 | 1/2/3 | 3 | A6+B6 I&C | Sirohi | Sirohi | Rohit & team |  | Done | 25.0288 | 72.9662 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR65 | 2025-09-25 | 2025-09-25 | 2025-09-28 | 2025-09-28 | 2025-09-28 | 2025-10-14 | Rohit | [16 empty] | UTHMAN |  | VINOD KUMAR | 8094636604 | ARJUN LAL | 8955001722 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-REAR-ENB-9042 | I-RJ-REAR-PMP-0024 | 2 | 1 | A6+B6 I&C | Sirohi | Sirohi | Dileep & Team |  | Done | 24.7061 | 72.5551 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR69 | 2025-10-11 | 2025-10-11 | 2025-10-14 | 2025-10-14 | 2025-10-14 | 2025-10-14 | Dileep & Rajkumar team | [16 empty] | Dhan |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-LDNU-ENB-I022 | I-RJ-LDNU-PMP-0053 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.6484 | 74.4023 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR70 | 2025-10-16 | 2025-10-16 | 2025-10-25 | 2025-10-26 | 2025-10-25 | 2025-10-29 | Vikram Jangid Nagaur team | [16 empty] | Shiv Mandir (No. 1 School) | [7 empty] | JLJH
I-RJ-NGUR-ENB-9097 | I-RJ-NGUR-PMP-0051 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.162 | 73.7109 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-31 | Vikram Jangid Nagaur team | [13 empty] | 50 | 50 |  | Nagaur |  | MAHENDRA JAT | 8290502749 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-NGUR-ENB-9096 | I-RJ-NGUR-PMP-0050 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0499 | 73.5011 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Vikram Jangid Nagaur team | [13 empty] | 40 | 40 |  | Tankla |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-MKRN-ENB-V005 | I-RJ-MKRN-PMP-0048 | 3 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.0397 | 74.6194 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | Prema Ram Outsource | [13 empty] | 60 | 5 |  | KALWA BARA |  | Chiranji Lal | 6350491964 | RICHHPAL GURJAR | 8441931031 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-SRGR-ENB-9013 | I-RJ-SRGR-PMP-0030 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1751 | 73.8945 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | Aneesh & Team | [13 empty] | 50 | 5 |  | Bidwal Station |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-6006 | I-RJ-SRGR-PMP-0022 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.2009 | 73.8498 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | Aneesh & Team | [13 empty] | 50 | 50 |  | 3 Ap |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-6012 | I-RJ-SRGR-PMP-0027 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1933 | 73.9909 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-10-30 | Aneesh & Team | [13 empty] | 60 | 5 |  | SURATGARH THER |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-H001 | I-RJ-SRGR-PMP-0059 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.0404 | 73.9669 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Aneesh & Team | [13 empty] | 60 | 60 |  | Deidaspura |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-9069 | I-RJ-SRGR-PMP-0044 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.2071 | 74.142 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Aneesh & Team | [13 empty] | 50 | 50 |  | Suratgarh |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-I014 | I-RJ-SRGR-PMP-0066 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.2447 | 74.1266 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-10-31 | Aneesh & Team | [13 empty] | 60 | 60 |  | 165RD/(3TTDD) |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-NGUR-ENB-6017 | I-RJ-NGUR-PMP-0036 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0201 | 73.5139 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | Vikram Jangid Nagaur team | [13 empty] | 60 | 60 |  | NAGRI |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-KESR-ENB-9051 | I-RJ-KESR-PMP-0005 | 2/3 | 2 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9867 | 73.2753 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | Vikram Jangid Nagaur team | [13 empty] | 100 | 55 |  | Panchala |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-NGUR-ENB-9020 | I-RJ-NGUR-PMP-0042 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.0032 | 73.4805 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-31 | 2025-10-31 | 2025-10-31 | 2025-11-01 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | Gudiya |  | DHARMARAM JAJRA | 6376202299 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-SRGR-ENB-9088 | I-RJ-SRGR-PMP-0046 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1905 | 73.6516 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | Aneesh & Team | [13 empty] | 40 | 5 |  | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-9034 | I-RJ-SRGR-PMP-0038 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1152 | 73.6372 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | Aneesh & Team | [13 empty] | 50 | 50 |  | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-VJIG-ENB-I011 | I-RJ-VJIG-PMP-0020 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.0449 | 73.5272 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | Aneesh & Team | [13 empty] | 60 | 60 |  | (2BPM) Gopalpura |  | SURENDER SINGH | 8955001723 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-MKRN-ENB-I014 | I-RJ-MKRN-PMP-0042 | 3 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.0825 | 74.4735 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-01 | Prema Ram Outsource | [13 empty] | 50 | 50 |  | Beenjari |  | JITENDRA PATIDAR | 6350491976 | SUKHDEV ROYAL | 9672742052 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-MRTA-ENB-9115 | I-RJ-MRTA-PMP-0068 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.7882 | 73.8251 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | Vikram Jangid Nagaur team | [13 empty] | 50 | 50 |  | MERTA |  | Arif Khan | 6367853630 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-DDWN-ENB-I028 | I-RJ-DDWN-PMP-0028 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.407 | 74.8057 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | Prema Ram Outsource | [13 empty] | 50 | 5 |  | NOOWA |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MRTA-ENB-I011 | I-RJ-MRTA-PMP-0038 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.7978 | 73.8363 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-02 | Vikram Jangid Nagaur team | [13 empty] | 60 | 5 |  | Gagura |  | Arif Khan | 6367853630 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-GGGR-ENB-I031 | I-RJ-GGGR-PMP-0134 | 1/2/3 | 3 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.9441 | 73.892 | COW | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-02 | 2025-11-03 | 2025-11-02 | 2025-11-03 | Aneesh & Team | [13 empty] | 90 | 50 |  | Amogh Enclave |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JAIPUR
I-RJ-GGGR-ENB-I032 | I-RJ-GGGR-PMP-0132 | 1/2/3 | 3 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.9406 | 73.9049 | COW | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Aneesh & Team | [13 empty] | 90 | 50 |  | Signal Area |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JAIPUR
I-RJ-GGGR-ENB-I033 | I-RJ-GGGR-PMP-0133 | 1/2/3 | 3 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.9472 | 73.9038 | COW | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Aneesh & Team | [13 empty] | 90 | 50 |  | GOC Area - Officer Enclave |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JAIPUR
I-RJ-RSNG-ENB-9041 | I-RJ-RSNG-PMP-0011 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.4527 | 73.532 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Rakesh Outsource | [13 empty] | 50 | 50 |  | Singh Nagar |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-RSNG-ENB-9038 | I-RJ-RSNG-PMP-0010 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.5524 | 73.4811 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Rakesh Outsource | [13 empty] | 50 | 5 |  | Rai Singh Nagar |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-SRGR-ENB-6010 | I-RJ-SRGR-PMP-0026 | 1/2/3 | 3 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.4133 | 73.8765 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Tarachand Ref Rakesh Team | [13 empty] | 180 | 70 |  | SURATGARH CANN |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-KESR-ENB-9061 | I-RJ-KESR-PMP-0009 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1107 | 73.2291 | NBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Vikram Jangid Nagaur team | [13 empty] | 30 | 5 |  | Panchori |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-GJSP-ENB-9003 | I-RJ-GJSP-PMP-0004 | 1 | 1 | A6 I&C | Ganganagar | Ganganagar | Rakesh Outsource |  | Done | 29.6594 | 73.448 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-03 | Rakesh Outsource | [13 empty] | 30 | 5 |  | PADAMPUR |  | Mahender Singh | 6350492130 | Vinod Kumar | 6350492138 | RAMKARAN SHARMA | 9779476669 | JAIPUR
I-RJ-NGUR-ENB-9076 | I-RJ-NGUR-PMP-0048 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2323 | 73.7022 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-30 | 2025-10-30 | 2025-10-30 | 2025-11-02 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | Nagaur |  | MAHENDRA JAT | 8290502749 | BALU RAM | 8355811699 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-DDWN-ENB-I008 | I-RJ-DDWN-PMP-0020 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.3009 | 74.5635 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Prema Ram Outsource | [13 empty] | 120 | 5 |  | Singrawat-Kala |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-I039 | I-RJ-DDWN-PMP-0036 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.2312 | 74.5451 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-03 | Prema Ram Outsource | [13 empty] | 50 | 50 |  | KHOJAS |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-9087 | I-RJ-JAAL-PMP-0015 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.4751 | 73.9526 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Vikram Jangid Nagaur team | [13 empty] | 40 | 5 |  | Jayal |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-VJIG-ENB-9053 | I-RJ-VJIG-PMP-0013 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.3547 | 73.6506 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Rakesh | [13 empty] | 40 | 40 |  | Sri Vijainagar |  | SURENDER SINGH | 8955001723 | SANTOSH KUMAR | 6350491304 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-ANUG-ENB-I017 | I-RJ-ANUG-PMP-0016 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1884 | 73.3293 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Aneesh & Team | [13 empty] | 60 | 60 |  | 64 GB |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-ANUG-ENB-9043 | I-RJ-ANUG-PMP-0009 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.2003 | 73.2945 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Aneesh & Team | [13 empty] | 40 | 40 |  | Anupgarh |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-ANUG-ENB-I018 | I-RJ-ANUG-PMP-0017 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1812 | 73.2736 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Aneesh & Team | [13 empty] | 60 | 5 |  | 2PGM |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-NGUR-ENB-6005 | I-RJ-NGUR-PMP-0026 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.089 | 73.6455 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-10-31 | 2025-10-31 | 2025-11-04 | 2025-10-31 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | KHARNAL |  | MAHENDRA JAT | 8290502749 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-ANUG-ENB-9060 | I-RJ-ANUG-PMP-0010 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1553 | 73.1875 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | Aneesh & Team | [13 empty] | 50 | 50 |  | Anupgarh |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-MKRN-ENB-I002 | I-RJ-MKRN-PMP-0039 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.1264 | 74.6759 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-05 | premaram | [13 empty] | 60 | 5 |  | Deori |  | Prema Dahiya | 6350491992 | MAHENDRA NEHRA | 6350491087 | OM PRAKASH | 6350491377 | JODHPUR
I-RJ-MKRN-ENB-9041 | I-RJ-MKRN-PMP-0031 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.0696 | 74.5199 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-01 | 2025-11-01 | 2025-11-01 | 2025-11-05 | premaram | [13 empty] | 40 | 5 |  | Manani |  | Chiranji Lal | 6350491964 | RICHHPAL GURJAR | 8441931031 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-VJIG-ENB-9028 | I-RJ-VJIG-PMP-0006 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.3565 | 73.6997 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | RAKESH | [13 empty] | 50 | 50 |  | Saroopsar |  | SURENDER SINGH | 8955001723 | SANTOSH KUMAR | 6350491304 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-9115 | I-RJ-SRGR-PMP-0052 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.3241 | 73.751 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-04 | RAKESH | [13 empty] | 40 | 40 |  | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-RSNG-ENB-9034 | I-RJ-RSNG-PMP-0009 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.5174 | 73.487 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-03 | 2025-11-06 | 2025-11-03 | 2025-11-06 | RAKESH | [13 empty] | 50 | 5 |  | Chak 9TK |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-KESR-ENB-I009 | I-RJ-KESR-PMP-0017 | 1/3 | 2 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1122 | 73.5064 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-03 | 2025-11-03 | 2025-11-03 | 2025-11-06 | Aneesh | [13 empty] | 120 | 65 |  | DHEENGASARA |  | PREMA RAM | 6350431991 | BALU RAM | 8355811699 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DDWN-ENB-I031 | I-RJ-DDWN-PMP-0030 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.2383 | 74.3498 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | PREMARAM | [13 empty] | 80 | 45 |  | Beechawa |  | OMVEER SINGH | 9887268550 | KAILASH BHAKAR | 8875805543 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MKRN-ENB-6015 | I-RJ-MKRN-PMP-0027 | 3 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.0968 | 74.4312 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | PREMARAM | [13 empty] | 50 | 5 |  | Ranigaon |  | JITENDRA PATIDAR | 6350491976 | SUKHDEV ROYAL | 9672742052 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-PDMP-ENB-9029 | I-RJ-PDMP-PMP-0008 | 2 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.6136 | 73.8147 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-02 | 2025-11-02 | 2025-11-05 | 2025-11-02 | Tarachand Ref Rakesh Team | [13 empty] | 50 | 5 |  | Padampur |  | RAKESH KUMAR | 7849824288 | VACANT | VACANT | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-SKRN-ENB-9010 | I-RJ-SKRN-PMP-0004 | 2 | 1 | A6 I&C | Ganganagar | Ganganagar | Rakesh Outsource |  | Done | 29.8888 | 73.559 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | Rakesh | [13 empty] | 50 | 5 |  | Village-10 W (2 W-Gurusar) |  | Mahender Singh | 6350492130 | Vinod Kumar | 6350492138 | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-SRHI-ENB-9056 | I-RJ-SRHI-PMP-0020 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.7894 | 72.7675 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | Pawan | [13 empty] | 50 | 50 |  | Sirohi |  | Jagdish Kumar | 6350491299 | JITENDRA KUMAR | 9460654853 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRHI-ENB-6003 | I-RJ-SRHI-PMP-0004 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.7482 | 72.7105 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | Aneesh | [13 empty] | 60 | 60 |  | Pava Puri Jain Temple |  | BHAVESH KUMAR | 9672487892 | JITENDRA KUMAR | 9460654853 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-PDMP-ENB-9019 | I-RJ-PDMP-PMP-0005 | 1 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.7258 | 73.667 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | Tarachand Ref Rakesh Team | [13 empty] | 50 | 5 |  | Padampur |  | HANUMAN DAS | 8239158388 | VACANT | VACANT | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-PDMP-ENB-9038 | I-RJ-PDMP-PMP-0011 | 2 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.5201 | 73.7337 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | Tarachand Ref Rakesh Team | [13 empty] | 50 | 50 |  | Sriganganagar |  | RAKESH KUMAR | 7849824288 | VACANT | VACANT | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-SRGR-ENB-I007 | I-RJ-SRGR-PMP-0064 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.4925 | 73.7143 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | Tarachand Ref Rakesh Team | [13 empty] | 50 | 5 |  | Fardod |  | RAKESH KUMAR | 7849824288 | VAKIL KUMAR | 8078698892 | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-VJIG-ENB-9029 | I-RJ-VJIG-PMP-0007 | 2/3 | 2 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.3998 | 73.5892 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | RAKESH | [13 empty] | 100 | 55 |  | Shri Vijay Nagar |  | SURENDER SINGH | 8955001723 | SANTOSH KUMAR | 6350491304 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-ANUG-ENB-6002 | I-RJ-ANUG-PMP-0001 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.0935 | 73.1369 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | ANEESH | [13 empty] | 60 | 5 |  | PATRODA |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-ANUG-ENB-9068 | I-RJ-ANUG-PMP-0012 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.0506 | 73.1078 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | ANEESH | [13 empty] | 50 | 5 |  | Satrana |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-TSCC-ENB-I001 | I-RJ-TSCC-PMP-0001 | 1/2 | 2 | A6 I&C | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.0208 | 73.1254 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | ANEESH | [13 empty] | 50 | 5 |  | 22AS-B |  | CHET RAM | 6350492121 | Vinod Kumar | 6350492215 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-VJIG-ENB-9019 | I-RJ-VJIG-PMP-0003 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.2849 | 73.5011 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | RAKESH | [13 empty] | 50 | 5 |  | Vijay Nagar |  | SURENDER SINGH | 8955001723 | SANTOSH KUMAR | 6350491304 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-VJIG-ENB-6000 | I-RJ-VJIG-PMP-0001 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Rakesh Outsource |  | Done | 29.3561 | 73.3655 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-06 | RAKESH | [13 empty] | 60 | 5 |  | 4 Ksd |  | SURENDER SINGH | 8955001723 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-MKRN-ENB-I006 | I-RJ-MKRN-PMP-0040 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 26.9654 | 74.5776 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-05 | 2025-11-05 | 2025-11-05 | 2025-11-05 | PREMA | [13 empty] | 60 | 60 |  | NANDOLI MERTIYA |  | JITENDRA PATIDAR | 6350491976 | RICHHPAL GURJAR | 8441931031 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-PDMP-ENB-9024 | I-RJ-PDMP-PMP-0006 | 2 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.6823 | 73.5643 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | Tarachand Ref Rakesh Team | [13 empty] | 50 | 5 |  | Padampur |  | HANUMAN DAS | 8239158388 | VACANT | VACANT | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-PDMP-ENB-I001 | I-RJ-PDMP-PMP-0015 | 2 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.642 | 73.5926 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-07 | 2025-11-07 | 2025-11-07 | [15 empty] | 60 | 5 |  | 6 RB |  | HANUMAN DAS | 8239158388 | VACANT | VACANT | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-PDMP-ENB-9005 | I-RJ-PDMP-PMP-0004 | 3 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.7295 | 73.5798 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-07 | Tarachand | [13 empty] | 50 | 5 |  | Padampur |  | HANUMAN DAS | 8239158388 | VACANT | VACANT | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-NSRB-ENB-9036 | I-RJ-NSRB-PMP-0029 | 2 | 1 | A6 I&C | Kishangarh | Ajmer | Rahul Outsource |  | Done | 26.3256 | 74.9611 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | Rahul Outsource | [13 empty] | 40 | 5 |  | Nasirabad |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JAIPUR
I-RJ-NAWW-ENB-I005 | I-RJ-NAWW-PMP-0035 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.2024 | 74.8344 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | PREMARAM | [13 empty] | 120 | 10 |  | Anandpura |  | Ganpat Ram Khod | 6350491968 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-JAAL-ENB-9083 | I-RJ-JAAL-PMP-0014 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2158 | 74.1767 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-06 | 2025-11-06 | 2025-11-08 | 2025-11-08 | Vikram | [13 empty] | 120 | 45 |  | Jayal |  | RATNA RAM | 6350492259 | KAILASH BHAKAR | 8875805543 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-H002 | I-RJ-JAAL-PMP-0023 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1467 | 74.2457 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | Vikram | [13 empty] | 120 | 65 |  | Bhiniyad Chak-1(A) |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-G005 | I-RJ-JAAL-PMP-0020 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.136 | 74.0679 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | Vikram | [13 empty] | 60 | 5 |  | Fardod |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PNDW-ENB-9014 | I-RJ-PNDW-PMP-0005 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & Team |  | Done | 24.8269 | 73.0073 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | ANEESH | [13 empty] | 60 | 60 |  | Parlai |  | JAYPAL SINGH | 8209403026 | VIMLESH KUMAR TIWARI | 9399419761 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-PNDW-ENB-9003 | I-RJ-PNDW-PMP-0003 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & Team |  | Done | 24.7664 | 73.0255 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | ANEESH | [13 empty] | 60 | 60 |  | Hajari |  | JAYPAL SINGH | 8209403026 | GHEESULAL MEENA | 6350492186 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-PNDW-ENB-9022 | I-RJ-PNDW-PMP-0010 | 1/2 | 2 | A6 I&C | Sirohi | Sirohi | Aneesh & Team |  | Done | 24.7169 | 73.0926 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-08 | ANEESH | [13 empty] | 60 | 60 |  | Garat |  | JAYPAL SINGH | 8209403026 | GHEESULAL MEENA | 6350492186 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-NAWW-ENB-H003 | I-RJ-NAWW-PMP-0031 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.1039 | 75.2447 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-12 | PREMARAM | [13 empty] | 120 | 10 |  | Dawali |  | MANGEE LAL | 8078698924 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9092 | I-RJ-NAWW-PMP-0018 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.1379 | 74.9692 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-12 | PREMARAM | [13 empty] | 40 | 5 |  | Indokha |  | Ganpat Ram Khod | 6350491968 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I011 | I-RJ-NAWW-PMP-0062 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.1924 | 74.994 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-07 | 2025-11-07 | 2025-11-07 | 2025-11-12 | PREMARAM | [13 empty] | 120 | 65 |  | Indali |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I021 | I-RJ-NAWW-PMP-0045 | 2 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.2584 | 75.0408 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-12 | PREMARAM | [13 empty] | 50 | 50 |  | Nalot |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-G002 | I-RJ-NAWW-PMP-0027 | 2 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.3455 | 75.0834 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-12 | PREMARAM | [13 empty] | 60 | 5 |  | Lalas |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9056 | I-RJ-NAWW-PMP-0005 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.35 | 75.0435 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-12 | PREMARAM | [13 empty] | 80 | 80 |  | Nehru Nagar |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9086 | I-RJ-NAWW-PMP-0015 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.3221 | 75.0089 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-12 | PREMARAM | [13 empty] | 40 | 5 |  | Adaksar |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KCMC-ENB-9007 | I-RJ-KCMC-PMP-0013 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.2964 | 74.9614 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-12 | PREMARAM | [13 empty] | 40 | 5 |  | Suratpura |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9070 | I-RJ-NAWW-PMP-0050 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.3242 | 74.9498 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-12 | PREMARAM | [13 empty] | 80 | 10 |  | Chawandiya |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-LDNU-ENB-I010 | I-RJ-LDNU-PMP-0027 | 2/3 | 2 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.47 | 74.3558 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Prema Ram Outsource | [13 empty] | 100 | 55 |  | GenanaCOW NN |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-H002 | I-RJ-DDWN-PMP-0017 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.3792 | 74.6888 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-02 | 2025-11-11 | 2025-11-02 | 2025-11-11 | Prema Ram Outsource | [13 empty] | 50 | 50 |  | Phogri |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PDMP-ENB-6001 | I-RJ-PDMP-PMP-0001 | 2 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.6161 | 73.8763 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-02 | 2025-11-02 | 2025-11-02 | 2025-11-09 | Tarachand | [13 empty] | 60 | 5 |  | 49 LLW |  | RAKESH KUMAR | 7849824288 | Sandeep Kumar | 6350491320 | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-DDWN-ENB-G003 | I-RJ-DDWN-PMP-0013 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.2501 | 74.7834 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | PREMARAM | [13 empty] | 60 | 5 |  | Nimod |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KCMC-ENB-I001 | I-RJ-KCMC-PMP-0017 | 3 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.2089 | 74.8182 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-09 | PREMARAM | [13 empty] | 60 | 5 |  | Ranasar |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PNDW-ENB-9016 | I-RJ-PNDW-PMP-0006 | 2 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.6052 | 72.8885 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | Aneesh | [13 empty] | 60 | 60 |  | Deora |  | MAHENDRA KUMAR | 9694971304 | DEVENDRA KUMAR | 7611913941 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-AJMR-ENB-I038 | I-RJ-AJMR-PMP-0296 | 1 | 1 | A6 I&C | Ajmer | Ajmer | Rahul Outsource |  | Done | 26.4915 | 74.7545 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR73 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-09 | Rahul Outsource | [13 empty] | 5 | 60 |  | Nolkha |  | GYAN SINGH RAWAT | 7014970918 | RAKESH KUMAR | 8740029627 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-REAR-ENB-9053 | I-RJ-REAR-PMP-0006 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.7224 | 72.495 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | Pawan | [13 empty] | 40 | 40 |  | Harni Amarpura |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRHI-ENB-9028 | I-RJ-SRHI-PMP-0014 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.8311 | 72.5542 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-09 | Pawan | [13 empty] | 50 | 5 |  | Mermandawara |  | Jagdish Kumar | 6350491299 | VACANT | VACANT | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRGR-ENB-I017 | I-RJ-SRGR-PMP-0103 | 1 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.1619 | 73.6568 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR73 | 2025-11-04 | 2025-11-05 | 2025-11-09 | 2025-11-10 | 2025-11-09 | 2025-11-10 | Tarachand | [13 empty] | 5 | 60 |  | 3 BMM |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRHI-ENB-9064 | I-RJ-SRHI-PMP-0024 | 2 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.872 | 72.578 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | Pawan | [13 empty] | 40 | 5 |  | Jaila |  | Jagdish Kumar | 6350491299 | VACANT | VACANT | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-PNDW-ENB-9065 | I-RJ-PNDW-PMP-0020 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.7255 | 72.9738 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-09 | Aneesh | [13 empty] | 40 | 5 |  | Nema Ram/Peshua |  | JAYPAL SINGH | 8209403026 | GHEESULAL MEENA | 6350492186 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRGR-ENB-9096 | I-RJ-SRGR-PMP-0093 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.1283 | 73.788 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR73 | 2025-11-04 | 2025-11-05 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-10 | TARACHAND | [13 empty] | 5 | 50 |  | Suratgarh |  | ASHOK SHARMA | 7733865665 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-KESR-ENB-I002 | I-RJ-KESR-PMP-0014 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Aneesh & Team |  | Done | 27.1096 | 73.2248 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-06 | 2025-11-06 | 2025-11-06 | 2025-11-18 | Pawan | [13 empty] | 60 | 5 |  | Panchori |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-MOSR-ENB-9004 | I-RJ-MOSR-PMP-0003 | 2 | 1 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.2076 | 74.4185 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | Premaram | [18 empty] | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KESR-ENB-H001 | I-RJ-KESR-PMP-0013 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Pawan & Team |  | Done | 27.2077 | 73.2435 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | Pawan | [13 empty] | 50 | 50 |  | Tantwas |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MKRN-ENB-9061 | I-RJ-MKRN-PMP-0052 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.1518 | 74.5506 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | Premaram | [18 empty] | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-BALI-ENB-9060 | I-RJ-BALI-PMP-0024 | 3 | 1 | A6+B6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 25.2469 | 73.3808 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-18 | ANEESH | [18 empty] | Jagdish Singh | 9928029065 | Rajendra Kumar | 9413139121 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-NGUR-ENB-G001 | I-RJ-NGUR-PMP-0059 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2364 | 73.6515 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-18 | Pawan | [18 empty] | BHANWAR LAL LATIYAL | 8003714631 | BALU RAM | 8355811699 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JLOR-ENB-9062 | I-RJ-JLOR-PMP-0024 | 3 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.3549 | 72.6007 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | Aneesh | [13 empty] | 40 | 5 |  | Ashirwad Colony |  | ANKIT KUMAR DHANWAL | 9315079392 | GANPAT LAL | 8290147329 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-TONK-ENB-9038 | I-RJ-TONK-PMP-0054 | 2 | 1 | A6 I&C | Tonk | Ajmer | Suresh & Team |  | Done | 25.9752 | 75.6679 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | Suresh | [13 empty] | 50 | 5 |  | Bharni |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JAIPUR
I-RJ-SEGN-ENB-I001 | I-RJ-SEGN-PMP-0018 | 2 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 25.0766 | 72.9888 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-17 | Aneesh | [13 empty] | 60 | 5 |  | Posailia |  | VINOD KUMAR | 8094636604 | ARJUN LAL | 8955001722 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-PNDW-ENB-9029 | I-RJ-PNDW-PMP-0014 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.549 | 72.9877 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-09 | 2025-11-11 | 2025-11-09 | 2205-11-13 | Pawan | [13 empty] | 50 | 50 |  | Salphi ki phali |  | MAHENDRA KUMAR | 9694971304 | DEVENDRA KUMAR | 7611913941 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-ABRD-ENB-9009 | I-RJ-ABRD-PMP-0003 | 1/2 | 2 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.4965 | 72.8204 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2205-11-13 | Pawan | [13 empty] | 120 | 120 |  | Ore |  | RAVI KUMAR | 7014503722 | SURESH KUMAR | 9664276191 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-ABRD-ENB-9034 | I-RJ-ABRD-PMP-0008 | 1/2 | 2 | A6 I&C | Sirohi | Sirohi | Aneesh & Team |  | Done | 24.4773 | 72.8838 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Aneesh | [13 empty] | 100 | 55 |  | Aburoad |  | RAVI KUMAR | 7014503722 | SURESH KUMAR | 9664276191 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-RNWR-ENB-9046 | I-RJ-RNWR-PMP-0011 | 1/2/3 | 3 | A6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 24.7282 | 72.1747 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | Aneesh & Team | [13 empty] | 120 | 45 |  | Sewadiya |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-MNAB-ENB-6000 | I-RJ-MNAB-PMP-0001 | 3 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & Team |  | Done | 24.6038 | 72.7358 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-12 | Pawan | [13 empty] | 30 | 30 |  | Gyan sarover |  | SHIVKARAN SINGH | 8003396261 | SURESH KUMAR | 9664276191 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SNCE-ENB-I029 | I-RJ-SNCE-PMP-0047 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 24.8086 | 71.7777 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | Aneesh & Team | [13 empty] | 50 | 50 |  | DhamanaJLR_U |  | CHANDAN MAL | 9783284500 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-ABRD-ENB-9055 | I-RJ-ABRD-PMP-0013 | 3 | 1 | A6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.5496 | 72.8228 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Aneesh | [13 empty] | 50 | 5 |  | Abu Road |  | RAVI KUMAR | 7014503722 | SURESH KUMAR | 9664276191 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SNCE-ENB-H004 | I-RJ-SNCE-PMP-0028 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 24.9359 | 71.4014 | GBT | 0 | A6 I&C , ATP11A & 11C |  | 1 A6 FAULTY/ REPLACED WITH A6 AND STUB ON 31TH JAN BY ANEESH | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | Aneesh | [13 empty] | 60 | 5 |  | Doogri |  | RAM GOPAL | 9571316104 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-I003 | I-RJ-SNCE-PMP-0031 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 25.0197 | 71.6257 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | Aneesh | [13 empty] | 60 | 60 |  | VEERAWA |  | RAM GOPAL | 9571316104 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-CWAN-ENB-9010 | I-RJ-CWAN-PMP-0004 | 1/3 | 2 | A6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 24.9207 | 71.7401 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-14 | Aneesh | [13 empty] | 80 | 45 |  | Siwara |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JLJH
I-RJ-REAR-ENB-9034 | I-RJ-REAR-PMP-0003 | 3 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.6795 | 72.6736 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-13 | Pawan | [13 empty] | 50 | 5 |  | Reodar |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-MNAB-ENB-I002 | I-RJ-MNAB-PMP-0006 | 3 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.5843 | 72.716 | RTP | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | Pawan | [13 empty] | 40 | 5 |  | Gomukh Road |  | SHIVKARAN SINGH | 8003396261 | SURESH KUMAR | 9664276191 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRHI-ENB-9043 | I-RJ-SRHI-PMP-0016 | 1/2 | 2 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.9662 | 72.7777 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-10 | PAWAN | [13 empty] | 120 | 65 |  | Road at post udd |  | Jagdish Kumar | 6350491299 | JITENDRA KUMAR | 9460654853 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRHI-ENB-9042 | I-RJ-SRHI-PMP-0015 | 2 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.9219 | 72.6911 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-08 | 2025-11-08 | 2025-11-08 | 2025-11-10 | PAWAN | [13 empty] | 50 | 5 |  | Kalindri |  | Jagdish Kumar | 6350491299 | JITENDRA KUMAR | 9460654853 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-REAR-ENB-9033 | I-RJ-REAR-PMP-0002 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.5906 | 72.5612 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Pawan | [13 empty] | 50 | 5 |  | Karoti |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRGR-ENB-9094 | I-RJ-SRGR-PMP-0083 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 28.9987 | 73.9021 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR73 | 2025-11-04 | 2025-11-05 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | TARACHAND | [13 empty] | 5 | 40 |  | Suratgarh |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-REAR-ENB-9036 | I-RJ-REAR-PMP-0004 | 2 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.5995 | 72.4893 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | Pawan | [13 empty] | 50 | 50 |  | Reodar |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-SRGR-ENB-I009 | I-RJ-SRGR-PMP-0091 | 1/2 | 2 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.3735 | 73.8163 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR73 | 2025-11-04 | 2025-11-05 | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | TARACHAND | [13 empty] | 10 | 120 |  | 1 SGM |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-REAR-ENB-I001 | I-RJ-REAR-PMP-0012 | 1/2 | 2 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.6701 | 72.4963 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-10 | Pawan | [13 empty] | 120 | 65 |  | JEERAVAL |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-NWAI-ENB-I007 | I-RJ-NWAI-PMP-0043 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Suresh & Team |  | Done | 26.5067 | 75.795 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Suresh | [13 empty] | 120 | 65 |  | RAHOLI |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JAIPUR
I-RJ-RNWR-ENB-9037 | I-RJ-RNWR-PMP-0008 | 3 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.7554 | 72.2036 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Pawan | [16 empty] | Raniwara |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-6004 | I-RJ-SNCE-PMP-0002 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.0154 | 71.7743 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Aneesh | [16 empty] | Sahu and Dookiyon Ki Dhani |  | DHANESH KUMAR | 9772728785 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RNWR-ENB-6004 | I-RJ-RNWR-PMP-0001 | 3 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.7841 | 72.0757 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Pawan | [16 empty] | Satroo |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SRGR-ENB-G001 | I-RJ-SRGR-PMP-0057 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.4489 | 73.8772 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-11 | TARACHAND | [5 empty] | NO | NO | NA |  |  | Ready |  |  | 70 | 70 | 0 | Lalpura Paliwala |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-HMGR-ENB-6006 | I-RJ-HMGR-PMP-0032 | 3 | 1 | A6 I&C | Hanumangarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.2833 | 74.4782 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-12 | TARACHAND | [13 empty] | 60 | 5 |  | 9 Bpm |  | VACANT | VACANT | RANJEET SINGH | 8239827805 | VACANT | VACANT | JAIPUR
I-RJ-BNML-ENB-I007 | I-RJ-BNML-PMP-0015 | 3 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.0645 | 72.4509 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | Pawan | [13 empty] | 50 | 50 |  | Jodwara U |  | KAILASH KUMAR | 8058302215 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-SNCE-ENB-A004 | I-RJ-SNCE-PMP-0025 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 24.82 | 71.6966 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-12 | 2025-11-12 | 2025-11-12 | 2025-11-14 | Aneesh | [13 empty] | 50 | 5 |  | Amli |  | CHANDAN MAL | 9783284500 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-LDNU-ENB-9060 | I-RJ-LDNU-PMP-0040 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.5492 | 74.6941 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | Premaram | [18 empty] | BALDEWA RAM | 8058503498 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-Y001 | I-RJ-DDWN-PMP-0041 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.4747 | 74.6966 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-14 | Premaram | [18 empty] | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-RNWR-ENB-9036 | I-RJ-RNWR-PMP-0007 | 1 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.7615 | 72.3182 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Pawan | [13 empty] | 40 | 40 |  | Raniwara |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RNWR-ENB-I009 | I-RJ-RNWR-PMP-0019 | 2/3 | 2 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.6731 | 72.2763 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-11 | 2025-11-11 | 2025-11-11 | 2025-11-11 | Pawan | [13 empty] | 120 | 5 |  | BaragaonJLR |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-ANUG-ENB-A001 | I-RJ-ANUG-PMP-0013 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.118 | 73.1634 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR73 | 2025-11-04 | 2025-11-05 | 2025-11-13 | 2025-11-13 | 2025-11-13 | 2025-11-13 | Tarachand | [13 empty] | 60 | 60 |  | Chak 6P |  | DAULAT RAM | 6350492122 | SUNIL KUMAR | 6350616507 | RAJA RAM | 8003992944 | JLKD
I-RJ-DENA-ENB-I009 | I-RJ-DENA-PMP-0034 | 1 | 1 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9057 | 74.135 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Vikram | [13 empty] | 60 | 5 |  | BHADWASI |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-SNCE-ENB-9010 | I-RJ-SNCE-PMP-0007 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.9148 | 71.7385 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Aneesh | [16 empty] | Sivada |  | DHANESH KUMAR | 9772728785 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-DENA-ENB-9087 | I-RJ-DENA-PMP-0019 | 2 | 1 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.6936 | 74.2665 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Vikram | [13 empty] | 40 | 5 |  | Degana |  | IMARAN KHAN | 9887333514 | SALEEM MOHAMMAD DESHWALI | 7891896395 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-RNWR-ENB-V001 | I-RJ-RNWR-PMP-0025 | 2 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.7917 | 72.2707 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | Pawan | [16 empty] | Malwara |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RNWR-ENB-I004 | I-RJ-RNWR-PMP-0017 | 2 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.9324 | 72.1747 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-11-16 | Pawan | [13 empty] | 60 | 60 |  | Bandhar |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-9014 | I-RJ-SNCE-PMP-0010 | 2/3 | 2 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.7937 | 71.7818 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2205-11-15 | Aneesh | [16 empty] | Opp Shree Radheshwar Stone |  | CHANDAN MAL | 9783284500 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-MPUR-ENB-9036 | I-RJ-MPUR-PMP-0038 | 2/3 | 2 | A6 I&C | Tonk | Ajmer | Suresh & Team |  | Done | 26.3742 | 75.4746 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-16 | Suresh | [13 empty] | 100 | 55 |  | Malpura |  | SATYANARAYAN SINGH | 7665666391 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT | JAIPUR
I-RJ-REAR-ENB-I008 | I-RJ-REAR-PMP-0016 | 3 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.5809 | 72.3573 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-10 | 2025-11-11 | 2025-11-10 | 2025-11-11 | Pawan | [13 empty] | 60 | 60 |  | PEETHAPURA |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-BORA-ENB-I011 | I-RJ-BORA-PMP-0013 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.2123 | 71.9766 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | Aneesh | [13 empty] | 50 | 50 |  | BC Bagora Infill |  | SHARWAN KUMAR | 6378280042 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-DDWN-ENB-9104 | I-RJ-DDWN-PMP-0051 | 1/2 | 2 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.4399 | 74.6807 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | Premaram | [18 empty] | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-BORA-ENB-I002 | I-RJ-BORA-PMP-0009 | 1/2 | 2 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.0713 | 72.1222 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | Pawan | [13 empty] | 120 | 65 |  | JERAN |  | MAHBUB KHAN | 7045641935 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-JAAW-ENB-I002 | I-RJ-JAAW-PMP-0016 | 3 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.3469 | 72.2763 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | Aneesh | [13 empty] | 60 | 60 |  | MOKNI KHERA |  | DUNGARA RAM | 7849824302 | UPENDRA KUMAR | 9799877374 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-DOLI-ENB-I007 | I-RJ-DOLI-PMP-0034 | 1/2 | 2 | A6 I&C | Tonk | Ajmer | Suresh & Team |  | Done | 25.9131 | 75.3358 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | Suresh | [13 empty] | 120 | 10 |  | Thanwala |  | Chetan Prakash Jat | 6350491764 | JAWAN SINGH RAJPUT | 6376917823 | VACANT | VACANT | JAIPUR
I-RJ-DDWN-ENB-A001 | I-RJ-DDWN-PMP-0011 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.4462 | 74.6463 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-16 | Premaram | [18 empty] | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MOSR-ENB-9003 | I-RJ-MOSR-PMP-0004 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.3176 | 74.6721 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-16 | Premaram | [18 empty] | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NGUR-ENB-I017 | I-RJ-NGUR-PMP-0064 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.4507 | 73.8276 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-04 | 2025-11-04 | 2025-11-04 | 2025-11-20 | Vikram | [13 empty] | 60 | 60 |  | CHAU |  | BHARAT THALOR | 8078698860 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-RNWR-ENB-I013 | I-RJ-RNWR-PMP-0020 | 1/2 | 2 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.9193 | 72.2715 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2205-11-20 | Aneesh | [13 empty] | 120 | 5 |  | KoriChaupawatan_G |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RNWR-ENB-I006 | I-RJ-RNWR-PMP-0018 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.8491 | 72.0376 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Aneesh | [13 empty] | 60 | 60 |  | KOTRA |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-MENW-ENB-9011 | I-RJ-MENW-PMP-0009 | 1/2/3 | 3 | A6 I&C | Nagaur | Nagaur | Pawan & Team |  | Done | 26.6553 | 73.7395 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | Pawan | [16 empty] | Gotan |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SNCE-ENB-6006 | I-RJ-SNCE-PMP-0003 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.7569 | 71.9949 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | Aneesh | [16 empty] | SANKAR |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RNWR-ENB-H001 | I-RJ-RNWR-PMP-0015 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.7111 | 72.1028 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-19 | 2025-11-19 | 2025-11-19 | 2025-11-19 | Aneesh | [13 empty] | 60 | 5 |  | Maitriwara |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-MRTA-ENB-I019 | I-RJ-MRTA-PMP-0040 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Pawan & Team |  | Done | 26.6034 | 73.7219 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Pawan | [13 empty] | 60 | 5 |  | Talanpur |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-MENW-ENB-V001 | I-RJ-MENW-PMP-0006 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Pawan & Team |  | Done | 26.6391 | 73.7397 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Pawan | [16 empty] | JKCementColony |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DENA-ENB-9097 | I-RJ-DENA-PMP-0021 | 1 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.7604 | 74.4514 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-18 | 2025-11-18 | 2025-11-18 | 2025-11-22 | Pawan | [13 empty] | 40 | 5 |  | Degana |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9081 | I-RJ-DENA-PMP-0016 | 1 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.6813 | 74.4842 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | Pawan | [13 empty] | 40 | 5 |  | Riya Bari |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9100 | I-RJ-DENA-PMP-0059 | 2 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.7406 | 74.4152 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-17 | 2025-11-17 | 2025-11-17 | 2025-11-22 | Pawan | [18 empty] | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-KCRA-ENB-G001 | I-RJ-KCRA-PMP-0003 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9912 | 73.97 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-09 | 2025-11-09 | 2025-11-09 | 2025-11-22 | Pawan | [13 empty] | 50 | 5 |  | Mahio Ka Mohalla |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-PASS-ENB-A001 | I-RJ-PASS-PMP-0015 | 2 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.9553 | 74.768 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-16 | 2025-11-16 | 2025-11-16 | 2025-11-22 | Pawan | [13 empty] | 50 | 5 |  | Khokhar |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MRTA-ENB-6006 | I-RJ-MRTA-PMP-0004 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.6468 | 74.1894 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-21 | Pawan | [13 empty] | 50 | 5 |  | Lampolai |  | IMARAN KHAN | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-NAWW-ENB-9098 | I-RJ-NAWW-PMP-0054 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.2697 | 75.0716 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-20 | Premaram | [16 empty] | LAMBA |  | MANGEE LAL | 8078698924 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-RSNG-ENB-9050 | I-RJ-RSNG-PMP-0045 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.521 | 73.5321 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-20 | 2025-11-20 | 2025-11-20 | 2025-11-21 | Tarachand | [16 empty] | Rai Singh Nagar |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-MRTA-ENB-I005 | I-RJ-MRTA-PMP-0036 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Pawan & Team |  | Done | 26.5368 | 74.0284 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | Pawan | [13 empty] | 50 | 5 |  | AAKELI |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-NAWW-ENB-9071 | I-RJ-NAWW-PMP-0009 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.0613 | 75.0469 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-25 | Premaram | [16 empty] | Bhagwanpura |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-H001 | I-RJ-NAWW-PMP-0029 | 3 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.3178 | 75.0336 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | Premaram | [18 empty] | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9068 | I-RJ-DENA-PMP-0047 | 2 | 1 | A6 I&C | Makrana | Nagaur | Pawan & Team |  | Done | 26.9495 | 74.3016 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | Pawan | [18 empty] | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-JAAL-ENB-9075 | I-RJ-JAAL-PMP-0042 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Pawan & Team |  | Done | 27.2563 | 74.2238 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-22 | 2025-11-22 | 2025-11-22 | 2025-11-22 | Pawan | [18 empty] | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-SOJT-ENB-9056 | I-RJ-SOJT-PMP-0036 | 2 | 1 | A6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 26.0662 | 73.6192 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-22 | Aneesh | [18 empty] | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SOJT-ENB-9054 | I-RJ-SOJT-PMP-0040 | 2 | 1 | A6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 26.0629 | 73.7812 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-22 | Aneesh | [18 empty] | Mangi Lal Bairwa | 9828846903 | SAMER ALI | 7073800169 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-JAAN-ENB-9046 | I-RJ-JAAN-PMP-0037 | 3 | 1 | A6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 26.2209 | 73.9846 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-21 | Aneesh | [18 empty] | Nathu Singh | 9660202162 | DURGARAM HARSALIYA | 8529607895 | VACANT | VACANT | JLJH
I-RJ-RSNG-ENB-I001 | I-RJ-RSNG-PMP-0052 | 2/3 | 2 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.396 | 73.2126 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-24 | Tarachand | [16 empty] | 22 PTD-B |  | RAM KUMAR | 7849824285 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JLKD
I-RJ-MKRN-ENB-6016 | I-RJ-MKRN-PMP-0028 | 1/2 | 2 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.021 | 74.7658 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-25 | 2025-11-25 | 2025-11-25 | 2025-11-25 | Premaram | [13 empty] | 100 | 10 |  | GUDA RPTR |  | Chiranji Lal | 6350491964 | Devilal Gurjar | 8078699370 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-MRTA-ENB-9013 | I-RJ-MRTA-PMP-0011 | 1 | 1 | A6 I&C | Nagaur | Nagaur | VIKRAM/ Pawan & Team |  | Done | 26.7253 | 74.0652 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-21 | 2025-11-23 | 2025-11-21 | 2025-11-29 | Vikram | [13 empty] | 60 | 60 |  | Santa Ki Dhani |  | IMARAN KHAN | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-PALI-ENB-V001 | I-RJ-PALI-PMP-0090 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 25.7782 | 73.2901 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR77 | 2025-11-20 | 2025-11-21 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | Aneesh | [16 empty] | Cotton mail |  | JAGDISH SINGH | 8302540479 | RAVINDRA SINGH | 9079623229 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SRGR-ENB-I020 | I-RJ-SRGR-PMP-0097 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.0992 | 74.127 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-24 | Tarachand | [16 empty] | GUSAINSAR |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-NAWW-ENB-9061 | I-RJ-NAWW-PMP-0067 | 1/2/3 | 3 | A6+B6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.2759 | 74.9215 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-23 | 2025-11-23 | 2025-11-23 | 2025-11-23 | Premaram | [16 empty] | Shiv |  | Ganpat Ram Khod | 6350491968 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9059 | I-RJ-NAWW-PMP-0006 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.108 | 74.9066 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-21 | 2025-11-21 | 2025-11-22 | 2025-11-25 | Premaram | [16 empty] | kuchaman city |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9074 | I-RJ-NAWW-PMP-0011 | 1 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.1546 | 74.9956 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR76 | 2025-11-15 | 2025-11-17 | 2025-11-21 | 2025-11-21 | 2025-11-21 | 2025-11-25 | Premaram | [16 empty] | Kankriya |  | RAMESHWAR LAL | 6350491990 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NGUR-ENB-9038 | I-RJ-NGUR-PMP-0045 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.8631 | 73.6338 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-27 | Vikram | [13 empty] | 50 | 5 |  | kankdai |  | DHARMARAM JAJRA | 6376202299 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JODHPUR
I-RJ-MRTA-ENB-9086 | I-RJ-MRTA-PMP-0057 | 1/2 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.7831 | 74.0597 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-28 | 2025-11-29 | 2025-11-28 | 2025-11-29 | Vikram | [16 empty] | Thala ki Dhani |  | Arif Khan | 6367853630 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-PNDW-ENB-I010 | I-RJ-PNDW-PMP-0051 | 1/2/3 | 3 | A6+B6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.7923 | 73.0438 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR77 | 2025-11-20 | 2025-11-21 | 2025-11-29 | 2025-11-29 | 2025-11-29 | 2025-11-29 | Aneesh | [16 empty] | SirohiRoad-new |  | JAYPAL SINGH | 8209403026 | VIMLESH KUMAR TIWARI | 9399419761 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-PNDW-ENB-I011 | I-RJ-PNDW-PMP-0048 | 1/2/3 | 3 | A6+B6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.7908 | 73.054 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR77 | 2025-11-20 | 2025-11-21 | 2025-11-28 | 2025-11-28 | 2025-11-28 | 2025-11-28 | Aneesh | [16 empty] | Pindwara |  | JAYPAL SINGH | 8209403026 | VIMLESH KUMAR TIWARI | 9399419761 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-SMRP-ENB-9056 | I-RJ-SMRP-PMP-0020 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 25.3064 | 73.1684 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR77 | 2025-11-20 | 2025-11-21 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-11-24 | Aneesh | [16 empty] | SUMERPUR |  | HANWANT KUMAR | 9351228535 | SHRAWAN KUMAR | 9326488412 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SNCE-ENB-V001 | I-RJ-SNCE-PMP-0066 | 1/2/3 | 3 | A6+B6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.754 | 71.7768 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR77 | 2025-11-20 | 2025-11-21 | 2025-11-26 | 2025-11-26 | 2025-11-26 | 2025-11-26 | Aneesh | [16 empty] | Sanchore |  | CHANDAN MAL | 9783284500 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-NGUR-ENB-I001 | I-RJ-NGUR-PMP-0102 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1994 | 73.7425 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR75 | 2025-11-14 | 2025-11-14 | 2025-11-27 | 2025-11-27 | 2025-11-27 | 2025-11-30 | Vikram | [16 empty] | Tehsil,Nagaur |  | MAHENDRA JAT | 8290502749 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MKRN-ENB-I013 | I-RJ-MKRN-PMP-0075 | 1/2/3 | 3 | A6+B6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.8646 | 74.4083 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR69 | 2025-10-11 | 2025-10-11 | 2025-11-28 | 2025-11-30 | 2025-11-28 | 2025-11-30 | Premaram | [16 empty] | BAJOLI |  | JITENDRA PATIDAR | 6350491976 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-RAPR-ENB-9047 | I-RJ-RAPR-PMP-0023 | 1/3 | 2 | A6+B6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 26.1124 | 73.8732 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR77 | 2025-11-20 | 2025-11-21 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | Aneesh | [16 empty] | Seengla |  | Nathu Singh | 9660202162 | DURGARAM HARSALIYA | 8529607895 | VACANT | VACANT | JLJH
I-RJ-NWAI-ENB-9067 | I-RJ-NWAI-PMP-0027 | 1/2/3 | 3 | A6 I&C | Tonk | Ajmer | Sandeep/Suresh & Team |  | Done | 26.3666 | 75.9322 | RTT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | 2025-11-14 | 2025-11-14 | 2025-11-14 | 2025-12-02 | Sandeep | [13 empty] | 90 | 50 |  | Niwai |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | JAIPUR
I-RJ-SNCE-ENB-I007 | I-RJ-SNCE-PMP-0034 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.0204 | 71.8339 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | Aneesh | [18 empty] | DHANESH KUMAR | 9772728785 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-BNML-ENB-I011 | I-RJ-BNML-PMP-0046 | 3 | 1 | A6+B6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.0548 | 72.3464 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-06 | 2025-12-07 | 2025-12-06 | 2025-12-07 | ANEESH | [16 empty] | LEDARMER |  | GHAN SHYAM | 9351930732 | APEEL SINGH | 7568739839
I-RJ-DDWN-ENB-9093 | I-RJ-DDWN-PMP-0044 | 1/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.3895 | 74.5601 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-07 | 2025-12-07 | 2025-12-08 | 2025-12-08 | Premaram | [16 empty] | Bangla Bass Didwana |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561
I-RJ-NGUR-ENB-9017 | I-RJ-NGUR-PMP-0098 | 2 | 1 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.2631 | 73.8552 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-07 | 2025-12-07 | 2025-12-08 | 2025-12-08 | Vikram | [16 empty] | Harima |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501
I-RJ-MKRN-ENB-I008 | I-RJ-MKRN-PMP-0077 | 1/2/3 | 3 | A6+B6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 26.9965 | 74.5161 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | premaram | [16 empty] | GEHRA KALAN |  | JITENDRA PATIDAR | 6350491976 | Girwar Singh | 6350491970
I-RJ-PNDW-ENB-I009 | I-RJ-PNDW-PMP-0043 | 1/3 | 2 | A6+B6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.5831 | 72.9007 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-09 | 2025-12-09 | 2025-12-09 | 2025-12-09 | Aneesh | [16 empty] | Bhimana |  | MAHENDRA KUMAR | 9694971304 | DEVENDRA KUMAR | 7611913941
I-RJ-RAPR-ENB-9011 | I-RJ-RAPR-PMP-0031 | 2/3 | 2 | A6+B6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 25.996 | 73.9562 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-10 | 2025-12-10 | 2025-12-10 | 2025-12-10 | Aneesh | [16 empty] | Gudiya |  | BARKAT MOHMMAD | 6350491310 | PINKU SINGH | 9660860336
I-RJ-PASS-ENB-G005 | I-RJ-PASS-PMP-0020 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.81 | 74.5902 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | 2025-11-18 | 2025-12-11 | 2025-11-18 | 2025-12-11 | premaram | [13 empty] | 60 | 5 |  | Bagot |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-RSNG-ENB-9076 | I-RJ-RSNG-PMP-0053 | 1 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.6491 | 73.4135 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-15 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Tarachand Ref Rakesh Team | [16 empty] | Raisinghnagar |  | RAM KUMAR | 7849824285 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JAIPUR
I-RJ-SEGN-ENB-9035 | I-RJ-SEGN-PMP-0035 | 1/2/3 | 3 | A6+B6 I&C | Sirohi | Sirohi | Aneesh & Team |  | Done | 25.1548 | 73.0535 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-16 | Aneesh & Team | [16 empty] | Sheoganj |  | Babulal meena | 6350491325 | ARJUN LAL | 8955001722 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-DDWN-ENB-9081 | I-RJ-DDWN-PMP-0071 | 2/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.0813 | 74.3814 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-15 | 2025-12-15 | 2025-12-16 | 2025-12-15 | Prema Ram Outsource | [16 empty] | Bajiyon Ki Dhani |  | JITENDRA PATIDAR | 6350491976 | SUKHDEV ROYAL | 9672742052 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-KESR-ENB-V003 | I-RJ-KESR-PMP-0028 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9771 | 73.4062 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-11 | 2025-12-12 | 2025-12-12 | 2025-12-19 | Vikram | [16 empty] | Khimsar |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703
I-RJ-JAAL-ENB-I006 | I-RJ-JAAL-PMP-0057 | 1/2 | 2 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1057 | 74.1007 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-16 | 2025-12-16 | 2025-12-16 | 2025-12-17 | Vikram | [16 empty] | DEHARI |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501
I-RJ-PNDW-ENB-9062 | I-RJ-PNDW-PMP-0044 | 1 | 1 | A6+B6 I&C | Sirohi | Sirohi | Aneesh & team |  | Done | 24.6225 | 72.9782 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | 2025-12-08 | 2025-12-18 | 2025-12-17 | 2025-12-22 | Aneesh & team | [16 empty] | Vasa |  | MAHENDRA KUMAR | 9694971304 | DEVENDRA KUMAR | 7611913941
I-RJ-MKRN-ENB-9040 | I-RJ-MKRN-PMP-0061 | 2/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.0446 | 74.4326 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-16 | 2025-12-18 | 2025-12-17 | 2025-12-18 | Premaram | [16 empty] | Noondara |  | JITENDRA PATIDAR | 6350491976 | SUKHDEV ROYAL | 9672742052 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-ANUG-ENB-9072 | I-RJ-ANUG-PMP-0034 | 2 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.2978 | 73.2614 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-17 | 2025-12-18 | 2025-12-18 | 2025-12-18 | Tarachand | [16 empty] | Anupgarh |  | DAULAT RAM | 6350492122 | SANDEEP GHOYAL | 8875966264 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SNNU-ENB-I002 | I-RJ-SNNU-PMP-0003 | 1/2 | 2 | A6+B6 I&C | Sirohi | Sirohi | Aneesh & Team |  | Done | 24.508 | 72.7928 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-17 | 2025-12-17 | 2025-12-17 | 2025-12-22 | Aneesh | [16 empty] | Akhara Bhatta |  | RAVI KUMAR | 7014503722 | SURESH KUMAR | 9664276191 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JODHPUR
I-RJ-MKRN-ENB-9060 | I-RJ-MKRN-PMP-0053 | 1 | 1 | A6+B6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.1059 | 74.75 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-17 | 2025-12-19 | 2025-12-17 | 2025-12-19 | Premaram | [16 empty] | Makrana |  | Chiranji Lal | 6350491964 | Devilal Gurjar | 8078699370 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-NAWW-ENB-9066 | I-RJ-NAWW-PMP-0068 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.024 | 74.8841 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-20 | 2025-12-20 | 2025-12-20 | 2025-12-20 | Premaram | [16 empty] | Ulana |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-RNWR-ENB-9051 | I-RJ-RNWR-PMP-0034 | 2 | 1 | A6+B6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 24.7336 | 72.1118 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-18 | 2025-12-18 | 2025-12-18 | 2025-12-18 | Aneesh | [16 empty] | Gang |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JODHPUR
I-RJ-SNCE-ENB-9105 | I-RJ-SNCE-PMP-0071 | 1/2 | 2 | A6+B6 I&C | Jalor | Sirohi | Aneesh & Team |  | Done | 24.8516 | 71.6595 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-19 | 2025-12-19 | 2025-12-19 | 2025-12-19 | Aneesh | [16 empty] | Hindwara |  | DHANESH KUMAR | 9772728785 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JODHPUR
I-RJ-SNCE-ENB-9084 | I-RJ-SNCE-PMP-0015 | 1/3 | 2 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.7601 | 71.8859 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-20 | 2025-12-20 | 2025-12-20 | Aneesh & team | [13 empty] | 80 | 5 |  | DANATA |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-CWAN-ENB-9007 | I-RJ-CWAN-PMP-0002 | 1/3 | 2 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.8999 | 71.7621 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-20 | 2025-12-20 | 2025-12-20 | Aneesh & team | [13 empty] | 80 | 10 |  | Chitalwana |  | DHANESH KUMAR | 9772728785 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-9098 | I-RJ-SNCE-PMP-0018 | 3 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.0816 | 71.9034 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-22 | Aneesh & team | [13 empty] | 40 | 5 |  | Chitlwana |  | MAHBUB KHAN | 7045641935 | DAMA RAM | 6350491610 | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-JAAW-ENB-9037 | I-RJ-JAAW-PMP-0014 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.2038 | 72.0476 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-22 | Aneesh & team | [13 empty] | 40 | 40 |  | Dadal |  | SHARWAN KUMAR | 6378280042 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-RNWR-ENB-9027 | I-RJ-RNWR-PMP-0005 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.8831 | 72.2736 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-22 | Aneesh & team | [13 empty] | 40 | 5 |  | Chaara |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-DDWN-ENB-9058 | I-RJ-DDWN-PMP-0007 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.3312 | 74.7711 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-22 | Premaram | [13 empty] | 40 | 5 |  | Dabada |  | Ramdev Ram | 6350492177 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-9090 | I-RJ-DDWN-PMP-0010 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.413 | 74.598 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-21 | 2025-12-22 | 2025-12-22 | 2025-12-24 | Premaram | [13 empty] | 40 | 5 |  | Didwana |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-KSGR-ENB-9064 | I-RJ-KSGR-PMP-0040 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rahul Outsource |  | Done | 26.5157 | 74.9277 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-23 | Rahul Outsource | [13 empty] | 40 | 5 |  | Barna |  | MUNNA MOHAMMED | 7568796116 | KAMAL KUMAR CHOUDHARY | 9799973971 | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-JAAL-ENB-9078 | I-RJ-JAAL-PMP-0012 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Pawan & Team |  | Done | 27.0319 | 73.9368 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | Pawan & Team | [13 empty] | 40 | 5 |  | Jhunjhala |  | HANUMAN RAM | 7849824281 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-9082 | I-RJ-JAAL-PMP-0013 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.3069 | 73.9041 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-23 | 2025-12-23 | 2025-12-23 | 2025-12-23 | Vikram Jangid Nagaur team | [13 empty] | 40 | 5 |  | Jayal |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DENA-ENB-9098 | I-RJ-DENA-PMP-0022 | 2 | 1 | A6 I&C | Makrana | Nagaur | Pawan & Team |  | Done | 26.9738 | 74.1547 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Pawan & Team | [13 empty] | 40 | 5 |  | Dagri |  | RATNA RAM | 6350492259 | RAJESH KASWAN | 9509617574 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DENA-ENB-9009 | I-RJ-DENA-PMP-0008 | 2 | 1 | A6 I&C | Makrana | Nagaur | Pawan & Team |  | Done | 26.6058 | 74.4372 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Pawan & Team | [13 empty] | 40 | 40 |  | Nimbola |  | NATHU RAM | 9664263744 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NGUR-ENB-9081 | I-RJ-NGUR-PMP-0086 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9768 | 73.5267 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR80 | 2025-12-18 | 2025-12-19 | 2025-12-24 | 2025-12-24 | 2025-12-24 | 2025-12-24 | Vikram | [13 empty] | 40 | 5 |  | Khimsar |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-9055 | I-RJ-JAAL-PMP-0060 | 1/2 | 2 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1722 | 74.1324 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-16 | 2025-12-25 | 2025-12-25 | 2025-12-27 | Vikram | [16 empty] | Dharna |  | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JODHPUR
I-RJ-PASS-ENB-9039 | I-RJ-PASS-PMP-0028 | 1/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Pawan & Team |  | Done | 26.7754 | 74.4754 | GBT | 0 |  |  |  | Allotment- AIR79 | 2025-12-12 | 2025-12-13 | 2025-12-25 | 2025-12-25 | 2025-12-25 | 2025-12-26 | Pawan & Team | [16 empty] | Kheri Kheevsi |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JODHPUR
I-RJ-MKRN-ENB-9054 | I-RJ-MKRN-PMP-0055 | 1/3 | 2 | A6+B6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.1352 | 74.5122 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR81 | 2026-01-21 | 2026-01-22 | 2026-01-24 | 2026-01-24 | 2026-01-24 | 2026-01-24 | Prema Ram Outsource | [16 empty] | Makrana |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 |  |  | JLJH
I-RJ-SJRD-ENB-V001 | I-RJ-SJRD-PMP-0004 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Aneesh & team |  | Done | 25.8627 | 73.7496 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR81 | 2026-01-21 | 2026-01-22 | 2026-01-24 | 2026-01-24 | 2026-01-24 | 2026-01-24 | Aneesh & team | [16 empty] | Sojat Road |  | Om Prakash | 9672320287 | SAMER ALI | 7073800169 |  |  | JLJH
I-RJ-MKRN-ENB-9062 | I-RJ-MKRN-PMP-0059 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.1259 | 74.6067 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR81 | 2026-01-21 | 2026-01-22 | 2026-01-25 | 2026-01-31 | 2026-01-25 | 2026-01-31 | Premaram | [16 empty] | Nagwara Kalan |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 |  |  | JLJH
I-RJ-JLOR-ENB-9037 | I-RJ-JLOR-PMP-0016 | 3 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.3329 | 72.6724 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | NA | [13 empty] | 50 | 5 |  | DHARMARAM GHNCHI |  | PRABHAKAR SINGH | 6350491294 | AJAY RANA | 9636817067 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-BAGA-ENB-6000 | I-RJ-BAGA-PMP-0001 | 3 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.2019 | 72.5885 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | NA | [13 empty] | 50 | 5 |  | Bagra |  | ANKIT KUMAR DHANWAL | 9315079392 | GANPAT LAL | 8290147329 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-BNML-ENB-6004 | I-RJ-BNML-PMP-0003 | 1 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.8137 | 72.4561 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | PAWAN | [13 empty] | 50 | 5 |  | Jaswantpura_Bheenmal |  | KAILASH KUMAR | 8058302215 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-BORA-ENB-6003 | I-RJ-BORA-PMP-0004 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.9986 | 72.0546 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ANEESH | [13 empty] | 50 | 5 |  | PUNASA |  | JETMAL SINGH | 7014142932 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-NGUR-ENB-I014 | I-RJ-NGUR-PMP-0091 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 27.1917 | 73.8861 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | VIKRAM | [13 empty] | 50 | 5 |  | GAGWANA |  | BHARAT THALOR | 8078698860 | MAHENDRA DHUNDHWAL | 9057571856 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SNCE-ENB-9102 | I-RJ-SNCE-PMP-0019 | 3 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.6861 | 71.8485 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ANEESH | [13 empty] | 50 | 50 |  | SANCHORE |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-KDRD-ENB-6000 | I-RJ-KDRD-PMP-0001 | 2 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.8898 | 72.0926 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ANEESH | [13 empty] | 50 | 5 |  | Karda |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-9107 | I-RJ-SNCE-PMP-0020 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.7411 | 71.9559 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-30 | ANEESH | [13 empty] | 50 | 50 |  | Sankad |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-BNML-ENB-9034 | I-RJ-BNML-PMP-0008 | 2 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.0064 | 72.3045 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Pawan | [13 empty] | 50 | 5 |  | Kakani |  | GHAN SHYAM | 9351930732 | APEEL SINGH | 7568739839 | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-BORA-ENB-9028 | I-RJ-BORA-PMP-0021 | 1 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.0853 | 72.1724 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Pawan | [13 empty] | 50 | 50 |  | Bora |  | MAHBUB KHAN | 7045641935 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-MKRN-ENB-9035 | I-RJ-MKRN-PMP-0030 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.1246 | 74.631 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | Premaram | [13 empty] | 50 | 50 |  | Safer Bari |  | Prema Dahiya | 6350491992 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-9017 | I-RJ-DDWN-PMP-0062 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.1821 | 74.4049 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | Premaram | [13 empty] | 50 | 5 |  | Badbara |  | OMVEER SINGH | 9887268550 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DENA-ENB-6083 | I-RJ-DENA-PMP-0006 | 1 | 1 | A6 I&C | Makrana | Nagaur | Rahul Outsource |  | Done | 26.5611 | 74.4715 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Rahul Outsource | [13 empty] | 50 | 5 |  | THANWALA |  | NATHU RAM | 9664263744 | SALEEM MOHAMMAD DESHWALI | 7891896395 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-6074 | I-RJ-DENA-PMP-0001 | 3 | 1 | A6 I&C | Makrana | Nagaur | Rahul Outsource |  | Done | 26.5148 | 74.3135 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Rahul Outsource | [13 empty] | 50 | 5 |  | ALNIYAWAS |  | NATHU RAM | 9664263744 | SALEEM MOHAMMAD DESHWALI | 7891896395 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-JAAW-ENB-6004 | I-RJ-JAAW-PMP-0005 | 2/3 | 2 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.2226 | 72.0922 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Pawan | [13 empty] | 100 | 10 |  | TILORA |  | SHARWAN KUMAR | 6378280042 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-JAAW-ENB-6003 | I-RJ-JAAW-PMP-0004 | 3 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.2359 | 72.1349 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | Aneesh | [13 empty] | 50 | 5 |  | Surana |  | MAHBUB KHAN | 7045641935 | UPENDRA KUMAR | 9799877374 | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-KESR-ENB-V001 | I-RJ-KESR-PMP-0018 | 2 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.9727 | 73.4155 | GBT | 0 | A6 I&C , ATP11A & 11C |  | One CPRI Faulty/ extra MIN done | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-02-04 | 2026-02-04 | 2026-02-04 | 2026-02-04 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | Hendigrap Fectory |  | DHARMARAM JAJRA | 6376202299 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MRTA-ENB-6001 | I-RJ-MRTA-PMP-0001 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.5761 | 73.863 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | GAGRANA |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MRTA-ENB-9036 | I-RJ-MRTA-PMP-0053 | 3 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.5091 | 73.945 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | Badgaon |  | Rakesh Rakesh | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-PASS-ENB-9017 | I-RJ-PASS-PMP-0007 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 26.716 | 74.5997 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Premaram | [13 empty] | 50 | 5 |  | Bajwa |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PASS-ENB-9023 | I-RJ-PASS-PMP-0008 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 26.6954 | 74.6263 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Premaram | [13 empty] | 50 | 5 |  | Parbatsar |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-SNCE-ENB-9036 | I-RJ-SNCE-PMP-0013 | 1 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.7678 | 71.7102 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Aneesh | [13 empty] | 50 | 5 |  | Dabhal |  | CHANDAN MAL | 9783284500 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-9008 | I-RJ-SNCE-PMP-0005 | 2/3 | 2 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.832 | 71.7748 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | Aneesh | [13 empty] | 100 | 100 |  | Dhamana Ka Goliya |  | DHANESH KUMAR | 9772728785 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-9076 | I-RJ-SNCE-PMP-0014 | 3 | 1 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 24.8016 | 71.4866 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-02-01 | 2026-02-02 | 2026-02-02 | 2026-02-02 | Aneesh | [13 empty] | 50 | 50 |  | Chitanwada |  | JETMAL SINGH | 7014142932 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-9092 | I-RJ-SNCE-PMP-0017 | 1/2/3 | 3 | A6 I&C | Jalor | Sirohi | Aneesh & team |  | Done | 25.0629 | 71.8747 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR82 | 2026-01-28 | 2026-01-29 | 2026-02-01 | 2026-02-02 | 2026-02-02 | 2026-02-02 | Aneesh | [13 empty] | 150 | 60 |  | SANCHOR |  | DHANESH KUMAR | 9772728785 | DAMA RAM | 6350491610 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-BORA-ENB-6002 | I-RJ-BORA-PMP-0003 | 2 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.1511 | 72.0212 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | PAWAN | [13 empty] | 60 | 5 |  | DHUMBARIYA |  | SHARWAN KUMAR | 6378280042 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-LDNU-ENB-I015 | I-RJ-LDNU-PMP-0029 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.6414 | 74.6837 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | Premaram | [13 empty] | 60 | 5 |  | Kushalpura |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAW-ENB-I003 | I-RJ-JAAW-PMP-0017 | 3 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.3492 | 72.3976 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | PAWAN | [13 empty] | 60 | 5 |  | OTWALA |  | DUNGARA RAM | 7849824302 | UPENDRA KUMAR | 9799877374 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-JLOR-ENB-H001 | I-RJ-JLOR-PMP-0030 | 3 | 1 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.414 | 72.5628 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | PAWAN | [13 empty] | 60 | 5 |  | Teekhi |  | PRABHAKAR SINGH | 6350491294 | GANPAT LAL | 8290147329 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-DENA-ENB-9014 | I-RJ-DENA-PMP-0010 | 3 | 1 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.8621 | 74.039 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-08 | 2026-02-08 | 2026-02-08 | 2026-02-08 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | Chackdhani |  | IMARAN KHAN | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-MAJN-ENB-9013 | I-RJ-MAJN-PMP-0006 | 1 | 1 | A6 I&C | Pali | Sirohi | Pawan & Team |  | Done | 25.6198 | 73.5356 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-08 | 2026-02-08 | 2026-02-08 | 2026-02-08 | Pawan & Team | [13 empty] | 60 | 60 |  | Dhamli |  | NARENDRA KUMAR GURJAR | 6376917827 | BHAWANI SINGH | 9799650934 | VACANT | VACANT | JLJH
I-RJ-AHOR-ENB-9009 | I-RJ-AHOR-PMP-0003 | 1/2 | 2 | A6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.32 | 72.9241 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-08 | 2026-02-08 | 2026-02-08 | 2026-02-08 | Pawan & Team | [13 empty] | 100 | 10 |  | Vedna |  | SANJAY KUMAR MEENA | 9024489656 | Shankar Lal | 6350491316 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-PNDW-ENB-9020 | I-RJ-PNDW-PMP-0009 | 1 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.6222 | 72.9093 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Pawan | [13 empty] | 60 | 60 |  | Chavarli |  | MAHENDRA KUMAR | 9694971304 | DEVENDRA KUMAR | 7611913941 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-PASS-ENB-9029 | I-RJ-PASS-PMP-0009 | 2 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 26.8773 | 74.7729 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Premaram | [13 empty] | 60 | 5 |  | parbatsar |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PNDW-ENB-9021 | I-RJ-PNDW-PMP-0040 | 3 | 1 | A6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.6849 | 72.9523 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Pawan& | [13 empty] | 60 | 5 |  | Panchayat Samity land,Goliya |  | MAHENDRA KUMAR | 9694971304 | DEVENDRA KUMAR | 7611913941 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-DENA-ENB-9008 | I-RJ-DENA-PMP-0007 | 3 | 1 | A6 I&C | Makrana | Nagaur | Rahul Outsource |  | Done | 26.544 | 74.5087 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | NA | [13 empty] | 50 | 5 |  | Badi Ghati |  | NATHU RAM | 9664263744 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I001 | I-RJ-NAWW-PMP-0032 | 1 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.0117 | 74.8031 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | 2026-02-10 | 2026-02-10 | 2026-02-10 | 2026-02-10 | Premaram | [13 empty] | 60 | 5 |  | Maglana |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-LDNU-ENB-I005 | I-RJ-LDNU-PMP-0050 | 3 | 1 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.5461 | 74.4942 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | Premaram | [13 empty] | NA | NA |  | CHHAPARA |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-ANGR-ENB-I001 | I-RJ-ANGR-PMP-0030 | 1 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 28.9627 | 72.9878 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-10 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | Tarachand | [13 empty] | 60 | 5 |  | 3GM(JANTAWALI) |  | CHET RAM | 6350492121 | Vinod Kumar | 6350492215 | RAJA RAM | 8003992944 | JLKD
I-RJ-MKRN-ENB-G001 | I-RJ-MKRN-PMP-0072 | 2 | 1 | A6 I&C | Makrana | Nagaur | Prema Ram Outsource |  | Done | 27.107 | 74.5029 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-02-17 | 2026-02-17 | 2026-02-17 | 2026-02-17 | Premaram | [13 empty] | 60 | 5 |  | Indokha |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SNCE-ENB-6003 | I-RJ-SNCE-PMP-0074 | 2 | 1 | A6+B6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.8 | 71.889 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-18 | 2026-02-18 | Pawan | [13 empty] | NA | NA |  | PUR |  | CHANDAN MAL | 9783284500 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RNWR-ENB-I005 | I-RJ-RNWR-PMP-0032 | 1/2 | 2 | A6+B6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.8926 | 72.0347 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Pawan | [13 empty] | NA | NA |  | DIGAON |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RAPR-ENB-9036 | I-RJ-RAPR-PMP-0032 | 2/3 | 2 | A6+B6 I&C | Pali | Sirohi | Hanuman & Team |  | Done | 25.9819 | 73.9915 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | 2026-02-18 | Hanuman | [13 empty] | NA | NA |  | Raipur |  | BARKAT MOHMMAD | 6350491310 | PINKU SINGH | 9660860336 | VACANT | VACANT | JLJH
I-RJ-MAJN-ENB-9047 | I-RJ-MAJN-PMP-0045 | 2 | 1 | A6+B6 I&C | Pali | Sirohi | Hanuman & Team |  | Done | 25.7567 | 73.8305 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 |  | 2026-02-19 | 2026-02-19 | 2026-02-19 | 2026-02-19 | Hanuman | [13 empty] | NA | NA |  | Marwar |  | Om Prakash | 9672320287 | BHAWANI SINGH | 9799650934 | VACANT | VACANT | JLJH
I-RJ-NAWW-ENB-I003 | I-RJ-NAWW-PMP-0056 | 1/3 | 2 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.119 | 74.9783 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-02-16 | 2026-02-16 | 2026-02-18 | 2026-02-18 | Satveer | [13 empty] | 120 | 10 |  | Gogor |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PALI-ENB-9032 | I-RJ-PALI-PMP-0101 | 1 | 1 | A6+B6 I&C | Pali | Sirohi | Hanuman & Team |  | Done | 25.866 | 73.3066 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | Hanuman | [13 empty] | NA | NA |  | Bhagariya |  | KUNDAN LAL | 8005566207 | RAVINDRA KUMAR | 9529143828 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-REAR-ENB-9017 | I-RJ-REAR-PMP-0038 | 2/3 | 2 | A6+B6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.7295 | 72.399 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 2026-02-20 | 2026-02-20 | Pawan & Team | [13 empty] | NA | NA |  | Nandgaon Goshala |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-NAWW-ENB-I020 | I-RJ-NAWW-PMP-0065 | 2 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.1993 | 74.7925 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-20 | Satveer | [13 empty] | 60 | 5 |  | RASAL |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-LDNU-ENB-I020 | I-RJ-LDNU-PMP-0054 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.6402 | 74.3865 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-02-19 | 2026-02-19 | 2026-02-20 | 2026-02-20 | Premaram | [13 empty] | NA | NA |  | BhatiaColonyJawabas |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SMRP-ENB-V001 | I-RJ-SMRP-PMP-0030 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi |  |  | MRN Done | 25.1567 | 73.0809 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR77 | 2025-11-20 | 2025-11-21 | [21 empty] | Sumerpur Main market |  | Babulal meena | 6350491325 | ARJUN LAL | 8955001722 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-JAAL-ENB-I003 | I-RJ-JAAL-PMP-0056 | 3 | 1 | A6+B6 I&C | Ladnu | Nagaur |  |  | MRN Done-SFP Pending | 27.2857 | 74.2542 | GBT | 0 |  |  |  | Allotment- AIR78 | 2025-12-03 | 2025-12-03 | [21 empty] | NOKHA JODHA |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543
I-RJ-JAAL-ENB-9080 | I-RJ-JAAL-PMP-0029 | 2/3 | 2 | A6+B6 I&C | Ladnu | Nagaur |  |  | MRN Done | 27.279 | 74.2848 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR74 | 2025-11-11 | 2025-11-11 | [23 empty] | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-UNRA-ENB-I003 | I-RJ-UNRA-PMP-0030 | 1 | 1 | A6 I&C | Tonk | Ajmer |  |  | MRN Done | 25.9671 | 75.8192 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | [18 empty] | 60 | 5 |  | BINJARI |  | Anil Kumar Chouhan | 6350491771 | Hansraj Gurjar | 6376917825 | VACANT | VACANT | JAIPUR
I-RJ-SNCE-ENB-9130 | I-RJ-SNCE-PMP-0023 | 1/2/3 | 3 | A6 I&C | Jalor | Sirohi |  |  | MRN Done | 24.694 | 71.8885 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-31 | [18 empty] | 120 | 45 |  | Sanchor |  | BHAJAN LAL | 6350491314 | ASU RAM | 8769527529 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-ANGR-ENB-9024 | I-RJ-ANGR-PMP-0004 | 2 | 1 | A6 I&C | Suratgarh | Ganganagar |  |  | MRN Approved | 29.0149 | 73.0731 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | [18 empty] | 30 | 5 |  | 03 STR; Gharsana |  | CHET RAM | 6350492121 | Vinod Kumar | 6350492215 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-SRGR-ENB-I001 | I-RJ-SRGR-PMP-0061 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar |  |  | MRN Done-SFP Pending | 29.1988 | 73.9003 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR72 | 2025-10-30 | 2025-10-01 | [18 empty] | 50 | 50 |  | Bridhwali infill |  | KAILASH TAAK | 7878779144 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JLKD
I-RJ-SRGR-ENB-9012 | I-RJ-SRGR-PMP-0029 | 1/2 | 2 | A6 I&C | Suratgarh | Ganganagar |  |  | MRN Approved | 29.2329 | 73.9086 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR71 | 2025-10-28 | 2025-10-28 | [18 empty] | 100 | 55 |  | Rajpura Piparan |  | DINESH KUMAR | 9549866266 | VIKAS KUMAR | 8094471600 | RAJA RAM | 8003992944 | JAIPUR
I-RJ-BEWR-ENB-I008 | I-RJ-BEWR-PMP-0076 | 1/2/3 | 3 | A6 I&C | Beawar | Ajmer | Rahul Outsource |  | Done | 26.1015 | 74.3075 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR83 | 2026-02-05 | 2026-02-06 | 2026-02-08 | 2026-03-02 | 2026-02-08 | 2026-03-02 | Rahul Outsource | [13 empty] | 120 | 50 |  | Sundar Nagar |  | VACANT | VACANT | Keshar Singh Chouhan | 6376917831 | MUKESH PRAJAPAT | 9001117533 | JLKD
I-RJ-JAAL-ENB-I015 | I-RJ-JAAL-PMP-0048 | 1 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.3738 | 74.0807 | GBT | 0 | A6 I&C , ATP11A & 11C |  | CPRI WAS SHORT/ REPLACED | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Premaram | [13 empty] | 60 | 5 |  | TANWARA |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JPUR-ENB-1409 | I-RJ-JPUR-GSC-N101 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8693 | 75.7615 | GBM-Hybrid | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR84 | 2026-02-06 | 2026-02-07 | 2026-02-09 | 2026-02-11 | 2026-02-09 | 2026-02-25 | Aneesh & team | [16 empty] | Near Manglam Jaipur Electronic Mall |  | BABU LAL MEENA | 8560873090 | RAGHUVEER PRASAD SAINI | 7877400576 | BUDHRAJ SINGH RAJAWAT | 9549688936 | JLKD
I-RJ-JPUR-ENB-1228 | I-RJ-JPUR-GSC-N083 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8185 | 75.8457 | GBM | 0 | MM WAVE I&C ,11A & 11C |  | 2 times extra visit for testing by aneesh | Allotment- AIR84 | 2026-02-06 | 2026-02-07 | 2026-02-10 | 2026-02-17 | 2026-02-10 | 2026-03-01 | Aneesh & team | [16 empty] | Prata Nagar, Sanganer |  | JITENDRA SAINI | 9785521595 | SITARAM NAGAR | 8239394576 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1122 | I-RJ-JPUR-GSC-N078 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8038 | 75.8247 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR84 | 2026-02-06 | 2026-02-07 | 2026-02-12 | 2026-02-16 | 2026-02-12 | 2026-02-26 | Aneesh & team | [16 empty] | Kumbha Marg T-Point Circle |  | JITENDRA SAINI | 9785521595 | SANTOSHA SHARMA | 6377200933 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-0902 | I-RJ-JPUR-GSC-N072 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8172 | 75.8091 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR84 | 2026-02-06 | 2026-02-07 | 2026-02-11 | 2026-02-16 | 2026-02-13 | 2026-02-27 | Aneesh & team | [16 empty] | Tirupati Balaji Nagar |  | PRATAP DESHWA | 8078699740 | SITARAM NAGAR | 8239394576 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-0887 | I-RJ-JPUR-GSC-N071 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9869 | 75.7839 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR84 | 2026-02-06 | 2026-02-07 | 2026-02-11 | 2026-02-20 | 2026-02-11 | 2026-02-25 | Aneesh & team | [16 empty] | VKI Ind Area |  | VINOD KUMAR | 6350492144 | SURY PRATAP SINGH | 8740028204 | NAVEEN SHARMA | 9314160167 | JLKD
I-RJ-JPUR-ENB-1709 | I-RJ-JPUR-GSC-N119 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9902 | 75.78 | GBM-Hybrid | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR86 | 2026-02-11 | 2026-02-11 | 2026-02-12 | 2026-02-17 | 2026-02-12 | 2026-02-26 | Aneesh & team | [16 empty] | Amber / Jaipur (M Corp.) (Part) |  | VINOD KUMAR | 6350492144 | PPRJ00139215 | 8740028204 | NAVEEN SHARMA | 9314160167 | JLKD
I-RJ-JPUR-ENB-1029 | I-RJ-JPUR-GSC-N074 | 2 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9851 | 75.7685 | GBM-Hybrid | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR86 | 2026-02-11 | 2026-02-11 | 2026-02-13 | 2026-02-16 | 2026-02-13 | 2026-03-01 | Aneesh & team | [16 empty] | Jaipur (M Corp.) |  | JITENDRA SHARMA | 9251636332 | PPRJ00139215 | 8740028204 | NAVEEN SHARMA | 9314160167 | JLKD
I-RJ-JPUR-ENB-1730 | I-RJ-JPUR-GSC-N122 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & Team |  | Done | 26.8044 | 75.8187 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-24 | 2026-02-16 | 2026-02-27 | Aneesh & team | [18 empty] | PRATAP DESHWA | 8078699740 | SITARAM NAGAR | 8239394576 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1360 | I-RJ-JPUR-GSC-N096 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Hanuman & Team |  | Done | 26.8081 | 75.8287 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-24 | 2026-02-16 | 2026-02-27 | Aneesh & team | [18 empty] | PRATAP DESHWA | 8078699740 | SITARAM NAGAR | 8239394576 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1468 | I-RJ-JPUR-GSC-N108 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Hanuman & Team |  | Done | 26.808 | 75.8384 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-18 | 2026-02-16 | 2026-02-26 | Aneesh & team | [18 empty] | JITENDRA SAINI | 9785521595 | SITARAM NAGAR | 8239394576 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-0876 | I-RJ-JPUR-GSC-N069 | 2 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & Team |  | Done | 26.8241 | 75.8474 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-14 | 2026-02-18 | 2026-02-16 | 2026-02-26 | Aneesh & team | [18 empty] | GHAMANDI LAL SAINI | 6350492235 | RAHUL KUMAR SAINI | 9057531972 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1040 | I-RJ-JPUR-GSC-N075 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Hanuman & Team |  | Done | 26.9156 | 75.7339 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-20 | 2026-02-18 | 2026-02-25 | Aneesh & team | [18 empty] | JUGAL KISHOR KUSHVAHA | 7849824270 | ROSHAN KUSHVAHA | 9799752500 | Kamlesh Sharma | 8078699590 | JLKD
I-RJ-JPUR-ENB-1080 | I-RJ-JPUR-GSC-N077 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & Team |  | Done | 26.7753 | 75.842 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-15 | 2026-02-25 | 2026-02-24 | 2026-02-26 | Aneesh & team | [18 empty] | DINESH KUMAR SHARMA | 6350491327 | SURENDRA KUMAR PRAJAPAT | 8949711579 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1428 | I-RJ-JPUR-GSC-N102 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & Team |  | Done | 26.7741 | 75.8519 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-15 | 2026-02-20 | 2026-02-16 | 2026-02-26 | Aneesh & team | [18 empty] | DINESH KUMAR SHARMA | 6350491327 | SURENDRA KUMAR PRAJAPAT | 8949711579 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1079 | I-RJ-JPUR-GSC-N076 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & Team |  | Done | 26.7808 | 75.8534 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-15 | 2026-02-20 | 2026-02-17 | 2026-02-26 | Aneesh & team | [18 empty] | DINESH KUMAR SHARMA | 6350491327 | SURENDRA KUMAR PRAJAPAT | 8949711579 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1151 | I-RJ-JPUR-GSC-N081 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & Team |  | Done | 26.7866 | 75.8385 | GBM | 0 | MM WAVE I&C ,11A & 11C |  | 2 times extra visit for testing by aneesh | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-20 | 2026-02-17 | 2026-03-02 | Aneesh & team | [18 empty] | VIKRAM SINGH | 6350492172 | SURENDRA KUMAR PRAJAPAT | 8949711579 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1382 | I-RJ-JPUR-GSC-N099 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & Team |  | Done | 26.7889 | 75.8444 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-20 | 2026-02-17 | 2026-02-26 | Aneesh & team | [18 empty] | VIKRAM SINGH | 6350492172 | SURENDRA KUMAR PRAJAPAT | 8949711579 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1320 | I-RJ-JPUR-GSC-N090 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Hanuman & Team |  | Done | 26.9426 | 75.7371 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-16 | 2026-02-26 | 2026-02-26 | 2026-02-27 | Aneesh & team | [18 empty] | Rajesh Saini | 8078699720 | NARAYAN SAINI | 6375358456 | Kamlesh Sharma | 8078699590 | JLKD
I-RJ-JPUR-ENB-1253 | I-RJ-JPUR-GSC-N087 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8419 | 75.812 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-17 | 2026-02-23 | 2026-02-18 | 2026-02-26 | Aneesh & team | [18 empty] | ashish sharma | 8078699532 | RAHUL PRAJAPAT | 8000170788 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JPUR-ENB-1350 | I-RJ-JPUR-GSC-N095 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8623 | 75.7652 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-17 | 2026-02-21 | 2026-02-18 | 2026-02-25 | Aneesh & team | [18 empty] | LUXMAN SINGH | 7568299590 | RAGHUVEER PRASAD SAINI | 7877400576 | BUDHRAJ SINGH RAJAWAT | 9549688936 | JLKD
I-RJ-JPUR-ENB-1019 | I-RJ-JPUR-GSC-N073 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8613 | 75.7716 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-17 | 2026-02-21 | 2026-02-19 | 2026-02-25 | Aneesh & team | [18 empty] | LUXMAN SINGH | 7568299590 | RAGHUVEER PRASAD SAINI | 7877400576 | BUDHRAJ SINGH RAJAWAT | 9549688936 | JLKD
I-RJ-JPUR-ENB-1524 | I-RJ-JPUR-GSC-N109 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9087 | 75.8472 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-19 | 2026-02-21 | 2026-02-20 | 2026-02-27 | Aneesh & team | [18 empty] | ASGAR KHAN | 8078699694 | KAMAL KUMAR KEWAT | 9680258384 | VACANT | VACANT | JLKD
I-RJ-JPUR-ENB-0881 | I-RJ-JPUR-GSC-N070 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8833 | 75.8187 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-19 | 2026-02-21 | 2026-02-20 | 2026-02-25 | Aneesh & team | [18 empty] | Anurag Sharma | 8078699520 | SHYAMU SAINI | 8955937634 | VACANT | VACANT | JLKD
I-RJ-JPUR-ENB-0114 | I-RJ-JPUR-GSC-N060 | 0 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9711 | 75.7732 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-20 | 2026-02-22 | 2026-02-21 | 2026-02-25 | Aneesh & team | [18 empty] | VINOD KUMAR | 6350492144 | SURY PRATAP SINGH | 8740028204 | NAVEEN SHARMA | 9314160167 | JLKD
I-RJ-JPUR-ENB-0467 | I-RJ-JPUR-GSC-N065 | 1 | 1 | MM WAVE | Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8168 | 75.8139 | GBM | 0 | MM WAVE I&C ,11A & 11C |  |  | Allotment- AIR87 | 2026-02-13 | 2026-02-13 | 2026-02-22 | 2026-02-24 | 2026-02-22 | 2026-02-27 | Aneesh & team | [18 empty] | PRATAP DESHWA | 8078699740 | SITARAM NAGAR | 8239394576 | RAJANIKANT SHARMA | 8058061656 | JLKD
I-RJ-JAAW-ENB-9036 | I-RJ-JAAW-PMP-0025 | 2 | 1 | A6+B6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 25.1967 | 72.1334 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR90 | 2026-02-20 | 2026-02-20 | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-21 | Pawan & Team | [16 empty] | pundrao |  | SHARWAN KUMAR | 6378280042 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-BALI-ENB-I004 | I-RJ-BALI-PMP-0026 | 2 | 1 | A6 I&C | Pali | Sirohi | Pawan & Team |  | Done | 24.8881 | 73.1328 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | Pawan | [13 empty] | 60 | 5 |  | Kagdara |  | BHARAT SINGH | 7725999422 | Rajendra Kumar | 9413139121 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-AHOR-ENB-9046 | I-RJ-AHOR-PMP-0038 | 3 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 25.5739 | 72.9885 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-22 | 2026-02-22 | 2026-02-22 | 2026-02-22 | Hanuman & Team | [13 empty] | 50 | 5 |  | SAWARAM |  | VACANT | VACANT | Shankar Lal | 6350491316 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-AHOR-ENB-9064 | I-RJ-AHOR-PMP-0013 | 2 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 25.4699 | 72.8236 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-22 | 2026-02-22 | 2026-02-22 | 2026-02-22 | Hanuman & Team | [13 empty] | 50 | 50 |  | Ahore |  | SANJAY KUMAR MEENA | 9024489656 | Shankar Lal | 6350491316 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-AHOR-ENB-I015 | I-RJ-AHOR-PMP-0022 | 1 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 25.4262 | 72.9407 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-22 | 2026-02-22 | 2026-02-22 | 2026-02-22 | Hanuman & Team | [13 empty] | 60 | 60 |  | CHANDRAI |  | VACANT | VACANT | Shankar Lal | 6350491316 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-JAAW-ENB-9024 | I-RJ-JAAW-PMP-0010 | 1 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 25.3305 | 72.3237 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Hanuman & Team | [12 empty] | 50 | 50 |  | Sayla |  | DUNGARA RAM | 7849824302 | UPENDRA KUMAR | 9799877374 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-JLOR-ENB-9019 | I-RJ-JLOR-PMP-0013 | 1 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 25.2115 | 72.4907 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Hanuman & Team | [12 empty] | 50 | 50 |  | Bakra Road |  | ANKIT KUMAR DHANWAL | 9315079392 | UPENDRA KUMAR | 9799877374 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-BHAS-ENB-I002 | I-RJ-BHAS-PMP-0001 | 3 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 25.0246 | 72.4797 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Hanuman & Team | [12 empty] | 60 | 5 |  | Malpura-Bhinmal |  | VINOD KUMAR | 8094636604 | VACANT | VACANT | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-NAWW-ENB-V001 | I-RJ-NAWW-PMP-0047 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.0379 | 75.0654 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Satveer Outsource | [13 empty] | 60 | 5 |  | Rajjas-Nagaur |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-I019 | I-RJ-NAWW-PMP-0044 | 1 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.0342 | 74.9398 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | Satveer Outsource | [13 empty] | 60 | 5 |  | Khairdya |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-DENA-ENB-9085 | I-RJ-DENA-PMP-0018 | 3 | 1 | A6 I&C | Makrana | Nagaur | Vikram Jangid Nagaur team |  | Done | 26.8809 | 74.2486 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Vikram Jangid Nagaur team | [13 empty] | 50 | 5 |  | Jalsu |  | SHARWAN RAM CHOUDHARY | 6350492178 | RAJESH KASWAN | 9509617574 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-RNWR-ENB-9030 | I-RJ-RNWR-PMP-0006 | 1 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 24.7611 | 72.1159 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Hanuman | [13 empty] | 50 | 50 |  | RANIWARA |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-RNWR-ENB-9018 | I-RJ-RNWR-PMP-0002 | 1/2 | 2 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 24.7359 | 72.2611 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Hanuman | [13 empty] | 100 | 55 |  | Dungari bhakto ka baas |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SRHI-ENB-9006 | I-RJ-SRHI-PMP-0053 | 3 | 1 | A6+B6 I&C | Sirohi | Sirohi | Pawan & Team |  | Done | 24.8742 | 72.9123 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-24 | Pawan | [13 empty] | NA | NA |  | V/p Balda |  | BHAVESH KUMAR | 9672487892 | VIMLESH KUMAR TIWARI | 9399419761 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-DDWN-ENB-I005 | I-RJ-DDWN-PMP-0058 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.4036 | 74.4455 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR90 | 2026-02-20 | 2026-02-20 | 2026-02-23 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Premaram | [16 empty] | Palot |  | BALDEWA RAM | 8058503498 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-9014 | I-RJ-DDWN-PMP-0006 | 3 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.4488 | 74.523 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Premaram | [13 empty] | 50 | 50 |  | Ajawa |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PASS-ENB-9047 | I-RJ-PASS-PMP-0014 | 2/3 | 2 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.993 | 74.771 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | SATVIR | [13 empty] | 100 | 55 |  | parbatsar |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PASS-ENB-6002 | I-RJ-PASS-PMP-0004 | 2 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.9657 | 74.6964 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | SATVIR | [13 empty] | 60 | 5 |  | BIDIYAD |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-PASS-ENB-V001 | I-RJ-PASS-PMP-0022 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.9202 | 74.7119 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | SATVIR | [13 empty] | 60 | 60 |  | Kinsreya-Nagaur |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NWAI-ENB-I007 | I-RJ-NWAI-PMP-0043 | 1 | 1 | A6 I&C | Tonk | Ajmer | Rahul Outsource |  | Done | 26.5067 | 75.795 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR83 | 2026-02-05 | 2026-02-06 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | Rahul Outsource | [13 empty] | 60 | 5 |  | RAHOLI |  | TRILOK RAJVANSHI | 9929100048 | JAL SINGH KOLI | 9680431625 | VACANT | VACANT | JLKD
I-RJ-NAWW-ENB-9045 | I-RJ-NAWW-PMP-0002 | 2 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 27.0984 | 74.849 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-25 | SATVIR | [13 empty] | 50 | 5 |  | Kuchaman city, |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-RNWR-ENB-9038 | I-RJ-RNWR-PMP-0009 | 3 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 24.6278 | 72.3133 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-24 | 2026-02-24 | 2026-02-24 | HANUMAN | [13 empty] | 50 | 50 |  | Ramiwara |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-BNML-ENB-9038 | I-RJ-BNML-PMP-0009 | 2 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 25.041 | 72.1015 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | HANUMAN | [13 empty] | 50 | 50 |  | Goliya |  | GHAN SHYAM | 9351930732 | APEEL SINGH | 7568739839 | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-SNCE-ENB-I002 | I-RJ-SNCE-PMP-0030 | 1 | 1 | A6 I&C | Jalor | Sirohi | Hanuman & Team |  | Done | 24.9228 | 71.6128 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | HANUMAN | [13 empty] | 60 | 60 |  | VEERAWA/Rampura |  | RAM GOPAL | 9571316104 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-PASS-ENB-9032 | I-RJ-PASS-PMP-0011 | 3 | 1 | A6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.7866 | 74.5633 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-25 | 2026-02-25 | 2026-02-25 | 2026-02-25 | SATVIR | [13 empty] | 50 | 50 |  | Parbatsar |  | Jamal Deen | 6350491953 | Arjun Rao | 8209549364 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-BHAS-ENB-H001 | I-RJ-BHAS-PMP-0002 | 1/2/3 | 3 | A6+B6 I&C | Jalor | Sirohi | Pawan & Team |  | Done | 24.8042 | 72.4626 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR90 | 2026-02-20 | 2026-02-20 | 2026-02-22 | 2026-02-23 | 2026-02-23 | 2026-02-25 | Hanuman | [16 empty] | Jaswant Pura |  | KAILASH KUMAR | 8058302215 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-JAAL-ENB-9066 | I-RJ-JAAL-PMP-0046 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.1156 | 74.3322 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR90 | 2026-02-20 | 2026-02-20 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | Premaram | [16 empty] | Badi Khatu |  | RATNA RAM | 6350492259 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-UNRA-ENB-I003 | I-RJ-UNRA-PMP-0030 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.9671 | 75.8192 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR83 | 2026-02-05 | 2026-02-06 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | Hanuman | [13 empty] | 60 | 5 |  | BINJARI |  | Anil Kumar Chouhan | 6350491771 | Hansraj Gurjar | 6376917825 | VACANT | VACANT | JLKD
I-RJ-UNRA-ENB-9008 | I-RJ-UNRA-PMP-0007 | 1 | 1 | A6 I&C | Tonk | Ajmer | Hanuman & Team |  | Done | 25.9602 | 76.1629 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-23 | 2026-02-26 | 2026-02-26 | 2026-02-26 | 2026-02-26 | Hanuman | [13 empty] | 50 | 5 |  | Choru |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-JAAL-ENB-9012 | I-RJ-JAAL-PMP-0007 | 2 | 1 | A6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.4581 | 74.0662 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | 2026-02-24 | 2026-02-27 | 2026-02-24 | 2026-03-02 | Premaram | [13 empty] | 60 | 60 |  | Surpaliya |  | BHAGIRATH PAREEK | 6350492228 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-I022 | I-RJ-DDWN-PMP-0066 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource |  | Done | 27.2062 | 74.4558 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR90 | 2026-02-20 | 2026-02-20 | 2026-02-25 | 2026-02-26 | 2026-02-26 | 2026-03-02 | Premaram | [16 empty] | BC Peedwa A infill |  | OMVEER SINGH | 9887268550 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-PLBG-ENB-9042 | I-RJ-PLBG-PMP-0011 | 3 | 1 | A6 I&C | Hanumangarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.575 | 73.8055 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-23 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-03-02 | Tarachand | [13 empty] | 50 | 50 |  | 63 LNP |  | RAKESH KUMAR | 7849824288 | VAKIL KUMAR | 8078698892 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-PDMP-ENB-V001 | I-RJ-PDMP-PMP-0020 | 3 | 1 | A6 I&C | Ganganagar | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.6151 | 73.8573 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-23 | 2026-02-28 | 2026-03-02 | 2026-02-28 | 2026-03-02 | Tarachand | [13 empty] | 50 | 50 |  | Jorkiyan |  | RAKESH KUMAR | 7849824288 | Sandeep Kumar | 6350491320 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-SRGR-ENB-9104 | I-RJ-SRGR-PMP-0084 | 3 | 1 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team |  | Done | 29.4599 | 73.8344 | GBT | 0 | A6 +B6 I&C , ATP11A & 11C |  |  | Allotment- AIR88 | 2026-02-13 | 2026-02-13 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | Tarachand | [16 empty] | Sidhuwala |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 | JLKD
I-RJ-PASS-ENB-I005 | I-RJ-PASS-PMP-0038 | 2 | 1 | A6+B6 I&C | Makrana | Nagaur | Satveer Outsource |  | Done | 26.7877 | 74.6255 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | Satveer Outsource | [13 empty] | NA | NA |  | Rabdiyad |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NSRB-ENB-I001 | I-RJ-NSRB-PMP-0014 | 3 | 1 | A6 I&C | Kishangarh | Ajmer | Rahul Outsource | 2026-03-14 | 1 | 26.3199 | 74.7429 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [18 empty] | 50 | 5 |  | TRANSPORT NAGAR,NASIRABAD |  | OMBIR SINGH | 6375459581 | MOHAMMAD IMRAN | 7240101103 | VACANT | VACANT | JLKD
I-RJ-PISN-ENB-H003 | I-RJ-PISN-PMP-0013 | 1 | 1 | A6 I&C | Beawar | Ajmer | Rahul Outsource | 2026-03-14 | 2 | 26.4205 | 74.4719 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [18 empty] | 50 | 5 |  | Picholiya |  | Raj Kumar | 6350491825 | VACANT | VACANT | MAHESH KUMAR | 6376917834 | JLKD
I-RJ-BSBM-ENB-I003 | I-RJ-BSBM-PMP-0003 | 1/2/3 | 3 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team | 2026-03-14 | 1 | 27.1751 | 73.6434 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [21 empty] | Belim Mohalla |  | MAHENDRA JAT | 8290502749 | BALU RAM | 8355811699 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-NGUR-ENB-9084 | I-RJ-NGUR-PMP-0112 | 2/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team | 2026-03-15 | 2 | 27.32 | 73.8415 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Manjhwas |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-NGUR-ENB-9087 | I-RJ-NGUR-PMP-0092 | 2/3 | 2 | A6+B6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team | 2026-03-16 | 3 | 27.1097 | 73.6091 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Barangaon |  | MAHENDRA JAT | 8290502749 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-BKRD-ENB-6000 | I-RJ-BKRD-PMP-0001 | 1 | 1 | A6 I&C | Nagaur | Nagaur | Vikram Jangid Nagaur team | 2026-03-17 | 4 | 27.0484 | 73.5843 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [18 empty] | 60 | 5 |  | BHAKROD |  | DHARMARAM JAJRA | 6376202299 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JAAL-ENB-9058 | I-RJ-JAAL-PMP-0061 | 2 | 1 | A6+B6 I&C | Ladnu | Nagaur | Vikram Jangid Nagaur team | 2026-03-18 | 5 | 27.4794 | 73.8814 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | jayal |  | BHARAT THALOR | 8078698860 | KAILASH BHAKAR | 8875805543 | OM PRAKASH | 6350491377 | JLJH
I-RJ-LDNU-ENB-9019 | I-RJ-LDNU-PMP-0038 | 1/2/3 | 3 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource | 2026-03-15 | 1 | 27.6423 | 74.5056 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [21 empty] | Kasumbi Alipur |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-9053 | I-RJ-JAAL-PMP-0033 | 2/3 | 2 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource | 2026-03-16 | 2 | 27.2509 | 74.0522 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Mandgio |  | BHARAT THALOR | 8078698860 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-JAAL-ENB-9074 | I-RJ-JAAL-PMP-0030 | 3 | 1 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource | 2026-03-16 | 3 | 27.3006 | 74.1242 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Dhatiyad |  | BHAGIRATH PAREEK | 6350492228 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 | JLJH
I-RJ-DDWN-ENB-9083 | I-RJ-DDWN-PMP-0043 | 1/2 | 2 | A6+B6 I&C | Ladnu | Nagaur | Prema Ram Outsource | 2026-03-17 | 4 | 27.3052 | 74.4867 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Khunkhuna |  | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 | JLJH
I-RJ-RSNG-ENB-V002 | I-RJ-RSNG-PMP-0051 | 1/2/3 | 3 | A6+B6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team | 2026-03-14 | 1 | 29.5279 | 73.4505 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [21 empty] | Near Dhan Mandi |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-RSNG-ENB-I003 | I-RJ-RSNG-PMP-0019 | 3 | 1 | A6 I&C | Suratgarh | Ganganagar | Tarachand Ref Rakesh Team | 2026-03-15 | 2 | 29.5943 | 73.5303 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [18 empty] | 60 | 5 |  | Kikrawali |  | LAL CHAND | 9672526292 | Chhotu Ram | 8955001748 | RAMKARAN SHARMA | 6350492192 | JLKD
I-RJ-BDRA-ENB-6007 | I-RJ-BDRA-PMP-0005 | 2 | 1 | A6 I&C | Hanumangarh | Ganganagar | Tarachand Ref Rakesh Team | 2026-03-16 | 3 | 28.9615 | 74.9581 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [18 empty] | 60 | 5 |  | Kunji |  | SHER SINGH | 9887604383 | BIRAM KUMAR | 8290149216 | VACANT | VACANT | JLKD
I-RJ-NAWW-ENB-9090 | I-RJ-NAWW-PMP-0071 | 3 | 1 | A6+B6 I&C | Makrana | Nagaur | Satveer Outsource | 2026-03-14 | 1 | 27.1289 | 74.9446 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Kerpura |  | Ganpat Ram Khod | 6350491968 | MAHENDRA NEHRA | 6350491087 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-NAWW-ENB-9096 | I-RJ-NAWW-PMP-0070 | 1/2 | 2 | A6+B6 I&C | Makrana | Nagaur | Satveer Outsource | 2026-03-15 | 2 | 27.0991 | 75.0208 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Khushiya |  | RAMESHWAR LAL | 6350491990 | SHER SINGH | 6350492106 | RAJENDRA SINGH RATHORE | 6350491813 | JLJH
I-RJ-MKRN-ENB-9064 | I-RJ-MKRN-PMP-0062 | 1 | 1 | A6+B6 I&C | Makrana | Nagaur | Satveer Outsource | 2026-03-16 | 3 | 27.1738 | 74.7307 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Makrana |  | Prema Dahiya | 6350491992 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-UNRA-ENB-6004 | I-RJ-UNRA-PMP-0004 | 3 | 1 | A6 I&C | Tonk | Ajmer | Omprakash Outsource | 2026-03-15 | 1 | 25.9561 | 76.2147 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [18 empty] | 60 | 5 |  | PACHLA RPTR |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLJH
I-RJ-JAAN-ENB-9073 | I-RJ-JAAN-PMP-0046 | 1 | 1 | A6+B6 I&C | Pali | Sirohi | Aneesh & team | 2026-03-15 | 2 | 26.2153 | 74.107 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Tunkara |  | LAXMAN SINGH | 6350491464 | INDRAJEET HARSHALIYA | 8875202884 | VACANT | VACANT | JLJH
I-RJ-JAAN-ENB-9023 | I-RJ-JAAN-PMP-0024 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Aneesh & team | 2026-03-16 | 3 | 26.302 | 74.1212 | GBM | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [21 empty] | Rabriyawas |  | SIKANDAR KHAN | 6350491317 | INDRAJEET HARSHALIYA | 8875202884 | VACANT | VACANT | JLJH
I-RJ-JAAN-ENB-9047 | I-RJ-JAAN-PMP-0045 | 2 | 1 | A6+B6 I&C | Pali | Sirohi | Aneesh & team | 2026-03-17 | 4 | 26.3918 | 74.1735 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Jaitaran |  | SIKANDAR KHAN | 6350491317 | INDRAJEET HARSHALIYA | 8875202884 | VACANT | VACANT | JLJH
I-RJ-SMRP-ENB-9048 | I-RJ-SMRP-PMP-0034 | 1/2/3 | 3 | A6+B6 I&C | Pali | Sirohi | Pawan & Team | 2026-03-15 | 1 | 25.4262 | 73.1799 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [21 empty] | Lapod |  | HANWANT KUMAR | 9351228535 | SHRAWAN KUMAR | 9326488412 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-BALI-ENB-9009 | I-RJ-BALI-PMP-0030 | 1 | 1 | A6+B6 I&C | Pali | Sirohi | Pawan & Team | 2026-03-16 | 2 | 25.33 | 73.2997 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Khimail |  | Jagdish Singh | 9928029065 | SHRAWAN KUMAR | 9326488412 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SMRP-ENB-9036 | I-RJ-SMRP-PMP-0026 | 1/2 | 2 | A6+B6 I&C | Pali | Sirohi | Pawan & Team | 2026-03-17 | 3 | 25.1347 | 73.1096 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Jawai Road |  | Babulal meena | 6350491325 | ARJUN LAL | 8955001722 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-JADE-ENB-9002 | I-RJ-JADE-PMP-0002 | 1/2/3 | 3 | A6+B6 I&C | Sirohi | Sirohi | Pawan & Team | 2026-03-18 | 4 | 24.9874 | 72.7486 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [21 empty] | Jawal |  | Jagdish Kumar | 6350491299 | JITENDRA KUMAR | 9460654853 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-PNDW-ENB-9015 | I-RJ-PNDW-PMP-0055 | 3 | 1 | A6+B6 I&C | Sirohi | Sirohi | Pawan & Team | 2026-03-19 | 5 | 24.7489 | 73.0133 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Kojra Circle |  | JAYPAL SINGH | 8209403026 | GHEESULAL MEENA | 6350492186 | LAKSHYADEEP SINGH GEHLOT | 7014119394 | JLJH
I-RJ-BNML-ENB-9012 | I-RJ-BNML-PMP-0021 | 1/2/3 | 3 | A6+B6 I&C | Jalor | Sirohi |  |  |  | 25.0444 | 72.4076 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [21 empty] | Main Market Tavab Near BSNL BTS |  | KAILASH KUMAR | 8058302215 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-BNML-ENB-9066 | I-RJ-BNML-PMP-0020 | 1/3 | 2 | A6+B6 I&C | Jalor | Sirohi |  |  |  | 25.1859 | 72.4471 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | BHINMAL |  | ANKIT KUMAR DHANWAL | 9315079392 | UPENDRA KUMAR | 9799877374 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-BNML-ENB-9079 | I-RJ-BNML-PMP-0031 | 3 | 1 | A6+B6 I&C | Jalor | Sirohi |  |  |  | 25.065 | 71.9658 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | Bagoda |  | MAHBUB KHAN | 7045641935 | VACANT | VACANT | Tapesh Chouhan | 9012266308 | JLJH
I-RJ-JLOR-ENB-I011 | I-RJ-JLOR-PMP-0055 | 2/3 | 2 | A6+B6 I&C | Jalor | Sirohi |  |  |  | 25.2397 | 72.5075 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | DAKATRA |  | ANKIT KUMAR DHANWAL | 9315079392 | AJAY RANA | 9636817067 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-RNWR-ENB-9026 | I-RJ-RNWR-PMP-0031 | 2 | 1 | A6+B6 I&C | Jalor | Sirohi |  |  |  | 24.7 | 72.2179 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR93 | 2026-03-13 | 2026-03-13 | [18 empty] | NA | NA |  | RANIWARA |  | BHAJAN LAL | 6350491314 | PRAVEEN KUMAR | 7073514436 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-SNCE-ENB-A003 | I-RJ-SNCE-PMP-0024 | 3 | 1 | A6 I&C | Jalor | Sirohi |  |  | Honeybee Issue | 24.7974 | 71.5235 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | [18 empty] | 50 | 5 |  | Bhadarna |  | JETMAL SINGH | 7014142932 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 | JLJH
I-RJ-DENA-ENB-6082 | I-RJ-DENA-PMP-0005 | 1/2 | 2 | A6 I&C | Makrana | Nagaur |  |  | Honeybee Issue | 26.9088 | 73.9864 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | [18 empty] | 120 | 120 |  | SINDLAS |  | IMARAN KHAN | 9887333514 | Ramdev Choudhary | 9414892394 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-JLOR-ENB-V001 | I-RJ-JLOR-PMP-0033 | 3 | 1 | A6 I&C | Jalor | Sirohi |  |  | HONEYBEE ISSUE | 25.4504 | 72.5715 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | [18 empty] | 60 | 5 |  | Mandawala |  | PRABHAKAR SINGH | 6350491294 | GANPAT LAL | 8290147329 | JEETENDRA KUMAWAT | 6377896839 | JLJH
I-RJ-DDWN-ENB-6011 | I-RJ-DDWN-PMP-0052 | 1/3 | 2 | A6 I&C | Ladnu | Nagaur |  |  | Honeybee Issue | 27.2016 | 74.5664 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | 2026-02-14 | [18 empty] | 120 | 10 |  | Ganwari |  | Prema Dahiya | 6350491992 | Mahaveer Kumar | 8078698874 | OM PRAKASH | 6350491377 | JLJH
I-RJ-MENW-ENB-9008 | I-RJ-MENW-PMP-0008 | 1/3 | 2 | A6+B6 I&C | Nagaur | Nagaur |  |  | Honeybee Issue | 26.6452 | 73.7326 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | [19 empty] | NA | NA |  | Gotan |  | BEERBAL GURJAR | 9636611927 | PAPURAM MANDAR | 6350491989 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-DDWN-ENB-9075 | I-RJ-DDWN-PMP-0048 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur |  |  | WO CLOSED/MIN PENDING | 27.4057 | 74.5572 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR91 | 2026-02-21 | 2026-02-21 | [18 empty] | 120 | 50 |  | Didwana |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH
I-RJ-SMRP-ENB-9037 | I-RJ-SMRP-PMP-0033 | 2/3 | 2 | A6+B6 I&C | Pali | Sirohi |  |  | MIN HOLD | 25.2019 | 73.1661 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | [19 empty] | NA | NA |  | Sumerpur |  | HANWANT KUMAR | 9351228535 | ARJUN LAL | 8955001722 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-SMRP-ENB-9046 | I-RJ-SMRP-PMP-0032 | 2/3 | 2 | A6+B6 I&C | Pali | Sirohi |  |  | MIN HOLD | 25.2272 | 73.1622 | GBT | 0 | A6+B6 I&C , ATP11A & 11C |  |  | Allotment- AIR89 | 2026-02-14 | [19 empty] | NA | NA |  | Khindara Sumerpur |  | HANWANT KUMAR | 9351228535 | ARJUN LAL | 8955001722 | CHAMPA LAL BAGRANI | 6378235878 | JLJH
I-RJ-BDRA-ENB-6007 | I-RJ-BDRA-PMP-0005 | 2 | 1 | A6 I&C | Hanumangarh | Ganganagar |  |  | MIN PENDING | 28.9615 | 74.9581 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | [19 empty] | 60 | 5 |  | Kunji |  | SHER SINGH | 9887604383 | BIRAM KUMAR | 8290149216 | VACANT | VACANT | JLKD
I-RJ-BKRD-ENB-6000 | I-RJ-BKRD-PMP-0001 | 1 | 1 | A6 I&C | Nagaur | Nagaur |  |  | MIN PENDING-WBS LOCKED | 27.0484 | 73.5843 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | 2026-02-07 | [18 empty] | 50 | 5 |  | BHAKROD |  | DHARMARAM JAJRA | 6376202299 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 | JLJH
I-RJ-UNRA-ENB-6004 | I-RJ-UNRA-PMP-0004 | 3 | 1 | A6 I&C | Tonk | Ajmer |  |  | MIN PENDING | 25.9561 | 76.2147 | GBT | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR85 | 2026-02-07 | [19 empty] | 60 | 5 |  | PACHLA RPTR |  | OM PRAKASH MEENA | 8955452044 | Rakesh Gurjar | 9079757549 | VACANT | VACANT | JLKD
I-RJ-DDWN-ENB-9075 | I-RJ-DDWN-PMP-0048 | 1/2/3 | 3 | A6 I&C | Ladnu | Nagaur |  |  | WO CLOSED/MIN PENDING | 27.4057 | 74.5572 | GBM | 0 | A6 I&C , ATP11A & 11C |  |  | Allotment- AIR92 | 2026-03-11 | 2026-03-12 | [18 empty] | 120 | 50 |  | Didwana |  | BALDEWA RAM | 8058503498 | Mahaveer Burdak | 7665889561 | OM PRAKASH | 6350491377 | JLJH

## SECTOR ADDITION
SITE ID | Sector | NO OF SECTOR | BAND | JC NAME | CMP | Team | Plan Date | Current Status | LATITUDE | LONGITUDE | SITE TYPE | SITE IP | ACTIVITY | ACTIVITY CHANGES IF ANY | EXTRA MIN IF ANY | ALLOTMENT LOT | ALLOTMENT DATE | MATERIAL DISPATCHED DATE | INSTALLATION DATE | INTEGRATION DATE | ATP 11A DATE | 11A REMARK | Material Need to MRN | EXTRA MIN (YES/NO) | MRN REQUIRED (YES/NO) | MRN FINALIZATION STATUS | REASON IF MRN PENDING | WCC | RECO STATUS | REASON IF RECO PENDING | READY FOR BILLING OR NOT | REMARKS IF ANY | Digitcom Remark | SITE NAME | SITE ADDRESS | IANL Name | IANL Contact | IANL Mail ID | JIO Technician Name | Jio Technician Contact | Rigger Name | Rigger Contact | CI Name | CI Number | Infra Engg Name | Infra Engg Mail ID | Infra Engg Number | MIN Location | MRN Location | WO NUMBER | DC NUMBER | PERFORMA INVOICE NO | INSTALLATION OF ANTENNAS QTY 2800 | SITE ACCEPTANCE TESTING QTY 1500 | CONFIGURATION SERVICES, IT HARDWARE QTY 700 | TRANSPORTATION OF FIM QTY 1500 | REMOVAL OF ANTENNA SET FOR W/L EQUIP QTY 2000 | DISMANTELLING OF GSM ANTENNA QTY 1000 | INSTALLATION OF GSM ANTENNA QTY 1200 | REVISIT CHARGES 1000 | EXTRA KM QTY 18 per Km | BILLING | WITHOUT TPT & SS | TPT BILLING | APPPROVED BILLING | TEAM EXP | TEAM PAYMENT | TEAM BALANCE
I-RJ-KTHM-ENB-X001 | 0/1/2 | 3 | PB ADDITION | Alwar | Alwar | Hanuman & Team |  | Done | 27.2132 | 77.0233 | GBT | 0 | PB ADDITION IN ALL 3 SECTOR & MB SB DISMANTLING |  |  | Allotment- 1 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-19 | 2025-04-19 |  |  | NO | YES | FILALIZED | [7 empty] | Sh.Bishan Lal Saini S/o Sh.Chutan Lal Saini, Khasra No.1144, Urli Patti, Vill- Sonkhar, Tehsil- Kathoomar, Distt.Alwar | [13 empty] | JLKD |  |  | PB001 | PFI015 | 1 | 0 | 1 | 2 | 1 | 5 | 2 | 0 | 272 | 20796 | 17796 |  |  | 5805
I-RJ-JDPR-ENB-0117 | 0/2 | 2 | PB ADDITION | Jodhpur | Jodhpur | Rajkumar & team |  | Done | 26.2671 | 72.9738 | GBM_Old | 0 | PB ADDITION IN ALPHA GAMMA & MB SB DISMANTLING |  |  | Allotment- 2 | 2025-04-19 | 2025-04-21 | 2025-04-23 | 2025-04-23 | 2025-04-23 |  |  | NO | YES | FILALIZED | [7 empty] | Near lata beauty parlor,chopasni housingh board, Jodhpur 342003 | [13 empty] | JLJH |  |  | PB002 | PFI015 | 1 | 0 | 1 | 2 | 1 | 3 | 1 | 0 | 0 | 12700 | 9700 |  |  | 4365
I-RJ-XXXX-COW-0137 | 0 | 1 | ANT ALARM RECTIFICATION | Balotra | Barmer | Rohit & team |  | Done | 25.9523 | 72.1893 | COW | 0 | FAULTY PB REPLACMENT |  |  | Allotment- 3 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | OK |  | NO | YES | FILALIZED | [12 empty] | JETA RAM | 7665881999 | VACANT | VACANT | JITENDRA SOLANKI | 6350492197 |  |  |  | JLJH |  |  | PB003 | PFI015 | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 96 | 9528 | 6528 |  |  | 1900
I-RJ-PHPD-ENB-H001 | 0 | 1 | BSA REMOVAL | Balotra | Barmer | Rohit & team |  | Done | 25.8536 | 72.2883 | GBT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 3 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | 2025-05-27 | OK |  | NO | YES | FILALIZED | [7 empty] | Sh. Jitendra singh s/o Sh. Bhur singh V/P Moongra, Via--Balotra, TH. Pachpadra, Distt. Barmer |  |  |  |  | JETA RAM | 7665881999 | VACANT | VACANT | JITENDRA SOLANKI | 6350492197 |  |  |  | JLJH |  |  | BSA002 | PFI014 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 84 | 6512 | 3512 |  |  | 1400
I-RJ-BRMR-ENB-0018 | 1 | 1 | BSA REMOVAL | Barmer | Barmer | Rohit & team |  | Done | 25.7568 | 71.3835 | GBT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 3 | 2025-05-27 | 2025-05-27 | 2025-05-29 | 2025-05-29 | 2025-05-29 | OK |  | NO | YES | FILALIZED | [7 empty] | Khasra No. 1462/2, Railway Kua No.03, Behind Hinglaj Temple, Ward No.40, Home Gourd Road, Barmer |  |  |  |  | VACANT | VACANT | Chaturbhuj Choudhary | 8005898235 | GIRDHARI RAM PRAJAPAT | 6350492189 |  |  |  | JLJH |  |  | BSA002 | PFI014 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 284 | 10112 | 7112 |  |  | 1400
I-RJ-BKNR-ENB-0009 | 0 | 1 | BSA REMOVAL | Bikaner | Bikaner | Dileep & team |  | Done | 28.028 | 73.3197 | GBT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 3 | 2025-05-27 | 2025-05-27 | 2025-05-30 | 2025-05-30 | 2025-05-30 | OK |  | NO | YES | FILALIZED | [7 empty] | Jaimalsar House, Old Ginani, Kohriyo Ka Mohalla, Bikaner |  |  |  |  | Surendra Kumar Samaria | 8078699480 | Bablu Nath Nath | 8078696110 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH |  |  | BSA002 | PFI014 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 396 | 12128 | 9128 |  |  | 1400
I-RJ-BKNR-ENB-A001 | 1 | 1 | BSA REMOVAL | Bikaner | Bikaner | Rohit & team |  | Done | 28.0281 | 73.3088 | GBT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 3 | 2025-05-27 | 2025-05-27 | 2025-05-30 | 2025-05-30 | 2025-05-30 | OK |  | NO | YES | FILALIZED | [7 empty] | National Highway 15, Pratap Basti, Bikaner |  |  |  |  | Surendra Kumar Samaria | 8078699480 | SUDHIR SHARMA | 9529491630 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH |  |  | BSA002 | PFI014 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 8 | 5144 | 2144 |  |  | 1400
I-RJ-BKNR-ENB-6002 | 0 | 1 | BSA REMOVAL | Bikaner | Bikaner | Dileep & team |  | Done | 28.0038 | 73.3115 | GBT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 3 | 2025-05-27 | 2025-05-27 | 2025-05-30 | 2025-05-30 | 2025-05-30 | OK |  | NO | YES | FILALIZED | [7 empty] | Ravindra ParekhNear Goga Gate, BikanerRAJ |  |  |  |  | RAJ KUMAR | 8824144441 | Ramkishan Jat | 8078699432 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH |  |  | BSA002 | PFI014 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 6 | 5108 | 2108 |  |  | 1400
I-RJ-JPUR-ENB-6159 | 1 | 1 | BSA REMOVAL | Rajapark, Jaipur | Jaipur-2 | Hanuman & Team |  | Done | 26.9067 | 75.8424 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 3 | 2025-05-27 | 2025-05-27 | 2025-06-04 | 2025-06-04 | 2025-06-04 | OK |  | NO | YES | FILALIZED | [7 empty] | SHRI VINENDRA KUMAR JAIN HOTEL UNITED BUILDING TRANSPORT NAGAR SHOW ROOM NO 5 AGRA ROAD JAIPUR |  |  |  |  | Anurag Sharma | 8078699520 | SHYAMU SAINI | 8955937634 | SANTOSH SHARMA | 9251637621 |  |  |  | JLKD |  |  | BSA01 | PFI014 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 5000 | 2000 |  |  | 1400
I-RJ-SDAR-ENB-H004 | 2 | 1 | 850-SB | Sardarshahar | Sikar | Aneesh & team |  | Done | 28.5775 | 74.3586 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-01 | OK |  | NO | NO | NR | [8 empty] | Sh. Ram kumar s/o Sh. Shera ram jat, V/P Malsar V/P Malsar, TH. Sardarshahar, Distt. Churu |  |  |  | MANISH KUMAR | 6350492251 | RAMNIWAS GIRI | 6350491513 | RAVINDER KUMAR | 6350616703 |  |  |  | JLKD |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 285 | 10000 | 8500 |  |  | 1400
I-RJ-FATG-ENB-I004 | 1 | 1 | 850-SB | Jaisalmer | Barmer | Rohit & team |  | Done | 26.8043 | 71.3111 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | 2025-07-01 | 2025-07-01 | 2025-07-01 | OK |  | NO | NO | NR | [8 empty] | Sh. Hathi Singh s/o Sh.Bhanwar singh, Near Dawana Moolana Road Village- Moolana Tehsil-Fatehgarh Dist-Jaisalmer |  |  |  | ISHWAR SINGH | 7023927882 | BASHIR KHAN | 9079161239 | VACANT | VACANT |  |  |  | JLKD |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 235 | 9000 | 7500 |  |  | 1400
I-RJ-RARH-ENB-I004 | 0 | 1 | 850-SB | Sujangarh | Sikar | Aneesh & team |  | Done | 28.1074 | 74.4286 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-02 | OK |  | NO | NO | NR | [8 empty] | Sh. Paras Nath S/O Sh. Nurang Nath V&ampPost.- Binadesar Sidawatan Th.- RatanGarh Distt- Churu 331022 |  |  |  | Jitendra Kumar | 6350491094 | VINOD NAIN | 6377209964 | Kana Ram | 6350491095 |  |  |  | JLKD |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 234 | 8980 | 7480 |  |  | 1400
I-RJ-SJGR-ENB-I020 | 1 | 1 | 850-SB | Sujangarh | Sikar | Aneesh & team |  | Done | 27.6377 | 73.8898 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-02 | OK |  | NO | NO | NR | [8 empty] | Sh. Manaram Saran s/o Sh. Jasu ram, Kh. No. 337, V/P Kandhalsar, Via--Lalgarh, Tehsil Sujangarh, Distt. Churu, PIN 331507 |  |  |  | kurda ram khileri | 6350491101 | JAGDISH PRAJAPAT | 6350491291 | Kana Ram | 6350491095 |  |  |  | JLKD |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 230 | 8900 | 7400 |  |  | 1400
I-RJ-KESR-ENB-I004 | 0/1/2 | 3 | 850-SB | Nagaur | Nagaur | Rohit & team |  | Done | 27.14 | 73.1929 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-02 | OK |  | NO | NO | NR | [8 empty] | Smt. Deepa devi w/o Sh. Joga ram, Kh. No. 1731, V- Bhomasar Post- Karnau, TH- Khinvsar, Distt- Nagaur |  |  |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 |  |  |  | JLJH |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 150 | 9700 | 8200 |  |  | 2600
I-RJ-NOHA-ENB-I014 | 1 | 1 | 850-SB | Bikaner | Bikaner | Rohit & team |  | Done | 27.2627 | 73.2763 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | 2025-07-02 | 2025-07-02 | 2025-07-02 | OK |  | NO | NO | NR | [8 empty] | Ward No 2 V/P Sarunda The- Nokha Dist Bikaner |  |  |  | RAKESH KUMAR | 9351038446 | SURESH KUMAR | 8078698902 | AJAY SINGH CHAUHAN | 9352230040 |  |  |  | JLJH |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 161 | 7520 | 6020 |  |  | 1400
I-RJ-SIKR-ENB-I019 | 0 | 1 | 850-SB | Sikar | Sikar |  |  | MRN Done | 27.3828 | 74.8794 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | [5 empty] | NO | NO | NR | [8 empty] | Khasra No. 474, Choti Losal via Losal, Distt. Sikar-332025 |  |  |  | TARACHAND CHOUDHARY | 6376917201 | MUKESH KUMAR | 9799094747 | INDRAJ SARAN | 8107587670 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 115 | 5300 | 2300 |  |  | 1400
I-RJ-PILN-ENB-I002 | 1 | 1 | 850-SB | Jhunjhunun | Sikar |  |  | MRN Done | 28.4222 | 75.7538 | GBT | 0 | 850 SB WITH RET INSTALLATION |  |  | Allotment- 4 | 2025-06-28 | 2025-06-30 | [5 empty] | NO | NO | NR | [8 empty] | Sh. Ajay Kumar, S/o Sh. Ratan Singh, Khasra No.- 704/261, Vill- Peepli |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 245 | 7900 | 4900 |  |  | 1400
I-RJ-JPUR-ENB-0758 | 2 | 1 | BSA REMOVAL | Vaishali, Jaipur | Jaipur-2 | Rajkumar & team |  | Done | 26.9224 | 75.6473 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-08 | 2025-07-08 | 2025-07-08 |  |  | NO | YES | FILALIZED | [8 empty] | P.No.56, Shri Ganesh Nagar, Siwar Mod, Bindayka, Sirsi Road Jaipur |  |  |  | Mangi Lal Yadav | 8078699650 | HARIOM MALI | 9166257320 | KAMLESH SHARMA | 8078699590 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 28 | 5560 | 2560 |  |  | 1400
I-RJ-JPUR-ENB-0134 | 2 | 1 | BSA REMOVAL | Vaishali, Jaipur | Jaipur-2 | Rajkumar & team |  | Done | 26.9296 | 75.7493 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-08 | 2025-07-08 | 2025-07-08 |  |  | NO | YES | FILALIZED | [8 empty] | Dayal Shekhwat W/o Devenrda Singh Rathor Shop No. 75, Jashawat Nagar, Khatipura Road, Jaipur |  |  |  | JUGAL KISHOR KUSHVAHA | 7849824270 | Shyoji Ram Mali | 8955001729 | KAMLESH SHARMA | 8078699590 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 36 | 5720 | 2720 |  |  | 1400
I-RJ-JPUR-ENB-1536 | 0/1/2 | 3 | BSA REMOVAL | Vaishali, Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9235 | 75.7153 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-08 | 2025-07-08 | 2025-07-08 |  |  | NO | YES | FILALIZED | [8 empty] | Jaipur |  |  |  | SANTOSH KUMAR SHARMA | 9251635946 | HARIOM MALI | 6350491658 | KAMLESH SHARMA | 8078699590 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 35 | 7700 | 4700 |  |  | 2600
I-RJ-JPUR-ENB-0125 | 1 | 1 | BSA REMOVAL | Vaishali, Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.8999 | 75.7501 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-08 | 2025-07-08 | 2025-07-08 |  |  | NO | YES | FILALIZED | [8 empty] | Near Someshwer Park,Vidhut Nagar-A,Ajmer Road Jaipur 302021 |  |  |  | LOKENDRA KUMAR | 9509627138 | Shyoji Ram Mali | 8955001729 | KAMLESH SHARMA | 8078699590 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 32 | 5640 | 2640 |  |  | 1400
I-RJ-JDPR-ENB-0025 | 0/1 | 2 | BSA REMOVAL | Jodhpur | Jodhpur | Rohit & team |  | Done | 26.2105 | 73.0239 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-08 | 2025-07-08 | 2025-07-08 |  |  | NO | YES | FILALIZED | [8 empty] | Lalit Paliwal S/o Sh. Kanhaya Lal PaliwalPlot No. 5-CS-4, Kudi Bhaktasni, Housing Board, Jodhpur - 342005 |  |  |  | PAVAN JANGID | 8619862952 | Govind ram | 9521010289 | Rajender Kumar | 9671501313 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 12 | 6240 | 3240 |  |  | 1900
I-RJ-JDPR-ENB-0014 | 1 | 1 | BSA REMOVAL | Jodhpur | Jodhpur | Rohit & team |  | Done | 26.2403 | 72.9979 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-08 | 2025-07-08 | 2025-07-08 |  |  | NO | YES | FILALIZED | [8 empty] | Badri Narayan Ladha S/o Moti lal Ladha Road No.11, Basni II nd Phase,Jodhpur |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 16 | 5320 | 2320 |  |  | 1400
I-RJ-KOTA-ENB-0062 | 0 | 1 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.2048 | 75.8286 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-09 | 2025-07-09 | 2025-07-09 |  |  | NO | YES | FILALIZED | [8 empty] | Mahendra Kumar Jain S/o Sh. Roop Chandra Jain House No.309, Ridhi Sidhi Nagar - I, Bundi Road, Kota - 324008 |  |  |  | AQUIB JAVED | 6350491018 | SATYANARAYAN GURJAR | 6350491561 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 276 | 10520 | 7520 |  |  | 1400
I-RJ-KOTA-ENB-0357 | 1 | 1 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.202 | 75.8282 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-09 | 2025-07-09 | 2025-07-09 |  |  | NO | YES | FILALIZED | [8 empty] | Near Suwalka Pearl Appartment, Ridhi Sidhi Nagar 1st, Kunhadi, Kota |  |  |  | AQUIB JAVED | 6350491018 | SATYANARAYAN GURJAR | 6350491561 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 276 | 10520 | 7520 |  |  | 1400
I-RJ-KOTA-ENB-0102 | 1 | 1 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.2377 | 75.8871 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-09 | 2025-07-09 | 2025-07-09 |  |  | NO | YES | FILALIZED | [8 empty] | Femida Aashina W/o Sh. Shafi MohammadHouse No.22, Street No.6, Pratap Colony, Rangpur Road, Kota - 324002 |  |  |  | Abdul Sattar | 6350491162 | BAWANIT KUMAR | 6350491635 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 243 | 9860 | 6860 |  |  | 1400
I-RJ-JPUR-ENB-0368 | 0 | 1 | BSA REMOVAL | Rajapark, Jaipur | Jaipur-2 | Rajkumar & team |  | Done | 26.8559 | 75.8311 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-09 | 2025-07-09 | 2025-07-09 |  |  | NO | YES | FILALIZED | [8 empty] | Hotel Hill View Road, Between F18 & F15, Malviya Industrial Area, Jaipur 302020 |  |  |  | Arjun Lal Jat | 8078699526 | VIVEK SHARMA | 7849824277 | SANTOSH SHARMA | 9251637621 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 42 | 5840 | 2840 |  |  | 1400
I-RJ-JPUR-ENB-0567 | 2 | 1 | BSA REMOVAL | Rajapark, Jaipur | Jaipur-2 | Rajkumar & team |  | Done | 26.9153 | 75.8252 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-09 | 2025-07-09 | 2025-07-09 |  |  | NO | YES | FILALIZED | [8 empty] | Sulabh complex ke paas, Sanagneri Gate, jaipur |  |  |  | VINOD KUMAR YADAV | 9672359628 | RAKESH KUMAR SAINI | 8949481674 | SANTOSH SHARMA | 9251637621 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 40 | 5800 | 2800 |  |  | 1400
I-RJ-LUNI-ENB-0010 | 1 | 1 | BSA REMOVAL | Jodhpur | Jodhpur | Rohit & team |  | Done | 26.1927 | 73.0563 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-10 | 2025-07-10 | 2025-07-10 |  |  | NO | YES | FILALIZED | [8 empty] | Out SidKudi Filter House, ear vyas Istitute, Jodhpur |  |  |  | SURENDRA KARWASRA | 6350492238 | Ravindra bishnoi | 6377295846 | Rajender Kumar | 9671501313 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 8 | 5160 | 2160 |  |  | 1400
I-RJ-PALI-ENB-0007 | 1 | 1 | BSA REMOVAL | Pali | Sirohi | Rohit & team |  | Done | 25.7735 | 73.314 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-10 | 2025-07-10 | 2025-07-10 |  |  | NO | YES | FILALIZED | [8 empty] | Tilok Ram patel s/o Dhana Ram27,kidvai Nagar, Garwala Jav, Main mandia Road, Pali |  |  |  | JAGDISH SINGH | 8302540479 | RAVINDRA KUMAR | 9529143828 | CHAMPA LAL BAGRANI | 6378235878 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 55 | 6100 | 3100 |  |  | 1400
I-RJ-KOTA-ENB-0013 | 0 | 1 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.177 | 75.8505 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-10 | 2025-07-10 |  |  | NO | YES | FILALIZED | [8 empty] | Yusuf Ali S/o Sh. Moh. Husain BandukwalaHouse No. 146, Kotri Road, Vallabhav Bari, Kota |  |  |  | KULDEEP SINGH | 6350491266 | KULDEEP SINGH | 6350491266 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 281 | 10620 | 7620 |  |  | 1400
I-RJ-KOTA-ENB-0110 | 0 | 1 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.1607 | 75.8695 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-10 | 2025-07-10 |  |  | NO | YES | FILALIZED | [8 empty] | Mr. Vijay Kumar S/O Lat Sh. Prabhu lal Plot-No--SPL/3/Z, PL industries, Chambal Ind Area, KOTA, Rajasthan |  |  |  | Mohit Sharma | 6350491223 | VINOD KUMAR | 8955109803 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 285 | 10700 | 7700 |  |  | 1400
I-RJ-KOTA-ENB-0068 | 0/2 | 2 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.1403 | 75.8749 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-10 | 2025-07-10 |  |  | NO | YES | FILALIZED | [8 empty] | Umesh Prajapati S/o ML PrajapatiBehind National School, Prem Nagar-Ist, Kota |  |  |  | Ashok Kumar Khalmaniya | 6350491166 | kamla shankar dhakar | 6350491211 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 287 | 11740 | 8740 |  |  | 1900
I-RJ-CHMU-ENB-0019 | 0 | 1 | BSA REMOVAL | Chomu | Jaipur-1 | Rajkumar & team |  | Done | 27.1637 | 75.7364 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-10 | 2025-07-10 |  |  | NO | YES | FILALIZED | [8 empty] | On morija road, Near Palika sign bord,between on side EB transformer amp; other site kumawat trackter, Morija road, Chomu |  |  |  | Shankar Lal Yadav | 6350491475 | VACANT | VACANT | ANKIT KUMAWAT | 6377201203 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 65 | 6300 | 3300 |  |  | 1400
I-RJ-ALWR-ENB-0055 | 0 | 1 | BSA REMOVAL | Alwar | Alwar | Rajkumar & team |  | Done | 27.571 | 76.6158 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-10 | 2025-07-10 | 2025-07-10 |  |  | NO | YES | FILALIZED | [8 empty] | Scheme No-2, Alwar |  |  |  | MINTU RAM BAIRWA | 6350491737 | VACANT | VACANT | GAJENDRA SINGH SHEKHAWAT | 8003390514 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 193 | 8860 | 5860 |  |  | 1400
I-RJ-RGMD-ENB-9029 | 1 | 1 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 24.6453 | 75.9463 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-11 | 2025-07-11 | 2025-07-11 |  |  | NO | YES | FILALIZED | [8 empty] | In Side Vegetable Mandi Premises, Ramganjmandi, Dist. Kota |  |  |  | MUKESH KUMAR SHARMA | 6350491226 | PAWAN KUMAR | 6350491241 | dinesh kumar sharma | 6350491191 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 355 | 12100 | 9100 |  |  | 1400
I-RJ-KOTA-ENB-0092 | 1/2 | 2 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.1273 | 75.8549 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-11 | 2025-07-11 | 2025-07-11 |  |  | NO | YES | FILALIZED | [8 empty] | Khushvindra Gupta S/O lat Sh H R Gupta Plot No-406,Neha Buety Parlor, Rang bari Kota, rajasthan |  |  |  | BAJRANG LAL SHARMA | 6350491168 | kamla shankar dhakar | 6350491211 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 293 | 11860 | 8860 |  |  | 1900
I-RJ-KOTA-ENB-0087 | 2 | 1 | BSA REMOVAL | Kota | Kota | Aneesh & team |  | Done | 25.1394 | 75.8269 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-11 | 2025-07-11 | 2025-07-11 |  |  | NO | YES | FILALIZED | [8 empty] | Dinesh Kumar Nagar s/o Sh. Anandi Lal Nagar House No. 3-SE-21, Mahaveer Nagar Ext. Kota |  |  |  | BAJRANG LAL SHARMA | 6350491168 | kamla shankar dhakar | 6350491211 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 290 | 10800 | 7800 |  |  | 1400
I-RJ-SRHI-ENB-9011 | 2 | 1 | BSA REMOVAL | Sirohi | Sirohi | Rohit & team |  | Done | 24.5231 | 72.5147 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-11 | 2025-07-11 | 2025-07-11 |  |  | NO | YES | FILALIZED | [8 empty] | #N/A |  |  |  | BHAVESH KUMAR | 9672487892 | VIMLESH KUMAR TIWARI | 9399419761 | LAKSHYADEEP SINGH GEHLOT | 7014119394 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 232 | 9640 | 6640 |  |  | 1400
I-RJ-UDPR-ENB-0080 | 2 | 1 | BSA REMOVAL | Udaipur | Udaipur | Rohit & team |  | Done | 24.553 | 73.6747 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-11 | 2025-07-11 | 2025-07-11 |  |  | NO | YES | FILALIZED | [8 empty] | Near Sehanai Marrige Garden Shi8karwadi Udaipur-313001 |  |  |  | UMAKANT TIWARI | 9602943123 | Bheru Lal Salvi | 6350491460 | NEMI CHAND | 6350492247 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 239 | 9780 | 6780 |  |  | 1400
I-RJ-TJRS-ENB-9085 | 1 | 1 | BSA REMOVAL | Tijara (N) (Bhiwadi) | Alwar | Rajkumar & team |  | Done | 28.1574 | 76.8793 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-11 | 2025-07-11 | 2025-07-11 |  |  | NO | YES | FILALIZED | [8 empty] | On Road Side T Point,Gate No. 2,Polycon Industrial Limited,F-94A,Chopnki Industrial Area,Bhiwadi |  |  |  | RAHUL KUMAR | 8445004815 | PRAVESH KUMAR CHOUDHARY | 8505059295 | NAWAL SINGH | 7015766923 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 245 | 9900 | 6900 |  |  | 1400
I-RJ-MPUR-ENB-9033 | 2 | 1 | BSA REMOVAL | Tonk | Ajmer | Aneesh & team |  | Done | 26.3024 | 75.3746 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-12 |  |  | NO | YES | FILALIZED | [8 empty] | RIIICO OFFICE Road No 2Malpura RIICO |  |  |  | MUKESH KUMAR GURJAR | 7850035105 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 80 | 6600 | 3600 |  |  | 1400
I-RJ-UDPR-ENB-0200 | 1 | 1 | BSA REMOVAL | Udaipur | Udaipur | Rohit & team |  | Done | 24.5938 | 73.7467 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-12 |  |  | NO | YES | FILALIZED | [8 empty] | Pratap Nagar, Udaipur |  |  |  | SUMEET SHARMA | 7737664418 | sohan singh dasana | 6350491466 | NEMI CHAND | 6350492247 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 236 | 9720 | 6720 |  |  | 1400
I-RJ-NTDW-ENB-9035 | 0/2 | 2 | BSA REMOVAL | Rajsamand | Bhilwara | Rohit & team |  | Done | 24.9309 | 73.8225 | RTM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-12 | 2025-07-12 | 2025-07-12 |  |  | NO | YES | FILALIZED | [8 empty] | Jagdeesh, Nai Road ,Near Bandari Vatika Nathdwara |  |  |  | Ashok kumar Kumhar | 8949549355 | Shambhu Lal Bhil | 6350491044 | BHUPENDRA KUMAR SHARMA | 6375865962 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 194 | 9880 | 6880 |  |  | 1900
I-RJ-BRPR-ENB-0022 | 1 | 1 | BSA REMOVAL | Bharatpur | Bharatpur | Rajkumar & team |  | Done | 27.204 | 77.4669 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-12 | 2025-07-12 | 2025-07-12 |  |  | NO | YES | FILALIZED | [8 empty] | Poonam Paliwal W/o Sh. Akhilesh Paliwal House No.12-A, Ganesh Nagar, Bharatpur |  |  |  | Vinod Kumar | 6350491338 | SUNIL SINGH | 7014797737 | HOTI SINGH | 6350491351 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 216 | 9320 | 6320 |  |  | 1400
I-RJ-JDPR-ENB-0158 | 1/2 | 2 | BSA REMOVAL | Jodhpur | Jodhpur | Rohit & team |  | Done | 26.2797 | 73.0172 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-18 | 2025-07-18 | 2025-07-18 |  |  | NO | YES | FILALIZED | [8 empty] | Mohd. Ismail Baig S/o Sh. Mohd. Iqbal Baig Hakam Bagh, Behind Olympic Cinema, Jodhpur - 342001 |  |  |  | JASWANT SINGH | 7340688065 | CHOTU SINGH | 6375271836 | Rajender Kumar | 9671501313 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 19 | 6380 | 3380 |  |  | 1900
I-RJ-BKNR-ENB-0219 | 0 | 1 | BSA REMOVAL | Bikaner | Bikaner | Rohit & team |  | Done | 27.9701 | 73.31 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-15 | 2025-07-15 | 2025-07-15 |  |  | NO | YES | FILALIZED | [8 empty] | Smt Pushpa Devi W/o Sh Amar SinghBaba Ramdev Colony, Nokha Road, Bikaner (Raj) |  |  |  | GOURI SHANKAR | 9314448912 | Ramkishan Jat | 8078699432 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 247 | 9940 | 6940 |  |  | 1400
I-RJ-BKNR-ENB-0005 | 0 | 1 | BSA REMOVAL | Bikaner | Bikaner | Rohit & team |  | Done | 28.0062 | 73.3204 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-15 | 2025-07-15 | 2025-07-15 |  |  | NO | YES | FILALIZED | [8 empty] | Surendra Sethia S/o Late Sh Khem Chand Sethia Rani Bazar, Behind Suraj Talkies, Bikaner |  |  |  | KRISHAN LAL | 8440061345 | Ramkishan Jat | 8078699432 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 251 | 10020 | 7020 |  |  | 1400
I-RJ-SDAR-ENB-0010 | 0/2 | 2 | BSA REMOVAL | Sardarshahar | Sikar | Rohit & team |  | Done | 28.449 | 74.5039 | NGBT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | 2025-07-17 | 2025-07-17 | 2025-07-17 |  |  | NO | YES | FILALIZED | [8 empty] | Khasra No-58/3, Plot No-A-13, Bhukalsar Baas, Ward No-13, Sardarshahar, Tehsil-Sardarshahar, Distt-Churu (Raj) |  |  |  | SURESH KUMAR PRAJAPAT | 6350491533 | RAJENDRA KUMAR MEGHWAL | 8078699424 | RAVINDER KUMAR | 6350616703 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 261 | 11220 | 8220 |  |  | 1900
I-RJ-GGGR-ENB-0005 | 0/1 | 2 | BSA REMOVAL | Ganganagar | Ganganagar | Rohit & team |  | Done | 29.9205 | 73.8743 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-16 |  |  | NO | YES | FILALIZED | [8 empty] | Sh Praveen Nagpal S/o Sh Milki Ram Nagpal172-G Block, Partik Plaza, Shri Ganganagar (Raj) |  |  |  | VIKRAM SINGH | 9680365252 | JASWINDER SINGH | 9501437875 | RAMKARAN SHARMA | 6350492192 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 484 | 15680 | 12680 |  |  | 1900
I-RJ-PDMP-ENB-9037 | 1/2 | 2 | BSA REMOVAL | Ganganagar | Ganganagar | Rohit & team |  | Done | 29.703 | 73.6312 | RTM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-16 | 2025-07-16 | 2025-07-16 |  |  | NO | YES | FILALIZED | [8 empty] | Sh Dinesh Miglani S/o Sh Tilak Raj, Male Square, Near Bharat Petrol Pump, Opp Kamal Variety Store, Main Road, Padampur, Tehsil-Padampur, Distt-Shri Ganganagar (Raj) |  |  |  | HANUMAN DAS | 8239158388 | VACANT | VACANT | RAMKARAN SHARMA | 6350492192 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 480 | 15600 | 12600 |  |  | 1900
I-RJ-BNSU-ENB-9025 | 2 | 1 | BSA REMOVAL | Alwar | Alwar |  |  | MRN Done | 27.6816 | 76.3516 | RTT | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-07 | [5 empty] | NO | YES | FILALIZED | [8 empty] | Sushil Kumar , Tehsil - Bansur , Alwar |  |  |  | JATIN SINGH SHEKHAWAT | 8005666463 | KULDEEP SAINI | 7073068883 | UPENDRA SINGH | 8000501241 |  |  |  | JLKD |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 158 | 8160 | 5160 |  |  | 1400
I-RJ-OSNN-ENB-9077 | 1 | 1 | 850-SB | Jodhpur | Jodhpur | Rohit & team |  | Done | 26.7159 | 73.1968 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-20 | 2025-07-20 |  |  | NO | NO | NR | [8 empty] | Khasra No. 179, 184, 191, 329, 412 & 72, Village- Hardani, Tehsil- Baori, Jodhpur (Raj.) |  |  |  | Bhiya Ram | 6350616503 | Deva Ram | 6350492245 | MITENDRA RAGHAV | 9368129150 |  |  |  | JLJH | JLJH |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 75 | 5800 | 4300 |  |  | 1400
I-RJ-NGUR-ENB-H007 | 0 | 1 | 850-SB | Nagaur | Nagaur | Rohit & team |  | Done | 26.937 | 73.7795 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-20 | 2025-07-20 |  |  | NO | NO | NR | [8 empty] | Sh. Ram karan s/o Sh. Mangla ram Kh. No. 366, V/P Bunrawata, TH. & Distt. Nagaur |  |  |  | DHARMARAM JAJRA | 6376202299 | MAHENDRA DHUNDHWAL | 9057571856 | DHARMENDRA SINGH | 8923520291 |  |  |  | JLJH | JLJH |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 141 | 7120 | 5620 |  |  | 1400
I-RJ-LDNU-ENB-H001 | 0 | 1 | 850-SB | Ladnun | Nagaur | Rohit & team |  | Done | 27.6156 | 74.2882 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | NO | NO | NR | [8 empty] | Sh. Asha ram s/o Sh. Joja ram V/P Hirawati, TH. Ladnu, Distt. Nagaur |  |  |  | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 |  |  |  | JLJH | JLJH |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 236 | 9020 | 7520 |  |  | 1400
I-RJ-SJGR-ENB-I012 | 2 | 1 | 850-SB | Sujangarh | Sikar | Rohit & team |  | Done | 27.7573 | 73.9253 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-21 | 2025-07-21 | 2025-07-21 |  |  | NO | NO | NR | [8 empty] | Sh. Deepa Ram S/o Sh. Bhoma Ram Kh.No. 192, V&ampPost- Gewarsar, Th.- Sujangarh, Distt- Churu 331507 |  |  |  | kurda ram khileri | 6350491101 | JAGDISH PRAJAPAT | 6350491291 | Kana Ram | 6350491095 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 227 | 8840 | 7340 |  |  | 1400
I-RJ-LLST-ENB-H001 | 0/1/2 | 3 | 850-SB | Dausa | Jaipur-1 | Aneesh & team |  | Done | 26.4933 | 76.4059 | GBT | 0 | SB ADDITION IN PLANNED SECTOR | only one ints done |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-22 | 2025-07-22 | 2025-07-22 |  |  | NO | NO | NR | [8 empty] | Sh. Rameshwar sharma s/o Sh. Kashi ram Kh. No. 149, V/P Suratpura, TH. Lalsot, Distt. Dausa |  |  |  | LOKESH KUMAR MEENA | 6350491476 | NATVAR SINGH | 9351228567 | MANOJ KUMAR SHARMA | 6350491496 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 125 | 9200 | 7700 |  |  | 2600
I-RJ-BYNA-ENB-I004 | 0 | 1 | 850-SB | Bharatpur | Bharatpur | Aneesh & team |  | Done | 26.8542 | 77.3229 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-22 | 2025-07-22 | 2025-07-22 |  |  | NO | NO | NR | [8 empty] | Khasra No.- 1642, VPO.- Thana Daang, Tehsil.- Bayana, Distt.- Bharatpur |  |  |  | NATWAR LAL SHARMA | 8696843924 | BHOOP SINGH | 6350491372 | HOTI SINGH | 6350491351 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 217 | 8640 | 7140 |  |  | 1400
I-RJ-LKNR-ENB-I009 | 0 | 1 | 850-SB | Bikaner | Bikaner | Rohit & team |  | Done | 28.5798 | 74.0618 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-23 | 2025-07-23 | 2025-07-23 |  |  | NO | NO | NR | [8 empty] | Sh. Ganesh Ram S/o Sh. Chanda Ram, Village-Dhani Pandusar Post-Karnisar Tehsil-Lunkaransar Dist.-Bikaner |  |  |  | SUNIL KUMAR | 6350666491 | NARESH KUMHAR | 9928996703 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH | JLJH |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 366 | 11620 | 10120 |  |  | 1400
I-RJ-BNSU-ENB-9061 | 0/1/2 | 3 | PB ADDITION | Alwar | Alwar | Aneesh & team |  | Done | 27.6935 | 76.3509 | RTT | 0 | PB ADDITIONA IN ALL SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-23 | 2025-07-23 | 2025-07-23 |  |  | NO | YES | FILALIZED | [8 empty] | Add Kotputli Bye Pass Road Bansur PO amp; PS Bansur Dist Alwar 301402 |  |  |  | PRAYASH CHOUDHARY | 9050478771 | KULDEEP SAINI | 7073068883 | UPENDRA SINGH | 8000501241 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 1 | 2 | 1 | 5 | 2 | 0 | 157 | 19040 | 16040 |  |  | 5805
I-RJ-CHMU-ENB-G005 | 0/2 | 2 | 850-SB | Chomu | Jaipur-1 | Rohit & team |  | Done | 27.2042 | 75.6813 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 6 | 2025-07-18 | 2025-07-19 | 2025-07-24 | 2025-07-24 | 2025-07-24 |  |  | NO | NO | NR | [8 empty] | Babu Lal Yadav s/o Chhotu Ram Yadav,Khasra No.665, Village & Post Lohawara, Tehsil-Chomu, Distt. Jaipur |  |  |  | Shankar Lal Yadav | 6350491475 | VACANT | VACANT | ANKIT KUMAWAT | 6377201203 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 72 | 6940 | 5440 |  |  | 1900
I-RJ-CHMU-ENB-G002 | 2 | 1 | 850-SB | Chomu | Jaipur-1 | Rohit & team |  | Done | 27.2381 | 75.5816 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 8 | 2025-07-22 | 2025-07-22 | 2025-07-24 | 2025-07-24 | 2025-07-24 |  |  | NO | NO | NR | [8 empty] | Sh. Harkchand Jain W/O Johari Lal, Vill & PO:- Aleesar, The:- Chomu, Dist:- Jaipur |  |  |  | MANISH KUMAR GURAVA | 6350491536 | HANSRAJ SONKARIA | 6350492188 | ANKIT KUMAWAT | 6377201203 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 78 | 5860 | 4360 |  |  | 1400
I-RJ-KOTA-ENB-G002 | 0/1/2 | 3 | PB ADDITION | Kota | Kota | Aneesh & team |  | Done | 25.2188 | 75.879 | RTT | 0 | PB ADDITIONA IN ALL SECTOR |  |  | Allotment- 7 | 2025-07-21 | 2025-07-22 | 2025-07-24 | 2025-07-24 | 2025-07-24 |  |  | NO | YES | FILALIZED | [8 empty] | Plot No. 1 , Guru Ramdas Niwas, Near Hotel Raj Kesar, Mala Road, Tehsil & Distt : Kota, Rajasthan. |  |  |  | Abdul Sattar | 6350491162 | BAWANIT KUMAR | 6350491635 | BANTI CHAUTHWANI | 6350491169 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 1 | 2 | 1 | 5 | 2 | 0 | 283 | 21560 | 18560 |  |  | 5805
I-RJ-DUDU-ENB-G002 | 1 | 1 | 850-SB | Chomu | Jaipur-1 | Rajkumar & team |  | Done | 26.8573 | 75.4014 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 9 | 2025-07-23 | 2025-07-23 | 2025-07-25 | 2025-07-25 | 2025-07-25 |  |  | NO | NO | NR | [12 empty] | Shankar Lal Jat | 6350491477 | GANESH LAL YADAV | 6350401079 | ANKIT KUMAWAT | 6377201203 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 15 | 4600 | 3100 |  |  | 1400
I-RJ-LXMG-ENB-G001 | 2 | 1 | 850-SB | Fatehpur | Sikar | Rohit & team |  | Done | 27.6872 | 74.953 | #N/A | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 9 | 2025-07-23 | 2025-07-23 | 2025-07-25 | 2025-07-25 | 2025-07-25 |  |  | NO | NO | NR | [12 empty] | MANPHOOL KHYALIA | 6350491071 | MANOJ KUMAR | 6376917742 | INDRAJ SARAN | 8107587670 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 148 | 7260 | 5760 |  |  | 1400
I-RJ-PHLE-ENB-G004 | 0/1/2 | 3 | 850-SB | Chomu | Jaipur-1 | Rajkumar & team |  | Done | 27.0333 | 75.4596 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 8 | 2025-07-22 | 2025-07-22 | 2025-07-25 | 2025-07-25 | 2025-07-25 |  |  | NO | NO | NR | [8 empty] | Prahalad Sahay Meena s/o Bheru Ram Meena, Khasra No.118/4,Village & Post Hingoniya, Tehsil Phulera, Distt Jaipur |  |  |  | MANOJ YADAV | 6350491151 | RAJU KUMAWAT | 6350491006 | ANKIT KUMAWAT | 6377201203 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 2 | 0 | 35 | 7400 | 5900 |  |  | 2600
I-RJ-BDSR-ENB-G001 | 0/2 | 2 | 850-SB | Sujangarh | Sikar | Rohit & team |  | Done | 27.8384 | 74.3212 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 9 | 2025-07-23 | 2025-07-23 | 2025-07-25 | 2025-07-25 | 2025-07-25 |  |  | NO | NO | NR | [12 empty] | kurda ram khileri | 6350491101 | JAGDISH PRAJAPAT | 6350491291 | Kana Ram | 6350491095 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 196 | 9420 | 7920 |  |  | 1900
I-RJ-CHRW-ENB-G001 | 2 | 1 | 850-SB | Jhunjhunun | Sikar | Rohit & team |  | Done | 28.3058 | 75.6309 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 9 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-26 |  |  | NO | NO | NR | [12 empty] | Jai Prakash | 6350491091 | RAM SINGH | 8741052127 | NARESH KUMAR | 6350491520 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 220 | 8700 | 7200 |  |  | 1400
I-RJ-ALWR-ENB-G001 | 1 | 1 | ANT ALARM RECTIFICATION | Alwar | Alwar | Rajkumar & team |  | Done | 27.6718 | 76.664 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 11 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-26 | 2025-07-26 |  |  | NO | YES | FILALIZED | [21 empty] | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 206 | 11920 | 8920 |  |  | 1900
I-RJ-KOTA-ENB-G001 | 0/1/2 | 3 | PB ADDITION | Kota | Kota | Aneesh & team |  | Done | 25.1449 | 75.8239 | RTT | 0 | PB ADDITIONA IN ALL SECTOR |  |  | Allotment- 10 | 2025-07-24 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-26 |  |  | NO | YES | FILALIZED | [8 empty] | Near thakur hospital,teen bati circle,Sri nathpuram,Kota(Raj.) | [12 empty] | JLKD | JLKD |  |  |  | 1 | 0 | 1 | 2 | 1 | 5 | 2 | 0 | 290 | 21700 | 18700 |  |  | 5805
I-RJ-RJGR-ENB-G008 | 0 | 1 | 850-SB | Sardarshahar | Sikar | Rohit & team |  | Done | 28.5668 | 75.4957 | #N/A | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 9 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-26 |  |  | NO | NO | NR | [12 empty] | SUSHIL SINGH | 9509619862 | GORAV JANGIR | 7877146736 | RAVINDER KUMAR | 6350616703 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 244 | 9180 | 7680 |  |  | 1400
I-RJ-DUSA-ENB-G001 | 0/1 | 2 | 850-SB | Dausa | Jaipur-1 | Rajkumar & team |  | Done | 27.0128 | 76.4257 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 9 | 2025-07-23 | 2025-07-23 | 2025-07-26 | 2025-07-26 | 2025-07-26 |  |  | NO | NO | NR | [12 empty] | MAHENDRA KUMAR BAIRWA | 6377201229 | Neela Ram Bairwa | 6376917723 | SANDEEP | 9929558672 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 108 | 7660 | 6160 |  |  | 1900
I-RJ-LLST-ENB-G001 | 2 | 1 | 850-SB | Dausa | Jaipur-1 | Rajkumar & team |  | Done | 26.5699 | 76.2692 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 10 | 2025-07-24 | 2025-07-24 | 2025-07-26 | 2025-07-26 | 2025-07-26 |  |  | NO | NO | NR | [8 empty] | Mool Chand Ji Meena S/o Bohri Lal ji Meena, Vill & PO:- Nirjharna, Tehsil:- Lalsot, Dist:- Dausa | [12 empty] | JLCD | JLCD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 107 | 6440 | 4940 |  |  | 1400
I-RJ-JARR-ENB-G001 | 2 | 1 | 850-SB | Chomu | Jaipur-1 | Rajkumar & team |  | Done | 26.9014 | 76.0943 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 10 | 2025-07-24 | 2025-07-24 | 2025-07-27 | 2025-07-27 | 2025-07-27 |  |  | NO | NO | NR | [8 empty] | Mohan Kanwar, Vill & Post Chawandiya, Tehsil- Jamwa Ram Garh, Distt Jaipur | [12 empty] | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 75 | 5800 | 4300 |  |  | 1400
I-RJ-JDPR-ENB-G003 | 0/1/2 | 3 | PB ADDITION | Jodhpur | Jodhpur | Nitesh & Team |  | Done | 26.2591 | 72.9733 | RTT | 0 | PB ADDITIONA IN ALL SECTOR |  |  | Allotment- 12 | 2025-07-25 | 2025-07-25 | 2025-07-27 | 2025-07-27 | 2025-07-27 |  |  | NO | YES | FILALIZED | [21 empty] | JLJH | JLJH |  |  |  | 1 | 0 | 1 | 2 | 1 | 5 | 2 | 0 | 20 | 16300 | 13300 |  |  | 5805
I-RJ-JDPR-ENB-G002 | 0/1/2 | 3 | PB ADDITION | Jodhpur | Jodhpur | Nitesh & Team |  | Done | 26.2714 | 72.9906 | RTT | 0 | PB ADDITIONA IN ALL SECTOR |  |  | Allotment- 12 | 2025-07-25 | 2025-07-25 | 2025-07-28 | 2025-07-28 | 2025-07-28 |  |  | NO | YES | FILALIZED | [21 empty] | JLJH | JLJH |  |  |  | 1 | 0 | 1 | 2 | 1 | 5 | 2 | 0 | 21 | 16320 | 13320 |  |  | 5805
I-RJ-JDPR-ENB-G006 | 0/1/2 | 3 | PB ADDITION | Jodhpur | Jodhpur | Nitesh & Team |  | Done | 26.2944 | 73.0271 | RTT | 0 | PB ADDITIONA IN ALL SECTOR |  |  | Allotment- 10 | 2025-07-24 | 2025-07-25 | 2025-07-29 | 2025-07-29 | 2025-07-29 |  |  | NO | YES | FILALIZED | [8 empty] | Nisar Mohammad S/o Late Shri Hazi Mohammad, " Hajan Fatma Plaza", Near Sagar Enterprises, Hathi Ram Ka Oda, Jodhpur, Rajasthan. | [12 empty] | JLJH | JLJH |  |  |  | 1 | 0 | 1 | 2 | 1 | 5 | 2 | 0 | 21 | 16320 | 13320 |  |  | 5805
I-RJ-JDPR-ENB-0353 | 1 | 1 | BSA REMOVAL | Jodhpur | Jodhpur | Nitesh & Team |  | Done | 26.2452 | 72.9504 | GBM | 0 | BSA NEED TO REMOVAL IN PLANNED SECTOR |  |  | Allotment- 5 | 2025-07-05 | 2025-07-09 | 2025-07-29 | 2025-07-29 | 2025-07-29 |  |  | NO | YES | FILALIZED | [8 empty] | On road diveder, Opp Surya Sweet home, Dali Bai Mandir road, Chaupasni, Jodhpur |  |  |  | PRAMOD SINGH | 9024256143 | VIKRAM KUMAR | 7240160569 | Mahendra Kumar Borana | 6350492267 |  |  |  | JLJH |  |  |  |  | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 20 | 5400 | 2400 |  |  | 1400
I-RJ-DUDU-ENB-G002 | 1 | 1 | ANT ALARM RECTIFICATION | Chomu | Jaipur-1 | Aneesh & team |  | Done | 26.8573 | 75.4014 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 14 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 | 2025-07-29 |  |  | NO | YES | FILALIZED | [12 empty] | Shankar Lal Jat | 6350491477 | GANESH LAL YADAV | 6350401079 | ANKIT KUMAWAT | 6377201203 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 17 | 8140 | 5140 |  |  | 1900
I-RJ-RJGR-ENB-G008 | 1 | 1 | ANT ALARM RECTIFICATION | Sardarshahar | Sikar | Aneesh & team |  | Done | 28.5668 | 75.4957 | #N/A | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 13 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-30 | 2025-07-30 |  |  | NO | YES | FILALIZED | [21 empty] | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 244 | 12680 | 9680 |  |  | 1900
I-RJ-LXMG-ENB-G001 | 2 | 1 | ANT ALARM RECTIFICATION | Fatehpur | Sikar | Aneesh & team |  | Done | 27.6872 | 74.953 | #N/A | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 14 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-07-31 |  |  | NO | YES | FILALIZED | [12 empty] | MANPHOOL KHYALIA | 6350491071 | MANOJ KUMAR | 6376917742 | INDRAJ SARAN | 8107587670 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 148 | 10760 | 7760 |  |  | 1900
I-RJ-LXMG-ENB-G001 | 2 | 1 | ANT ALARM RECTIFICATION | Fatehpur | Sikar | Aneesh & team |  | Done | 27.6872 | 74.953 | #N/A | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 15 | 2025-08-04 | 2025-08-05 | 2025-08-05 | 2025-08-05 | 2025-08-05 |  |  | NO | YES | FILALIZED | [12 empty] | MANPHOOL KHYALIA | 6350491071 | MANOJ KUMAR | 6376917742 | INDRAJ SARAN | 8107587670 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 148 | 10760 | 7760 |  |  | 2000
I-RJ-KPSN-ENB-V005 | 0/1/2 | 3 | PB ADDITION | Nimbahera | Bhilwara | Nitesh & Team |  | Done | 24.8867 | 74.3122 | GBT | 0 | PB ADDITIONA IN ALL SECTOR |  |  | Allotment- 8 | 2025-07-22 | 2025-07-22 | 2025-08-06 | 2025-08-06 | 2025-08-06 |  |  | NO | YES | FILALIZED | [8 empty] | SMT.GEETA DEVI W/O.LATE RAMJASJI,CHASTON KA CHOWK, |  |  |  | GORI SHANKAR MEENA | 6350491033 | RATAN LAL MALI | 9351228573 | AJRUDEEN KHAN | 9328683315 |  |  |  | JLJH | JLJH |  |  |  | 1 | 0 | 1 | 2 | 1 | 3 | 2 | 0 | 244 | 18780 | 15780 |  |  | 5805
I-RJ-SHRB-ENB-G001 | 1/2 | 2 | 850-SB | Jodhpur | Jodhpur | Nitesh & Team |  | Done | 26.599 | 72.3002 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-11 | 2025-08-11 |  |  | NO | NO | NR | [8 empty] | Phusa Ram S/o Rana Ram, Khasra No. 1851, Vpo - Setrawa, Tehsil - Shergarh, Distt.- Jodhpur |  |  |  | CHAILU SINGH | 9549723470 | JETHU SINGH | 9602943186 | VACANT | VACANT |  |  |  | Jodhpur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 117 | 7840 | 6340 |  |  | 1900
I-RJ-PHLS-ENB-G001 | 2 | 1 | 850-SB | Jodhpur | Jodhpur | Nitesh & Team |  | Done | 27.065 | 72.3146 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-11 | 2025-08-11 |  |  | NO | NO | NR | [8 empty] | Govind Ram Paliwal s/o Khem Chand, Khasra No. 134, 136, 503, 505,Village & Post Mokhari,Tehsil Phalodi, Distt Jodhpur |  |  |  | Shripal Singh Rathore | 6350492166 | RUPA RAM | 8209461426 | ALAUDDIN ANSARI | 9329513418 |  |  |  | Jodhpur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 167 | 7640 | 6140 |  |  | 1400
I-RJ-OSNN-ENB-G005 | 0/1 | 2 | 850-SB | Jodhpur | Jodhpur | Nitesh & Team |  | Done | 26.9605 | 72.8758 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-11 | 2025-08-11 | 2025-08-11 |  |  | NO | NO | NR | [8 empty] | Chhotu Singh s/o Purakh Singh, Khasra No. 62,Village & Post Motora, Osian, Distt. Jodhpur |  |  |  | DHIRENDRA SINGH | 6350492250 | ARJUN RAM | 6350492169 | ALAUDDIN ANSARI | 9329513418 |  |  |  | Jodhpur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 111 | 7720 | 6220 |  |  | 1900
I-RJ-PASS-ENB-G001 | 1 | 1 | 850-SB | Makrana | Nagaur | Nitesh & Team |  | Done | 26.9063 | 74.5946 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  |  | NO | NO | NR | [8 empty] | Mahesh Pal Singh s/o Dilip Singh, Village & Post-Badu Gadh, Tehsil- Parbatsar, Distt.- Nagour. Pin Code-341501 |  |  |  | MANEESH PRAJAPAT | 6350431983 | Girwar Singh | 6350491970 | RAJENDRA SINGH RATHORE | 6350491813 |  |  |  | Jodhpur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 215 | 8600 | 7100 |  |  | 1400
I-RJ-NAWW-ENB-G004 | 2 | 1 | 850-SB | Makrana | Nagaur | Nitesh & Team |  | Done | 27.2312 | 74.9832 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  |  | NO | NO | NR | [8 empty] | Narayan Singh s/o Late Hari Singh, Village & Post Kukanwali, TehsilNawa, Distt. Nagour |  |  |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 |  |  |  | Jodhpur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 287 | 10040 | 8540 |  |  | 1400
I-RJ-DUDU-ENB-G003 | 0 | 1 | 850-SB | Chomu | Jaipur-1 | Aneesh & team |  | Done | 26.7233 | 75.4513 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  |  | NO | NO | NR | [8 empty] | Jagdish Chandra Shou s/o Ganga Ram,Village & Post Jhag, Tehsil Mojamabad, Distt. Jaipur |  |  |  | Shankar Lal Jat | 6350491477 | GANESH LAL YADAV | 6350401079 | ANKIT KUMAWAT | 6377201203 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 16 | 4620 | 3120 |  |  | 1400
I-RJ-PHLE-ENB-G003 | 0/1 | 2 | 850-SB | Chomu | Jaipur-1 | Aneesh & team |  | Done | 26.8095 | 75.2879 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  |  | NO | NO | NR | [8 empty] | Lokendra Singh,Khasra No. 1142, Vill. & Post Akoda, Tehsil Phulera, Distt. Jaipur |  |  |  | BAJRANG LAL SHARMA | 6376599401 | GANESH LAL YADAV | 6350401079 | ANKIT KUMAWAT | 6377201203 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 24 | 5980 | 4480 |  |  | 1900
I-RJ-KSGR-ENB-G002 | 0 | 1 | 850-SB | Kishangarh | Ajmer | Nitesh & Team |  | Done | 26.7726 | 74.91 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-13 | 2025-08-13 | 2025-08-13 |  |  | NO | NO | NR | [8 empty] | Chhitar Jat s/o Gopal Jat, Khsara No. 472, Village & Post Thyod, Tesil- Kishangarh, Distt. Ajmer.Pin Code- 305814. |  |  |  | KAILASH CHAND RAIGER | 7014767214 | RAVIRAJ MEGHWAL | 9783998177 | MAHESH KUMAR | 6376917834 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 65 | 5600 | 4100 |  |  | 1400
I-RJ-KSGR-ENB-G001 | 0/2 | 2 | 850-SB | Kishangarh | Ajmer | Nitesh & Team |  | Done | 26.6832 | 74.86 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-13 | 2025-08-13 | 2025-08-13 |  |  | NO | NO | NR | [8 empty] | Bhag Chand Joshi, Vill &ampPost Ralawata, Tehsil Kishangarh, Distt. Ajmer |  |  |  | KAILASH CHAND RAIGER | 7014767214 | RAVIRAJ MEGHWAL | 9783998177 | MAHESH KUMAR | 6376917834 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 78 | 7060 | 5560 |  |  | 1900
I-RJ-AJMR-ENB-G001 | 0/1 | 2 | 850-SB | Ajmer | Ajmer | Nitesh & Team |  | Done | 26.3719 | 74.5084 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-13 | 2025-08-13 | 2025-08-13 |  |  | NO | NO | NR | [8 empty] | Smt. Lad Kanwar w/o Lt. Gishu Singh, Khasra No. 783,Khatta No. 7, Village & Post Bhawata, Teh.& Dt. Ajmer |  |  |  | Rakesh Paroda | 6350491793 | MOHAN SINGH | 9568428114 | MUKESH PRAJAPAT | 9001117533 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 122 | 7940 | 6440 |  |  | 1900
I-RJ-CHMU-ENB-6001 | 0/2 | 2 | 850-SB | Chomu | Jaipur-1 | Aneesh & team |  | Done | 27.1359 | 75.8039 | GBT_Rcom | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-13 | 2025-08-13 | 2025-08-13 |  |  | NO | NO | NR | [8 empty] | WARD NO-8, MEENA MOHALLA, VILLAGE and POST CHEETHWARI VIA MORIJA, TEHSIL CHOMU, DISTRICT JAIPUR-303805 |  |  |  | BALRAM YADAV | 6350491473 | HANSRAJ SONKARIA | 6350492188 | ANKIT KUMAWAT | 6377201203 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 75 | 7000 | 5500 |  |  | 1900
I-RJ-CHMU-ENB-G003 | 0/1 | 2 | 850-SB | Chomu | Jaipur-1 | Aneesh & team |  | Done | 27.2037 | 75.7585 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-13 | 2025-08-13 | 2025-08-13 |  |  | NO | NO | NR | [8 empty] | Kesar Lal & Lal Chand S/o Sh. Nanag Ram,Vill. & Po.:- Hathnoda, Tehsil :- Chomu,Distt. :- Jaipur, Rajasthan. |  |  |  | BALRAM YADAV | 6350491473 | HANSRAJ SONKARIA | 6350492188 | ANKIT KUMAWAT | 6377201203 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 70 | 6900 | 5400 |  |  | 1900
I-RJ-PISN-ENB-G002 | 1/2 | 2 | 850-SB | Beawar | Ajmer | Sunil Outsource |  | Done | 26.3934 | 74.3817 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-14 | 2025-08-14 | 2025-08-14 |  |  | NO | NO | NR | [8 empty] | Tej Singh Chouhan s/o Late Laxman Singh,Khasra No. 440/4781, Village & Post- Pisagan, Tehsil - Pisagan, Distt. Ajmer. Pin Code -305204 |  |  |  | SORAV SINGH | 8209449242 | SUNIL CHOUHAN | 7014399733 | MUKESH PRAJAPAT | 9001117533 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 144 | 8380 | 6880 |  |  | 1900
I-RJ-NMTH-ENB-G001 | 1/2 | 2 | 850-SB | Sikar | Sikar | Aneesh & team |  | Done | 27.5918 | 75.7506 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-13 | 2025-08-13 | 2025-08-13 |  |  | NO | NO | NR | [8 empty] | Madan lal Sharma s/o Beenj Raj Sharma, Khasra No. 2017/1,Village & Post Preetampuri, Tehsil Neem Ka Thana , Distt. Sikar |  |  |  | RATAN YADAV | 6350491008 | SURESH KUMAR | 9509617549 | SITARAM SAINI | 6377201162 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 120 | 7900 | 6400 |  |  | 1900
I-RJ-CHRW-ENB-G003 | 0 | 1 | 850-SB | Jhunjhunun | Sikar | Aneesh & team |  | Done | 28.204 | 75.5553 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-14 | 2025-08-14 | 2025-08-14 |  |  | NO | NO | NR | [8 empty] | Ramswaroop Singh s/o Chatar Singh,Khsra No. 179, Village & Post Bakhtawarpura, Tehsil Chirawa, Distt. Jhunjhunu |  |  |  | PANKAJ KUMAR | 6376917714 | JITENDRA SINGH | 6350491586 | NARESH KUMAR | 6350491520 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 203 | 8360 | 6860 |  |  | 1400
I-RJ-SDAR-ENB-G001 | 2 | 1 | 850-SB | Sardarshahar | Sikar | Aneesh & team |  | Done | 28.5047 | 74.7342 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-14 | 2025-08-14 | 2025-08-14 |  |  | NO | NO | NR | [8 empty] | Smt. Sita Devi w/o Late Laxmi Narayan @ Soda ram, Village & Post Melusar, Tehsil Sardarshahar, Distt. Churu |  |  |  | SITA RAM | 6350491104 | RAMNIWAS GIRI | 6350491513 | RAVINDER KUMAR | 6350616703 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 254 | 9380 | 7880 |  |  | 1400
I-RJ-SARH-ENB-G001 | 0 | 1 | 850-SB | Bhilwara | Bhilwara | Nitesh & Team |  | Done | 25.1636 | 74.3433 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-14 | 2025-08-14 | 2025-08-14 |  |  | NO | NO | NR | [8 empty] | Smt. Santi devi Sharma, c/o Gopal lal S/O late Mohan lal ji Sharma,Khasara no.1818, khatta no.390, vpo soniyana, Tehsil Sarlda, Distt-Bhilwara |  |  |  | RAMCHANDRA CHOUDHARY | 6377397927 | RANJEET SINGH | 9588210853 | BHUPENDRA KUMAR SHARMA | 6375865962 |  |  |  | Jodhpur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 213 | 8560 | 7060 |  |  | 1400
I-RJ-VLLN-ENB-G001 | 2 | 1 | 850-SB | Udaipur | Udaipur | Nitesh & Team |  | Done | 24.6439 | 74.0984 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-14 | 2025-08-14 | 2025-08-14 |  |  | NO | NO | NR | [8 empty] | Shankar Lal s/o Late Hukmi Chand, Khasra No. 1096,Village & Post- Rundera, Tehsil- Vallabh Nagar, Distt.- Udaipur. |  |  |  | SOHAN SALVI | 6350491418 | VACANT | VACANT | NEMI CHAND | 6350492247 |  |  |  | Jodhpur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 272 | 9740 | 8240 |  |  | 1400
I-RJ-MPUR-ENB-G003 | 0 | 1 | 850-SB | Tonk | Ajmer | Nitesh & Team |  | Done | 26.4006 | 75.504 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-16 | 2025-08-16 | 2025-08-16 |  |  | NO | NO | NR | [8 empty] | Bhawani Ram Sharma s/o Ramnarayan, Khasra No.2153/1,Village & Post Soda, Tehsil Malpura, Distt. Tonk |  |  |  | SATYANARAYAN SINGH | 7665666391 | MOHAN LAL JANGID | 9783024898 | VACANT | VACANT |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 70 | 5700 | 4200 |  |  | 1400
I-RJ-KESR-ENB-I004 | 0/1/2 | 1 | Ant Alarm Rectification | Nagaur | Nagaur | Nitesh & Team |  | Done | 27.14 | 73.1929 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 18 | 2025-08-19 | 2025-08-19 | 2025-08-22 | 2025-08-22 | 2025-08-22 |  |  | NO | YES | FILALIZED | [8 empty] | Smt. Deepa devi w/o Sh. Joga ram, Kh. No. 1731, V- Bhomasar Post- Karnau, TH- Khinvsar, Distt- Nagaur |  |  |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 |  |  |  | JLJH | JLJH |  |  |  | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 144 | 10680 | 7680 |  |  | 2000
I-RJ-SRGR-ENB-G001 | 0/2 | 2 | 850-SB | Suratgarh | Ganganagar | Aneesh & team |  | Done | 29.4489 | 73.8772 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 19 | 2025-08-20 | 2025-08-21 | 2025-08-23 | 2025-08-23 | 2025-08-23 |  |  | NO | NO | NR | [8 empty] | Dungar Ram S/o Dhanna Ram,Vill & Po : Mogra Kalan, Tehsil : Luni, Distt : Jodhpur . Rajasthan |  |  |  | Deepak Sharma | 8078698950 | VAKIL KUMAR | 8078698892 | RAJA RAM | 8003992944 |  |  |  | JLJH | JLJH |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 432 | 14140 | 12640 |  |  | 1900
I-RJ-CHKU-ENB-G001 | 1 | 1 | 850-SB | Chomu | Jaipur-1 | Dileep & team |  | Done | 26.6597 | 75.8321 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-25 | 2025-08-25 | 2025-08-25 |  |  | NO | NO | NR | [8 empty] | Jagdish Prasad & Ram Prasad, Khasra No. 1353,Vill & Post Tatiriya, Tehsil- Chaksu, Distt- Jaipur |  |  |  | ROHIT SINGH SOLANKEY | 6350491546 | MUKESH KUMAR SHARMA | 9660411505 | ANKIT KUMAWAT | 6377201203 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 67 | 5640 | 4140 |  |  | 1400
I-RJ-LLST-ENB-H001 | 0 | 1 | Ant Alarm Rectification | Dausa | Jaipur-1 | Rajkumar & team |  | Done | 26.4933 | 76.4059 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 20 | 2025-08-22 | 2025-08-22 | 2025-08-25 | 2025-08-25 | 2025-08-25 |  |  | NO | YES | FILALIZED | [8 empty] | Sh. Rameshwar sharma s/o Sh. Kashi ram Kh. No. 149, V/P Suratpura, TH. Lalsot, Distt. Dausa |  |  |  | LOKESH KUMAR MEENA | 6350491476 | NATVAR SINGH | 9351228567 | MANOJ KUMAR SHARMA | 6350491496 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 125 | 10300 | 7300 |  |  | 2000
I-RJ-SIKR-ENB-G005 | 2 | 1 | 850-SB | Sikar | Sikar | Aneesh & team |  | Done | 27.4781 | 75.0888 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 17 | 2025-08-19 | 2025-08-19 | 2025-08-25 | 2025-08-25 | 2025-08-25 |  |  | NO | NO | NR | [21 empty] | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 106 | 6420 | 4920 |  |  | 1400
I-RJ-LXMK-ENB-G003 | 2 | 1 | 850-SB | Alwar | Alwar | Rajkumar & team |  | Done | 27.4839 | 76.8675 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 17 | 2025-08-19 | 2025-08-19 | 2025-08-25 | 2025-08-25 | 2025-08-25 |  |  | NO | NO | NR | [21 empty] | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 187 | 8040 | 6540 |  |  | 1400
I-RJ-SEPU-ENB-I005 | 1 | 1 | 850-SB | Dhaulpur | Bharatpur | Bharat Outsource |  | Done | 26.904 | 77.7403 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | 2025-08-26 | 2025-08-26 | 2025-08-26 |  |  | NO | NO | NR | [8 empty] | Smt Jamvati w/o Sh Radhe Shyam, Khasra No 1083, Village Maloni Panwar, Th Sepau, Dist Dholpur |  |  |  | NEERAJ KUMAR | 6376917704 | SONU RAJPOOT | 7240543005 | SHRI BHAGWAN | 6350491348 |  |  |  | Jaipur |  |  |  |  | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 299 | 10280 | 8780 |  |  | 1400
I-RJ-JARR-ENB-G001 | 2 | 1 | ANT ALARM RECTIFICATION | Chomu | Jaipur-1 | Dileep & team |  | Done | 26.9014 | 76.0943 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 22 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-29 | 2025-08-29 |  |  | NO | YES | FILALIZED | [8 empty] | Mohan Kanwar, Vill & Post Chawandiya, Tehsil- Jamwa Ram Garh, Distt Jaipur | [12 empty] | JLKD | JLKD | [16 empty] | 2000
I-RJ-RJGR-ENB-G008 | 1 | 1 | ANT ALARM RECTIFICATION | Sardarshahar | Sikar | Rajkumar & team |  | Done | 28.5668 | 75.4957 | #N/A | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 22 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-29 | 2025-08-29 |  |  | NO | YES | FILALIZED | [21 empty] | JLKD | JLKD | [16 empty] | 2000
I-RJ-MSUD-ENB-9027 | 0/1/2 |  | BAND ADDITION-850 |  | Udaipur | Rohit & team |  | Done | 24.3531 | 72.423 |  |  | ONLY 3 RRH OF 850 BAND NEED TO INSTALL WITH POWER CPRI |  |  | Allotment- 21 | 2025-08-27 | 2025-08-28 | 2025-08-30 | 2025-08-30 | 2025-08-30 |  | No-Dismantle | NO | NO | NR | [21 empty] | JLJH | JLJH | [16 empty] | 1500
I-RJ-MNAB-ENB-B001 | 0/1/2 | 3 | BAND ADDITION-1800/850 |  | Udaipur | Rohit & team |  | Done | 24.3515 | 72.4238 |  |  | PB ADDITION IN ALL 3 SECTOR & SB 2300 DISMANTLING, 1800 & 850 BAND RRH NEED TO INSTALL WITH POWER CPRI/CDU-RDU SWAP ALSO |  |  | Allotment- 21 | 2025-08-27 | 2025-08-28 | 2025-09-03 | 2025-09-03 | 2025-09-03 |  | 2300-SB—3+ 1 CDU +L9CAB4R+L9CAB4 | NO | YES | FINALIZED | [21 empty] | JLJH | JLJH | [16 empty] | 4500
I-RJ-ABRD-ENB-9017 | 0/1/2 | 3 | BAND ADDITION-850/SEC ADD-2300/1800 |  | Udaipur | Rohit & team |  | Done | 24.3859 | 72.4637 |  |  | PB INSTALLATION IN ALL 3 SEC, MB SB DISMANTLING IN 2 SEC, 3 RRH 850 BAND 1,1 RRH 2300/1800 BAND NEED TO ADD WITH POWER CPRI |  |  | Allotment- 21 | 2025-08-27 | 2025-08-28 | 2025-08-31 | 2025-09-01 | 2025-09-01 |  | MB--2 | NO | YES | FINALIZED | [21 empty] | JLJH | JLJH | [16 empty] | 4000
I-RJ-RJGR-ENB-9056 | 0 | 1 | 850-SB | Sardarshahar | Sikar |  |  | MRN Done | 28.5968 | 75.4641 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 16 | 2025-08-08 | 2025-08-09 | [5 empty] | NO | NO | NR | [8 empty] | Vijay Kumar, Kandhran, Rajgarh |  |  |  | SUSHIL SINGH | 9509619862 | GORAV JANGIR | 7877146736 | RAVINDER KUMAR | 6350616703 |  |  |  | Jaipur |  |  |  |  | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 275 | 8500 | 5500 |  |  | 1400
I-RJ-UDPR-ENB-9071 | 0 | 1 | ANT ALARM RECTIFICATION | Udaipur | Udaipur | Rohit & team |  | Done | 24.7772 | 73.6251 | GBT |  | Faulty SB REPLACEMENT |  |  | Allotment- 23 | 2025-08-30 | 2025-09-02 | 2025-09-04 | 2025-09-04 | 2025-09-04 |  |  | NO | YES | FILALIZED | [21 empty] | JLJH | JLJH | [16 empty] | 2000
I-RJ-RJGH-ENB-9052 | 1 | 1 | ANT ALARM RECTIFICATION | Alwar | Alwar | Aneesh & team |  | Done | 27.2916 | 76.643 | GBT |  | Faulty SB REPLACEMENT |  |  | Allotment- 24 | 2025-09-04 | 2025-09-04 | 2025-09-05 | 2025-09-05 | 2025-09-05 |  |  | NO | YES | FILALIZED | [12 empty] | LOKESH JAT | 8740054275 | Om Prakash Ray | 6376914074 | GAJENDRA SINGH SHEKHAWAT | 8003390514 |  |  |  | JLKD | JLKD | [16 empty] | 2000
I-RJ-MNRL-ENB-I004 | 1 | 1 | ANT ALARM RECTIFICATION | Bharatpur | Bharatpur | Aneesh & team |  | Done | 26.3687 | 77.2156 | GBT |  | Faulty SB REPLACEMENT |  |  | Allotment- 23 | 2025-08-30 | 2025-09-02 | 2025-09-06 | 2025-09-06 | 2025-09-06 |  |  | NO | YES | FILALIZED | [21 empty] | JLKD | JLKD | [16 empty] | 2000
I-RJ-RJGR-ENB-G003 | 1 | 1 | 850-SB | Sardarshahar | Sikar | Rajkumar & team |  | Done | 28.563 | 75.4524 | GBT |  | ANTENNA NEED TO INSTALL IN 850 BSA RUNNING SECTOR |  |  | Allotment- 24 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-06 |  |  | NO | NO | NR | [8 empty] | Begraj s/o Late Fataram, Village & Post Harpalu, Tehsil Rajgarh, Distt. Choru |  |  |  | SUSHIL SINGH | 9509619862 | GORAV JANGIR | 7877146736 | RAVINDER KUMAR | 6350616703 |  |  |  | JLKD | JLKD | [16 empty] | 1400
I-RJ-SIKR-ENB-G001 | 0/1/2 | 3 | PB ADDITION | Sikar | Sikar | Dileep & team |  | Done | 27.6164 | 75.148 | RTT |  | PB INSTALLATION & ONLY MB SB DISNAMTLING REQUIRED IN ALL 3 SECTOR |  |  | Allotment- 24 | 2025-09-04 | 2025-09-04 | 2025-09-06 | 2025-09-06 | 2025-09-06 |  |  | NO | YES | PENDING | [8 empty] | Near Doctor Satish Kapoor, Naykan Mohalla, Ward No. 07, Sikar, Rajasthan. |  |  |  | ANIL KUMAR SAINI | 6350491570 | RUPESH NARWAL | 9116104176 | INDRAJ SARAN | 8107587670 |  |  |  | JLKD | JLKD | [16 empty] | 5805
I-RJ-KESR-ENB-I004 | 2 | 1 | Ant Alarm Rectification | Nagaur | Nagaur | Rohit & team |  | Done | 27.14 | 73.1929 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 25 | 2025-09-05 | 2025-09-05 | 2025-09-06 | 2025-09-06 | 2025-09-06 |  |  | NO | YES | FILALIZED | [8 empty] | Smt. Deepa devi w/o Sh. Joga ram, Kh. No. 1731, V- Bhomasar Post- Karnau, TH- Khinvsar, Distt- Nagaur |  |  |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 |  |  |  | JLJH | JLJH | [16 empty] | 2000
I-RJ-MAJN-ENB-G001 | 0 | 1 | 850-SB | Pali | Sirohi | Rohit & team |  | Done | 25.7623 | 73.7445 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 26 | 2025-09-10 | 2025-09-10 | 2025-09-11 | 2025-09-11 | 2025-09-11 |  |  | NO | NO | NR | [8 empty] | Gram Panchayat Manda Through Sarpanch, Khasra No. 414, Vpo- Manda, Tehsil- Marwar Jn., Distt.- Pali |  |  |  | Om Prakash | 9672320287 | BHAWANI SINGH | 9799650934 | VACANT | VACANT |  |  |  | JLJH | JLJH | [16 empty] | 1400
I-RJ-REAR-ENB-G001 | 0/1 | 2 | 850-SB | Sirohi | Sirohi | Rohit & team |  | Done | 24.5555 | 72.3898 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 26 | 2025-09-10 | 2025-09-10 | 2025-09-14 | 2025-09-14 | 2025-09-14 |  |  | NO | NO | NR | [8 empty] | Smt. Savita Devi w/o Ramesh Kumar, Village & Post- Mandar, Tehsil-Reodar, Distt.- Sirohi. Pin Code- 307027 |  |  |  | RAM PRASAD | 8445012382 | LAKHAMA RAM | 9461211477 | LAKSHYADEEP SINGH GEHLOT | 7014119394 |  |  |  | JLJH | JLJH | [16 empty] | 1900
I-RJ-HMGR-ENB-G001 | 0/1/2 | 3 | PB ADDITION | Hanumangarh | Ganganagar | Aneesh & team |  | Done | 29.6143 | 74.2841 | GBT | 0 | PB INSTALLATION IN ALL 3 SEC, MB & SB DISMANTLING REQD |  |  | Allotment- 26 | 2025-09-10 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-13 |  |  | NO | YES | PENDING | [8 empty] | Ambedker Circle,Hotel 7/11 , Hanumangarh |  |  |  | DEEPAK KUMAR | 8078699524 | MANOHAR LAL | 9636396382 | AMIT KUMAR | 7597389705 |  |  |  | JLJH | JLJH | [16 empty] | 5805
I-RJ-MNRL-ENB-I004 | 1 | 1 | ANT ALARM RECTIFICATION | Bharatpur | Bharatpur | Yashwant & team |  | Done | 26.3687 | 77.2156 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 27 | 2025-09-13 | 2025-09-13 | 2025-09-19 | 2025-09-19 | 2025-09-19 |  |  | NO | YES | PENDING | [21 empty] | JLKD | JLKD | [16 empty] | 2000
I-RJ-SHRB-ENB-G003 | 1/2 | 2 | 850-SB | Jodhpur | Jodhpur | Rohit & team |  | Done | 26.656 | 72.5788 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 28 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-19 | 2025-09-19 |  |  | NO | NO | NR | [8 empty] | Smt. Pushpa Kanwar w/o Virender singh Bhati, Village & Post - Chamu, Tehsil - Sheargarh, Distt. - Jodhpur |  |  |  | DEVENDRA JOSHI | 8955001746 | Deva Ram | 6350492245 | VACANT | VACANT |  |  |  | JLJH | JLJH | [16 empty] | 1900
I-RJ-MNRL-ENB-6001 | 0/2 | 2 | ANT ALARM RECTIFICATION | Bharatpur | Bharatpur | Yashwant & team |  | Done | 26.3008 | 77.2436 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 27 | 2025-09-13 | 2025-09-13 | 2025-09-19 | 2025-09-19 | 2025-09-19 |  |  | NO | YES | PENDING | [21 empty] | JLKD | JLKD | [16 empty] | 2800
I-RJ-PRTN-ENB-G001 | 0/2 | 2 | 850-SB | Banswara | Udaipur | Rohit & team |  | Done | 24.0296 | 74.7871 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 28 | 2025-09-17 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-22 |  |  | NO | NO | NR | [8 empty] | Smt. Madhu Bala Bordiya w/o Surendra Kumar, Khasra No.1738 & 1739,Samta Talkies, M.G. Road, Pratapgarh Distt. Chhitorgarh |  |  |  | LABHCHAND MEENA | 8279249089 | AVDHESH SHARMA | 6377022903 | UDAY BHAN SINGH RANAWAT | 8114424610 |  |  |  | JLJH | JLJH | [16 empty] | 1900
I-RJ-RAGH-ENB-G001 | 0/1 | 2 | 850-SB | Alwar | Alwar | Yashwant & team |  | Done | 27.5894 | 76.8151 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 28 | 2025-09-17 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-22 |  |  | NO | NO | NR | [8 empty] | Kalu Ram s/o Jhabbu, Khasra No. 619, Village & Post Ramgarh, Tehsil Ramgarh, Distt. Alwar |  |  |  | NITESH KUMAR | 7891350167 | AARIF KHAN | 8440064725 | GAJENDRA SINGH SHEKHAWAT | 8003390514 |  |  |  | JLKD | JLKD | [16 empty] | 1900
I-RJ-BNSU-ENB-G001 | 1/2 | 2 | 850-SB | Alwar | Alwar | Yashwant & team |  | Done | 27.7099 | 76.4766 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 28 | 2025-09-17 | 2025-09-18 | 2025-09-22 | 2025-09-22 | 2025-09-22 |  |  | NO | NO | NR | [8 empty] | Murari Lal s/o Late Champa Lal & Shyam Sunder s/o Late Champa Lal, Khasra No. 1899,1900, Village & Post HameerPur, Tehsil Bansoor, Distt. Alwar |  |  |  | PRAYASH CHOUDHARY | 9050478771 | KULDEEP SAINI | 7073068883 | UPENDRA SINGH | 8000501241 |  |  |  | JLKD | JLKD | [16 empty] | 1900
I-RJ-KTPI-ENB-G002 | 1/2 | 2 | 850-SB | Chomu | Jaipur-1 | Yashwant & team |  | Done | 27.5817 | 76.0334 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 28 | 2025-09-17 | 2025-09-18 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [13 empty] | Kishan Singh & Virender Singh S/O Shri Mohan Singh, VPO.: Bhonawas, Tehsil : Kotputli, Distt.: Jaipur, Rajasthan. |  |  |  | VINOD KUMAR | 6350491725 | SATISH KUMAR YADAV | 6350491529 | MANOJ KUMAR SHARMA | 6350491496 |  |  |  | JLKD | JLKD | [16 empty] | 1900
I-RJ-SGNR-ENB-9051 | 1 | 1 | PB ADDITION | Mansarovar, Jaipur | Jaipur-2 | Yashwant & team |  | Done | 26.8609 | 75.7184 | GBM | 0 | PB ADDITIONA IN BETA & MB SB DISMANTLING |  |  | Allotment- 29 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-24 | 2025-09-24 | [13 empty] | On Road divider, Between of both side open land, Narayan Sagar, Narayan Vihar, Mansarovar Jaipur |  |  |  | LUXMAN SINGH | 7568299590 | SANJAY KUMAR SHARMA | 7023128330 | BUDHRAJ SINGH RAJAWAT | 9549688936 |  |  |  | JLKD | JLKD |  |  |  | 1 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 9500 |  |  |  | 3300
I-RJ-MSUD-ENB-G001 | 0/1 | 2 | 850-SB | Beawar | Ajmer | Rajkumar & team |  | Done | 25.9931 | 74.3909 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 28 | 2025-09-17 | 2025-09-18 | 2025-09-24 | 2025-09-24 | 2025-09-24 | [13 empty] | Prem Raj Jain, Khasra No. 107, Vill & post Ratanpura, Tehsil Masuda, District Ajmer |  |  |  | GOVIND JYOTISHI | 7891237598 | Pawan Kumar Sharma | 6350491834 | VACANT | VACANT |  |  |  | JLKD | JLKD | [16 empty] | 1900
I-RJ-SJGR-ENB-9101 | 2 | 1 | 850-SB | Sujangarh | Sikar | Yashwant & team |  | Done | 27.6084 | 74.2172 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 29 | 2025-09-22 | 2025-09-23 | 2025-09-26 | 2025-09-26 | 2025-09-26 | [13 empty] | Lichhman Singh S/O Mool Singh, Vill Jeeli, Th Bidasar, Churu |  |  |  | UPENDRA SINGH | 6377209966 | JAGDISH PRAJAPAT | 6350491291 | Kana Ram | 6350491095 |  |  |  | JLKD | JLKD | [16 empty] | 1400
I-RJ-MNGO-ENB-G001 | 1 | 1 | 850-SB | Baran | Kota | Bhuwnesh Outsource |  | Done | 25.242 | 76.502 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 28 | 2025-09-17 | 2025-09-18 | 2025-10-07 | 2025-10-07 | 2025-10-07 | [13 empty] | Badri Lal Nagar s/o Ram Charan, Village & Post Bohat, Tehsil Mangrol, Distt. Baran |  |  |  | NARENDERA PAL SINGH | 9131467549 | NARESH KUMAR | 6350491231 | SUSHEEL KUMAR PANDEY | 8078698882 |  |  |  | JLKD | JLKD
I-RJ-LKNR-ENB-I009 | 0/1 | 2 | ANT ALARM RECTIFICATION | Bikaner | Bikaner | Aneesh & team |  | Done | 28.5798 | 74.0618 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 30 | 2025-09-27 | 2025-09-29 | 2025-10-01 | 2025-10-01 | 2025-10-01 | [17 empty] | SUNIL KUMAR | 6350666491 | NARESH KUMHAR | 9928996703 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH | JLJH
I-RJ-LKNR-ENB-9003 | 2 | 1 | 850-SB | Bikaner | Bikaner | Aneesh & team |  | Done | 28.7455 | 74.1087 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 30 | 2025-09-27 | 2025-09-29 | 2025-10-01 | 2025-10-01 | 2025-10-01 | [13 empty] | V.P.O-Suin, Tehsil-Lunkaransar, Distt-Bikaner (Raj) |  |  |  | Chhagan Gar | 9783311644 | RAJESH BANJARA | 8078699594 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH | JLJH
I-RJ-DAVG-ENB-G001 | 1 | 1 | 850-SB | Dausa | Jaipur-1 | Aneesh & team |  | Done | 26.5944 | 76.3235 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 31 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [13 empty] | Surajmal s/o Ganpat, Khasra No.1746, Village & Post Didwana (Kelawas), Tehsil Lalsot, Distt. Dausa. |  |  |  | ANANDI LAL SHARMA | 6350491592 | ashish kumar meena | 7240171525 | MANOJ KUMAR SHARMA | 6350491496 |  |  |  | JLKD | JLKD
I-RJ-JPUR-ENB-G011 | 2 | 1 | 850-SB | Vaishali, Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9015 | 75.6207 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 31 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [13 empty] | Jai Singh, Fateh Singh, Roop Singh s/o Late Badri Dan & Smt. Mangej kanwar w/o Late Badri Dan & Balveer Singh s/o Raghuveer Singh, Khasra No.160/2, Village & Post Mudiya Ramsar, Tehsil & Distt. Jaipur |  |  |  | Mangi Lal Yadav | 8078699650 | HARIOM MALI | 9166257320 | KAMLESH SHARMA | 8078699590 |  |  |  | JLKD | JLKD
I-RJ-RAPU-ENB-G001 | 0/2 | 2 | 850-SB | Bhilwara | Bhilwara | Dileep & Team |  | Done | 25.4226 | 74.1419 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 31 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [13 empty] | Ratan Lal Soni s/o Late Mohan Lal Soni, Village & Post Borana, Tehsil Raipur, Distt. Bhilwara. Pin Code - 311001 |  |  |  | RAVI KUMAR DAROGA | 6376917127 | RAKESH KUMAR HARIJAN | 6350491040 | VACANT | VACANT |  |  |  | JLJH | JLJH
I-RJ-THZI-ENB-G001 | 1/2 | 2 | 850-SB | Alwar | Alwar | Aneesh & team |  | Done | 27.4715 | 76.312 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 31 | 2025-10-09 | 2025-10-10 | 2025-10-15 | 2025-10-15 | 2025-10-15 | [13 empty] | Sh. Brahmanand Sharma S/O Nathu Ram Sharma, Vill & PO:-basai jogiyan Tehsil:-Thanagazi, Dist:-Alwar |  |  |  | BHOOPENDRA KUMAR SHARMA | 9001765074 | HARIRAM GURJAR | 9672572514 | GAJENDRA SINGH SHEKHAWAT | 8003390514 |  |  |  | JLKD | JLKD
I-RJ-CHRW-ENB-G002 | 0/1 | 2 | 850-SB | Jhunjhunun | Sikar | Aneesh & team |  | Done | 28.3294 | 75.8013 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 31 | 2025-10-09 | 2025-10-10 | 2025-10-12 | 2025-10-12 | 2025-10-12 | [13 empty] | Pali Ram Jakotiya s/o Baijnath, Village & Post Jakhod, Tehsil Chirawa,Distt Jhunjhunu |  |  |  | KULDEEP POONIA | 6350491140 | SURENDRA SINGH | 6377209965 | NARESH KUMAR | 6350491520 |  |  |  | JLKD | JLKD
I-RJ-NAWW-ENB-G002 | 0/2 | 2 | 850-SB | Makrana | Nagaur | Satveer & Team |  | Done | 27.3456 | 75.0835 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 31 | 2025-10-09 | 2025-10-10 | 2025-11-14 | 2025-11-14 | 2025-11-14 | [13 empty] | Ramjan Khan, Khasra No.68, Vill & Post Lalas Tehsil, Nawa, Distt. Nagour |  |  |  | MANGEE LAL | 8078698924 | MAHENDRA BHAKHAR | 7023304750 | RAJENDRA SINGH RATHORE | 6350491813 |  |  |  | JLJH | JLJH
I-RJ-PRDS-ENB-G001 | 0 | 1 | 850-SB | Banswara | Udaipur | Rajkumar & Team |  | Done | 23.7 | 74.7778 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 31 | 2025-10-09 | 2025-10-10 | 2025-10-12 | 2025-10-12 | 2025-10-12 | [13 empty] | Khasara No.1426 / 848, VPO - Salamgarh, Tehsil - Pratapgarh, Distt.Chittorgarh (Raj.) |  |  |  | AKHLESHWAR JADAV | 7665691228 | VACANT | VACANT | UDAY BHAN SINGH RANAWAT | 8114424610 |  |  |  | JLJH | JLJH
I-RJ-BSRI-ENB-9006 | 0/1/2 | 3 | 850-SB | Dhaulpur | Bharatpur | Aneesh & team |  | Done | 26.552 | 77.4208 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 32 | 2025-10-11 | 2025-10-13 | 2025-10-14 | 2025-10-14 | 2025-10-14 | [13 empty] | Suman W/o Sh. Mukesh Kumar MeenaGram Baroli, The. Sarmathura, Distt. Dholpur |  |  |  | RAMVARAN GURJAR | 9784342340 | RAHUL KUMAR KUSHWAH | 8952802066 | SHRI BHAGWAN | 6350491348 |  |  |  | JLKD | JLKD
I-RJ-NGAR-ENB-G001 | 2 | 1 | 850-SB | Bharatpur | Bharatpur | Aneesh & team |  | Done | 27.4204 | 77.1041 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 32 | 2025-10-11 | 2025-10-28 | 2025-10-29 | 2025-10-29 | 2025-10-29 | [13 empty] | Dal Chand Soni s/o Late Kallu Ram Soni, In front of Old PNB, Nagar, Tehsil- Nagar, Distt.- Bharatpur. Pin Code- 321205. |  |  |  | GANGADHAR PAL | 7409674611 | YOGESH KUMAR SHARMA | 9828499702 | VACANT | VACANT |  |  |  | JLKD | JLKD
I-RJ-SNCE-ENB-9076 | 0/2 | 2 | 850-SB | Jalore | Sirohi | Dileep & team |  | Done | 24.8015 | 71.4866 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 32 | 2025-10-11 | 2025-10-11 | 2025-10-15 | 2025-10-15 | 2025-10-15 | [13 empty] | Jalim SIngh - (50*50) Villa-Khatrni, Chitanwada, Sanchor |  |  |  | JETMAL SINGH | 7014142932 | BHAGA RAM | 9024465772 | Sharwan Bhati | 6377202100 |  |  |  | JLJH | JLJH
I-RJ-JPUR-ENB-0001 | 0/1/2 | 3 | PB ADDITION | Jaipur - Mansarovar | Jaipur-2 | Aneesh & team |  | Done | 26.8301 | 75.8351 | GBM | 0 | PB INSTALLATION IN ALL 3 SEC, MB & SB DISMANTLING REQD |  |  | Allotment- 32 | 2025-10-11 | 2025-10-13 | 2025-10-15 | 2025-10-15 | 2025-10-15 | [13 empty] | Khasra No. 1, 2, 3, 3/163, 4, 24, 25, 26, 29, 30, 39, 40#160; Khata No. New 7, Old-7, Village- Bad Tilawala, Tehsil- Sanganer, District- Jaipur (Raj) |  |  |  | GHAMANDI LAL SAINI | 6350492235 | NAVEEN KUMAR SAINI | 9509627148 | SANTOSH SHARMA | 9251637621 |  |  |  | JLKD | JLKD
I-RJ-KESR-ENB-G001 | 0/2 | 2 | 850-SB | Nagaur | Nagaur | Aneesh & team |  | Done | 27.1176 | 73.4429 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 35 | 2025-10-31 | 2025-11-04 | 2025-11-06 | 2025-11-06 | 2025-11-06 | [13 empty] | Mana Ram s/o Late Joga Ram, Khasra No. 211, Village & Post Bher, Tehsil- Khimsar, Distt. Nagour. Pin Code- 341001 |  |  |  | PREMA RAM | 6350431991 | MOOLJEET SINGH | 6377085703 | DHARMENDRA SINGH | 8923520291 |  |  |  | JLJH | JLJH
I-RJ-CHHN-ENB-9084 | 1 | 1 | 850-SB | Barmer | Barmer | Aneesh & team |  | Done | 25.1409 | 70.9591 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 35 | 2025-10-31 | 2025-11-04 | 2025-11-13 | 2025-11-13 | 2025-11-13 | [13 empty] | V+P-TALASAR,,T-SEDWA,D-BARMER |  |  |  | KAWRA RAM | 9610615095 | Dinesh Kumar | 6350616488 | GIRDHARI RAM PRAJAPAT | 6350492189 |  |  |  | JLJH | JLJH
I-RJ-JPUR-ENB-G003 | 0/1/2 | 3 | PB ADDITION | Rajapark, Jaipur | Jaipur-2 | Yashwant & team |  | Done | 26.932 | 75.8392 | RTT | 0 | PB INSTALLATION IN ALL 3 SEC, MB & SB DISMANTLING REQD |  |  | Allotment- 33 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-16 | 2025-10-16 | [13 empty] | Shakila BanoW/O Mohammad Mustak, Plot No. 17- A, Saiyyad Colony, Bas Badanpura, Tehsil & Distt : Jaipur, Rajasthan. |  |  |  | VISHNU KUMAR SHARMA | 7737649810 | DURGA PRASAD SHARMA | 6350491332 | SANTOSH SHARMA | 9251637621 |  |  |  | JLKD | JLKD
I-RJ-JPUR-ENB-G012 | 0/1/2 | 3 | PB ADDITION | Vkia, Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9515 | 75.7987 | RTT | 0 | PB INSTALLATION IN ALL 3 SEC, MB & SB DISMANTLING REQD |  |  | Allotment- 33 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-16 | 2025-10-16 | [13 empty] | Ruksana Bano W/o Nisar Ahmed, 985- A, Ram Nagar, Shastri Nagar, Jaipur, Rajasthan. |  |  |  | Ramji Lal Gurjar | 8078699750 | NISAR KHAN | 6261130409 | Naveen Sharma | 9314160167 |  |  |  | JLKD | JLKD
I-RJ-BMNW-ENB-G001 | 1 | 1 | 850-SB | Gangapur | Kota | Aneesh & team |  | Done | 26.4468 | 76.4946 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 33 | 2025-10-14 | 2025-10-15 | 2025-10-17 | 2025-10-17 | 2025-10-17 | [13 empty] | Khasra No:- 414, Khatta No:- 96, Vill & PO:- Bichhoch, Tehsil:- Bamanwas, Dist:- Sawai Madhopur |  |  |  | RUKAM KESH MEENA | 6350491196 | VACANT | VACANT | BHUPENDRA SINGH RAJAWAT | 6350491277 |  |  |  | JLKD | JLKD
I-RJ-JHZP-ENB-G001 | 1/2 | 2 | 850-SB | Bhilwara | Bhilwara | Suresh & Team |  | Done | 25.6552 | 75.3927 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 35 | 2025-10-31 | 2025-11-04 | 2025-11-17 | 2025-11-17 | 2025-11-17 | [13 empty] | MS Kanika Singh d/o Manoj Kumar, Khata No. 26, Village & Post Luhario Kalan, Tehsil Jahazpur, Distt. Bhilwarta. |  |  |  | AMIT KUMAR | 8950646891 | SONESH KUMAR MEENA | 6350491576 | DINESH KUMAR JANGID | 8003593956 |  |  |  | JLJH | JLJH
I-RJ-KTPI-ENB-G001 | 2 | 1 | 850-SB | Chomu | Jaipur-1 | Sandeep & Team |  | Done | 27.7732 | 76.1765 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 35 | 2025-10-31 | 2025-11-02 | 2025-11-25 | 2025-11-25 | 2025-11-25 | [13 empty] | Ram Choudhary s/o Late Harchand Jat, Village & Post Jaisinghpura, Tehsil Kotputali, Distt. Jaipur. |  |  |  | LILA RAM JAT | 6350491500 | SATISH KUMAR YADAV | 6350491529 | MANOJ KUMAR SHARMA | 6350491496 |  |  |  | JLKD | JLKD
I-RJ-MNGO-ENB-G001 | 1 | 1 | ANT ALARM RECTIFICATION | Baran | Kota | LOCAL TEAM |  | Done | 25.242 | 76.502 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 36 | 2025-11-19 | 2025-11-22 | 2025-11-27 | 2025-11-27 | 2025-11-27 | [13 empty] | Badri Lal Nagar s/o Ram Charan, Village & Post Bohat, Tehsil Mangrol, Distt. Baran |  |  |  | NARENDERA PAL SINGH | 9131467549 | NARESH KUMAR | 6350491231 | SUSHEEL KUMAR PANDEY | 8078698882 |  |  |  | JLKD | JLKD
I-RJ-NGUR-ENB-9012 | 1 | 1 | ANT ALARM RECTIFICATION | Nagaur | Nagaur | PAPPURAM |  | Done |  |  | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 37 | 2025-11-21 | 2025-11-21 | 2025-11-27 | 2025-11-27 | 2025-11-27
I-RJ-PRDS-ENB-G001 | 0 | 1 | ANT ALARM RECTIFICATION | Banswara | Udaipur | Aneesh & team |  | Done | 23.7 | 74.7778 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 40 | 2025-11-25 | 2025-11-25 | 2025-11-27 | 2025-11-27 | 2025-11-27 | [13 empty] | Khasara No.1426 / 848, VPO - Salamgarh, Tehsil - Pratapgarh, Distt.Chittorgarh (Raj.) |  |  |  | AKHLESHWAR JADAV | 7665691228 | VACANT | VACANT | UDAY BHAN SINGH RANAWAT | 8114424610 |  |  |  | JLJH | JLJH
I-RJ-PRDS-ENB-G001 | 0 | 1 | ANT ALARM RECTIFICATION | Banswara | Udaipur | Aneesh & team |  | Done | 23.7 | 74.7778 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 41 | 2025-11-29 | 2025-11-29 | 2025-11-30 | 2025-11-30 | 2025-11-30 | [13 empty] | Khasara No.1426 / 848, VPO - Salamgarh, Tehsil - Pratapgarh, Distt.Chittorgarh (Raj.) |  |  |  | AKHLESHWAR JADAV | 7665691228 | VACANT | VACANT | UDAY BHAN SINGH RANAWAT | 8114424610 |  |  |  | JLJH | JLJH
I-RJ-NLGR-ENB-G001 | 0/2 | 2 | 850-SB | Nawalgarh | Sikar | Aneesh & team |  | Done | 27.8646 | 75.3742 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 39 | 2025-12-10 | 2025-12-10 | 2025-12-11 | 2025-12-11 | 2025-12-11 | [13 empty] | Parlad Rai Meena, Village & Post Kholasiya, Tehsil navalgarh, Dist.- Jhunjhunu |  |  |  | DHARMPAL DHAKA | 6350491115 | DINESH DUDI | 8000505302 | NARESH KUMAR | 6350491520 |  |  |  | JLKD | JLKD
I-RJ-PHGI-ENB-G003 | 0 | 1 | 850-SB | Chomu | Jaipur-1 | Aneesh & team |  | Done | 26.6066 | 75.5146 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 39 | 2025-12-10 | 2025-12-10 | 2025-12-12 | 2025-12-12 | 2025-12-12 | [13 empty] | Durga Lal, Khasra No. 1913, Vill & Post Chakwada, Tehsil Fagi, Distt. Jaipur |  |  |  | YASHPAL CHOUDHARY | 6350491511 | RAJESH MEENA | 6350616523 | ANKIT KUMAWAT | 6377201203 |  |  |  | JLKD | JLKD
I-RJ-DLPR-ENB-9027 | 2 | 1 | 850-SB | Dhaulpur | Bharatpur | Aneesh & team |  | Done | 26.7523 | 77.8636 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 39 | 2025-12-10 | 2025-12-10 | 2025-12-14 | 2025-12-14 | 2025-12-14 | [13 empty] | Munna s/o Narayan, Vill- Odi ka pura, post- odi |  |  |  | DHARMENDRA GURJAR | 6376917741 | BHAGIRATH SINGH | 8502019532 | SHRI BHAGWAN | 6350491348 |  |  |  | JLKD | JLKD
I-RJ-BKNR-ENB-G003 | 0/1/2 | 3 | PB ADDITION | Bikaner | Bikaner | PAWAN & Team |  | Done | 28.0161 | 73.3068 | RTT | 0 | PB INSTALLATION IN ALL 3 SEC, MB & SB DISMANTLING REQD |  |  | Allotment- 42 | 2025-12-15 | 2025-12-16 | 2025-12-22 | 2025-12-22 | 2025-12-22 | [13 empty] | Vinod Shrimal S/o Kanhaiya Lal, E-49, Anandpuri, Behind Moti Doongri Road, Tehsil & Distt : Jaipur, Rajasthan. |  |  |  | Naresh Pal Singh | 8078698922 | Bablu Nath Nath | 8078696110 | ARJUN SINGH SIKARWAR | 8078698942 |  |  |  | JLJH | JLJH
I-RJ-LXMK-ENB-G002 | 0/1 | 2 | 850-SB | Alwar | Alwar | Aneesh & team |  | Done | 27.4257 | 76.8067 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 38 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-26 | 2025-12-26 | [13 empty] | Badlu Ram s/o Hersukha,Khasra No.410,.Village & Post Butoli, Tehsil Laxmangarh, Distt. Alwar |  |  |  | RATAN PRAKASH SAINI | 8824106100 | DEVENDRA SINGH | 7240518483 | GAJENDRA SINGH SHEKHAWAT | 8003390514 |  |  |  | JLKD | JLKD
I-RJ-NOHA-ENB-G001 | 0/2 | 2 | 850-SB | Bikaner | Bikaner | PAWAN & Team |  | Done | 27.7095 | 73.1455 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 38 | 2025-12-24 | 2025-12-25 | 2025-12-27 | 2025-12-27 | 2025-12-27 | [13 empty] | Luna Ram s/o Ladu Ram,Patta No.08, Village & Post Jai Singh Desar Magra, Tehsil- Nokha, Distt. Bikaner. |  |  |  | RAKESH KUMAR | 9351038446 | SURESH KUMAR | 8078698902 | AJAY SINGH CHAUHAN | 9352230040 |  |  |  | JLJH | JLJH
I-RJ-JJUN-ENB-G006 | 1 | 1 | ANT ALARM RECTIFICATION | Jhunjhunun | Sikar | Outsource |  | Done | 28.2332 | 75.4115 | GBT | 0 | Faulty SB REPLACEMENT |  |  | Allotment- 39 | 2025-12-10 | 2025-12-10 | 2025-12-30 | 2025-12-30 | 2025-12-30 | [17 empty] | MANJEET SINGH | 9351228544 | MUKESH SINGH | 6350491146 | NARESH KUMAR | 6350491520 |  |  |  | JLKD | JLKD
I-RJ-SDAR-ENB-G002 | 1/2 | 2 | 850-SB | Sardarshahar | Sikar | Aneesh & team |  | Done | 28.41 | 74.6086 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 38 | 2025-12-24 | 2025-12-25 | 2026-01-04 | 2026-01-04 | 2026-01-04 | [13 empty] | Bajrang Lal s/o Sagar Mal, Village & Post Pulasar, Tehsil- Sardar Shahar, Distt. Churu. |  |  |  | JAI SINGH SHEKHAWAT | 6350491092 | ANIL KUMAR MEGHWAL | 6350616487 | RAVINDER KUMAR | 6350616703 |  |  |  | JLKD | JLKD
I-RJ-JPUR-ENB-G009 | 0/1/2 | 3 | PB ADDITION | Vaishali, Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.9011 | 75.8232 | RTT | 0 | PB INSTALLATION IN ALL 3 SEC, MB & SB DISMANTLING REQD |  |  | Allotment- 42 | 2025-12-15 | 2025-12-16 | 2026-01-12 | 2026-01-12 | 2026-01-12 | [13 empty] | Vinod Shrimal S/o Kanhaiya Lal, E-49, Anandpuri, Behind Moti Doongri Road, Tehsil & Distt : Jaipur, Rajasthan. |  |  |  | BRIJ MOHAN SHARMA | 8955001716 | SHYAMU SAINI | 8955937634 | SANTOSH SHARMA | 9251637621 |  |  |  | JLKD | JLKD
I-RJ-JPUR-ENB-0159 | 0/1/2 | 3 | PB ADDITION/1800 Band Addition | Rajapark, Jaipur | Jaipur-2 |  |  | MRN Done | 26.8961 | 75.8426 | GBM | 0 | PB INSTALLATION IN ALL 3 SEC, 2300 SB & 850 SB DISMANTLING REQD /3 RRH 1800 NEED TO ADD WITH POWER CPRI SFP |  |  | Allotment- 34 | 2025-10-28 | 2025-10-28 | [16 empty] | Opp. Pt. No.2/510, Nr. Azad Park, Jawahar Nagar,jaipur |  |  |  | Anurag Sharma | 8078699520 | SHYAMU SAINI | 8955937634 | SANTOSH SHARMA | 9251637621 |  |  |  | JLKD | JLKD
I-UE-LDNU-ENB-I016 | 2 | 1 | ANT ALARM RECTIFICATION | Ladnun | Nagaur | PAPPURAM |  | Done |  |  |  |  | Faulty SB REPLACEMENT |  |  | Allotment- 43 | 2025-12-27 | 2025-12-28 | 2025-12-30 | 2025-12-30 | 2025-12-30 | [26 empty] | JLJH | JLJH
I-RJ-BAIB-ENB-9010 | 0/1 | 2 | 850-SB | Dausa | Jaipur-1 | Aneesh & team |  | Done | 26.9892 | 76.47 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 44 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-21 | 2026-01-21 | [13 empty] | Vill and post Kolwa gram, Tehsil. Baswa, Dist. Dausa |  |  |  | LEKHRAJ SINGH GURJAR | 7849824309 | Neela Ram Bairwa | 6376917723 | SANDEEP | 9929558672 |  |  |  | JLKD | JLKD
I-RJ-FPJJ-ENB-G003 | 0/2 | 2 | 850-SB | Fatehpur | Sikar | Aneesh & team |  | Done | 27.9345 | 75.0097 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 44 | 2026-01-19 | 2026-01-20 | 2026-01-22 | 2026-01-22 | 2026-01-22 | [13 empty] | Mahmood Bano w/o Late Mustag Khan, Vill. & Post Garinda, Distt. Sikar, Pin Code 332301 |  |  |  | Mahendra Singh | 6350491103 | KULDEEP SINGH | 6350491083 | Kana Ram | 6350491095 |  |  |  | JLKD | JLKD
I-RJ-PHLE-ENB-G001 | 1 | 1 | 850-SB | Chomu | Jaipur-1 | Aneesh & team |  | Done | 27.1416 | 75.4115 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 45 | 2026-02-04 | 2026-02-06 | 2026-02-10 | 2026-02-10 | 2026-02-10 | [13 empty] | Guman Singh s/o Chandra Singh,Khasra No. 380 ,Village & Post Harsoli,Tehsil Sambhar Distt. Jaipur |  |  |  | SURESH YADAV | 9783683121 | [7 empty] | JLKD
I-RJ-BIHN-ENB-G003 | 1 | 1 | 850-SB | Jodhpur | Jodhpur | Hanuman & Team |  | Done | 26.5267 | 73.2996 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 45 | 2026-02-04 | 2026-02-07 | 2026-02-17 | 2026-02-17 | 2026-02-17 | [13 empty] | Anada Ram s/o Binja Ram, Khasra No.147, Village & Post Bucheti, Tehsil- Bhopal Garh, Distt. Jodhpur |  |  |  | JAI SINGH | 9001651114 | [7 empty] | JLJH
I-RJ-BRMR-ENB-9054 | 2 | 1 | 850-SB | Barmer | Barmer | Devilal Outsource |  | Done | 25.6387 | 71.326 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 46 | 2026-03-07 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-11 | [13 empty] | Khasra No. 26 & 45,Village Segadi,Tehsil & Dist.Barmer(RAJ) |  |  |  | ROOPA RAM | 8875543804 | Ashok Singh | 7427038431 | GIRDHARI RAM PRAJAPAT | 6350492189 |  |  |  | JLJH
I-RJ-CHHN-ENB-9093 | 2 | 1 | 850-SB | Barmer | Barmer | Devilal Outsource |  | Done | 25.488 | 71.0388 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 46 | 2026-03-07 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-11 | [13 empty] | Shree Vankal Viratra Mata Trustv/p Dhok, the Choutan district Barmer |  |  |  | JASSA RAM | 9351228534 | TAGA RAM | 9001771626 | GIRDHARI RAM PRAJAPAT | 6350492189 |  |  |  | JLJH
I-RJ-CHHN-ENB-9084 | 1 | 1 | 850-SB | Barmer | Barmer | Devilal Outsource |  | Done | 25.1409 | 70.9591 | GBT | 0 | SB ADDITION IN PLANNED SECTOR |  |  | Allotment- 47 | 2025-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-30 | 2026-12-30 | [13 empty] | V+P-TALASAR,,T-SEDWA,D-BARMER |  |  |  | KAWRA RAM | 9610615095 | Dinesh Kumar | 6350616488 | GIRDHARI RAM PRAJAPAT | 6350492189 |  |  |  | JLJH | JLJH
I-RJ-JPUR-ENB-1504 | 0/1/2 | 3 | PB ADDITION | Mansarovar, Jaipur | Jaipur-2 | Aneesh & team |  | Done | 26.881 | 75.7731 | GBM |  | 01-PB with Accessories |  |  | Allotment- 48 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-13 | 2026-03-13 | [13 empty] | , Gopalpura Bye Pass, Jaipur |  |  |  | MANRAJ GURJAR | MANRAJ GURJAR | MANRAJ GURJAR | MANRAJ GURJAR | MANRAJ GURJAR | MANRAJ GURJAR |  |  |  | JLKD | JLKD
I-RJ-BEWR-ENB-0090 | 0/2 | 2 | PB ADDITION | Beawar | Ajmer |  |  |  | 26.0952 | 74.2947 | GBM |  | 01-PB with Accessories |  |  | Allotment- 48 | 2026-03-11 | 2026-03-12 | [16 empty] | Jodhpur Road, Opp-Mateshwari Tiles,Near Shri Das Ji Rathi Pyau,Shamshan Ghat Govindpura Boundary Beawar,Post-Beawar,Police Station #8211;Beawar |  |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  |  |  | JLKD | JLKD
I-RJ-KSGR-ENB-0066 | 0/1/2 | 3 | PB ADDITION | Kishangarh | Ajmer |  |  |  | 26.5966 | 74.8598 | GBM |  | 01-PB with Accessories |  |  | Allotment- 48 | 2026-03-11 | 2026-03-12 | [16 empty] | Land situated atVillage- Sanvatsar, Madanganj, Kishangarh, Ajmer (Raj.) |  |  |  | Jaiveer Singh Rajawat | Jaiveer Singh Rajawat | Jaiveer Singh Rajawat | Jaiveer Singh Rajawat | Jaiveer Singh Rajawat | Jaiveer Singh Rajawat |  |  |  | JLKD | JLKD

## Sheet1
SITE ID | Sector | NO OF SECTOR | BAND | JC NAME | CMP | Team | Plan Date | Vendor
I-RJ-JPUR-ENB-1504 | 0/1/2 | 3 | PB ADDITION | Mansarovar, Jaipur | Jaipur-2 | Aneesh & team | 2026-03-13 | Digitcom

## UBR-B6
B6 ENB ID | B6 PMP ID | COMMON ENB ID (FAR END LINK) | COMMON PMP ID (FAR END LINK) | B6 WBS ID | LINK ID | NO OF SECTOR | JC NAME | CMP | Team | Plan Date | Current Status | LATITUDE | LONGITUDE | SITE TYPE | SITE IP | ACTIVITY | ACTIVITY CHANGES IF ANY | EXTRA MIN IF ANY | ALLOTMENT LOT | ALLOTMENT DATE | MATERIAL DISPATCHED DATE | INSTALLATION DATE | INTEGRATION DATE | ATP 11A DATE | 11A REMARK | ATP11C | ATP11C DONE BY | HOTO DATE | REASON IF PENDING/REMARK | POWER CABLE LENGTH | CPRI LENGTH | HARD CONDUIT LENGTH | FLEXIBLE LENGTH | Material Need to MRN | EXTRA MIN (YES/NO) | MRN REQUIRED (YES/NO) | MRN FINALIZATION STATUS | REASON IF MRN PENDING | WCC | RECO STATUS | REASON IF RECO PENDING | READY FOR BILLING OR NOT | REMARKS IF ANY | Digitcom Remark | SITE NAME | SITE ADDRESS | IANL Name | IANL Contact | IANL Mail ID | JIO Technician Name | Jio Technician Contact | Rigger Name | Rigger Contact | CI Name | CI Number | Infra Engg Name | Infra Engg Mail ID | Infra Engg Number | MIN Location | MRN Location | DC NUMBER
I-RJ-DDWN-ENB-I041 | I-RJ-DDWN-PMP-0038 | I-RJ-MKRN-ENB-9046 | I-RJ-MKRN-PMP-0054 | IRJ-DDWN-PMP-M-0038 | I-RJ-DDWN-ENB-I041-I-RJ-MKRN-ENB-9046 | 1 | Makrana | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.1527 | 74.4797 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B01 | 2025-07-18 | 2025-07-18 | 2025-07-22 | 2025-07-24 | [26 empty] | Prema Dahiya | 6350491992 | SUKHDEV ROYAL | 9672742052 | OM PRAKASH | 6350491377 |  |  |  | JLJH
I-RJ-MKRN-ENB-6015 | I-RJ-MKRN-PMP-0027 | I-RJ-MKRN-ENB-9042 | I-RJ-MKRN-PMP-0057 | IRJ-MKRN-PMP-M-0027 | I-RJ-MKRN-ENB-6015-I-RJ-MKRN-ENB-9042 | 1 | Makrana | NAGAUR | VIKRAM OUTSOURCE |  | Done | 27.0968 | 74.4312 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B01 | 2025-07-18 | 2025-07-18 | 2025-07-24 | 2025-07-25 | [26 empty] | JITENDRA PATIDAR | 6350491976 | SUKHDEV ROYAL | 9672742052 | RAJENDRA SINGH RATHORE | 6350491813 |  |  |  | JLJH
I-RJ-NGUR-ENB-0026 | I-RJ-NGUR-PMP-0012 | I-RJ-NGUR-ENB-0032 | I-RJ-NGUR-PMP-0083 | IRJ-NGUR-PMP-M-0012 | I-RJ-NGUR-ENB-0026-I-RJ-NGUR-ENB-0032 | 1 | NAGAUR | NAGAUR | VIKRAM OUTSOURCE |  | Done | 27.2166 | 73.7314 | GBM | 0 | UBR I&C |  |  | ALLOTMENT B01 | 2025-07-18 | 2025-07-18 | 2025-07-28 | 2025-07-28 | [26 empty] | SUNIL KUMAR | 9412607678 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 |  |  |  | JLJH
I-RJ-DDWN-ENB-H001 | I-RJ-DDWN-PMP-0016 | I-RJ-LDNU-ENB-6001 | I-RJ-LDNU-PMP-0052 | IRJ-DDWN-PMP-M-0016 | I-RJ-DDWN-ENB-H001-I-RJ-LDNU-ENB-6001 | 1 | Ladnu | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.4705 | 74.5126 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B03 | 2025-07-25 | 2025-07-26 | 2025-07-30 | 2025-07-30 | [35 empty] | JLJH
I-RJ-BKRD-ENB-6000 | I-RJ-BKRD-PMP-0001 | I-RJ-NGUR-ENB-9074 | I-RJ-NGUR-PMP-0081 | IRJ-BKRD-PMP-M-0001 | I-RJ-BKRD-ENB-6000-I-RJ-NGUR-ENB-9074 | 1 | Nagaur | NAGAUR | VIKRAM OUTSOURCE |  | Done | 27.0484 | 73.5843 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B02 | 2025-07-21 | 2025-07-22 | 2025-07-31 | 2025-07-31 | [26 empty] | DHARMARAM JAJRA | 6376202299 | NENA RAM | 7627076857 | DHARMENDRA SINGH | 8923520291 |  |  |  | JLJH
I-RJ-JAAL-ENB-9062 | I-RJ-JAAL-PMP-0010 | I-RJ-JAAL-ENB-9088 | I-RJ-JAAL-PMP-0035 | IRJ-JAAL-PMP-M-0010 | I-RJ-JAAL-ENB-9062-I-RJ-JAAL-ENB-9088 | 1 | Ladnu | NAGAUR | VIKRAM OUTSOURCE |  | Done | 27.0489 | 74.1067 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B02 | 2025-07-21 | 2025-07-22 | 2025-08-03 | 2025-08-04 | [26 empty] | RATNA RAM | 6350492259 | JAGDEV RAM BHAKAR | 6350616501 | OM PRAKASH | 6350491377 |  |  |  | JLJH
I-RJ-LDNU-ENB-I017 | I-RJ-LDNU-PMP-0030 | I-RJ-LDNU-ENB-9060 | I-RJ-LDNU-PMP-0040 | IRJ-LDNU-PMP-M-0030 | I-RJ-LDNU-ENB-I017-I-RJ-LDNU-ENB-9060 | 1 | Ladnu | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.6049 | 74.6521 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B02 | 2025-07-21 | 2025-07-22 | 2025-07-28 | 2025-07-28 | [26 empty] | SITA RAM | 9875107105 | BHARAT PAL CHAHAR | 9610003398 | OM PRAKASH | 6350491377 |  |  |  | JLJH
I-RJ-DDWN-ENB-Y001 | I-RJ-DDWN-PMP-0041 | I-RJ-DDWN-ENB-9104 | I-RJ-DDWN-PMP-0051 | IRJ-DDWN-PMP-M-0041 | I-RJ-DDWN-ENB-Y001-I-RJ-DDWN-ENB-9104 | 1 | Ladnu | NAGAUR | Rohit & Team |  | Done | 27.4747 | 74.6966 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B03 | 2025-07-25 | 2025-07-26 | 2025-07-28 | 2025-07-28 | [35 empty] | JLJH
I-RJ-KCMC-ENB-I001 | I-RJ-KCMC-PMP-0017 | I-RJ-KCMC-ENB-9006 | I-RJ-KCMC-PMP-0020 | IRJ-KCMC-PMP-M-0017 | I-RJ-KCMC-ENB-I001-I-RJ-KCMC-ENB-9006 | 1 | Makrana | NAGAUR | Rohit & Team |  | Done | 27.2089 | 74.8182 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B03 | 2025-07-25 | 2025-07-26 | 2025-07-30 | 2025-07-30 | [35 empty] | JLJH
I-RJ-JGWS-ENB-I001 | I-RJ-JGWS-PMP-0001 | I-RJ-DENA-ENB-9068 | I-RJ-DENA-PMP-0047 | IRJ-JGWS-PMP-M-0001 | I-RJ-JGWS-ENB-I001-I-RJ-DENA-ENB-9068 | 1 | Ladnu | NAGAUR | Rohit & Team |  | Done | 26.9137 | 74.3131 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B03 | 2025-07-25 | 2025-07-26 | 2025-07-31 | 2025-07-31 | [35 empty] | JLJH
I-RJ-JAAL-ENB-9011 | I-RJ-JAAL-PMP-0006 | I-RJ-JAAL-ENB-I015 | I-RJ-JAAL-PMP-0048 | IRJ-JAAL-PMP-M-0006 | I-RJ-JAAL-ENB-9011-I-RJ-JAAL-ENB-I015 | 1 | Ladnu | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.3988 | 74.0177 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B03 | 2025-07-25 | 2025-07-26 | 2025-08-01 | 2025-08-03 | [35 empty] | JLJH
I-RJ-NGUR-ENB-9020 | I-RJ-NGUR-PMP-0042 | I-RJ-NGUR-ENB-9081 | I-RJ-NGUR-PMP-0086 | IRJ-NGUR-PMP-M-0042 | I-RJ-NGUR-ENB-9020-I-RJ-NGUR-ENB-9081 | 1 | Nagaur | NAGAUR | Rohit & Team |  | Done | 27.0032 | 73.4805 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B03 | 2025-07-25 | 2025-07-26 | 2025-08-01 | 2025-08-01 | [35 empty] | JLJH
I-RJ-MRTA-ENB-6004 | I-RJ-MRTA-PMP-0002 | I-RJ-MRTA-ENB-9036 | I-RJ-MRTA-PMP-0053 | IRJ-MRTA-PMP-M-0002 | I-RJ-MRTA-ENB-6004-I-RJ-MRTA-ENB-9036 | 1 | NAGAUR | NAGAUR | Rohit & Team |  | Done | 26.5668 | 73.9297 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B04 | 2025-08-04 | 2025-08-04 | 2025-08-05 | 2025-08-06 | [35 empty] | JLJH
I-RJ-MKRN-ENB-I016 | I-RJ-MRTA-PMP-0045 | I-RJ-MKRN-ENB-9043 | I-RJ-MKRN-PMP-0064 | IRJ-MKRN-PMP-M-0044 | I-RJ-MKRN-ENB-I016-I-RJ-MKRN-ENB-9043 | 1 | Makrana | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.0525 | 74.7273 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B04 | 2025-08-04 | 2025-08-04 | 2025-08-05 | 2025-08-06 | [35 empty] | JLJH
I-RJ-MRTA-ENB-I008 | I-RJ-MRTA-PMP-0045 | I-RJ-RAFS-ENB-9009 | I-RJ-RAFS-PMP-0003 | IRJ-MRTA-PMP-M-0045 | I-RJ-MRTA-ENB-I008-I-RJ-RAFS-ENB-9009 | 1 | NAGAUR | NAGAUR | Rohit & Team |  | Done | 26.4931 | 74.0749 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B04 | 2025-08-04 | 2025-08-04 | 2025-08-06 | 2025-08-06 | [35 empty] | JLJH
I-RJ-DDWN-ENB-I007 | I-RJ-DDWN-PMP-0019 | I-RJ-DDWN-ENB-6011 | I-RJ-DDWN-PMP-0052 | IRJ-DDWN-PMP-M-0019 | I-RJ-DDWN-ENB-I007-I-RJ-DDWN-ENB-6011 | 1 | Ladnu | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.1813 | 74.5332 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B03 | 2025-07-25 | 2025-07-26 | 2025-08-07 | 2025-08-07 | 2025-08-07 | [34 empty] | JLJH
I-RJ-JAAL-ENB-6005 | I-RJ-JAAL-PMP-0002 | I-RJ-JAAL-ENB-9075 | I-RJ-JAAL-PMP-0042 | IRJ-JAAL-PMP-M-0002 | I-RJ-JAAL-ENB-6005-I-RJ-JAAL-ENB-9075 | 1 | Ladnu | NAGAUR | VIKRAM OUTSOURCE |  | Done | 27.2461 | 74.2889 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-11 | 2025-08-13 | 2025-08-13 | 2025-08-13 | [20 empty] | Janwas | [13 empty] | JLJH
I-RJ-NAWW-ENB-I002 | I-RJ-NAWW-PMP-0033 | I-RJ-NAWW-ENB-I020 | I-RJ-NAWW-PMP-0065 | IRJ-NAWW-PMP-M-0033 | I-RJ-NAWW-ENB-I002-I-RJ-NAWW-ENB-I020 | 1 | Makrana | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.1652 | 74.7828 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-11 | 2025-08-13 | 2025-08-13 | 2025-08-13 | [20 empty] | RASAL | [13 empty] | JLJH
I-RJ-SRGR-ENB-9016 | I-RJ-SRGR-PMP-0033 | I-RJ-LKNR-ENB-9092 | I-RJ-LKNR-PMP-0063 | IRJ-SRGR-PMP-M-0033 | I-RJ-SRGR-ENB-9016-I-RJ-LKNR-ENB-9092 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 28.9725 | 73.8628 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-15 | 2025-08-17 | 2025-08-17 | [20 empty] | Chak Jor | [13 empty] | JLKD
I-RJ-JAAL-ENB-I020 | I-RJ-JAAL-PMP-0027 | I-RJ-DENA-ENB-H001 | I-RJ-DENA-PMP-0063 | IRJ-JAAL-PMP-M-0027 | I-RJ-JAAL-ENB-I020-I-RJ-DENA-ENB-H001 | 1 | Makrana | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.0455 | 74.1686 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-11 | 2025-08-16 | 2025-08-16 | 2025-08-16 | [20 empty] | Chua | [13 empty] | JLJH
I-RJ-DENA-ENB-6081 | I-RJ-DENA-PMP-0004 | I-RJ-DENA-ENB-I002 | I-RJ-DENA-PMP-0054 | IRJ-DENA-PMP-M-0004 | I-RJ-DENA-ENB-6081-I-RJ-DENA-ENB-I002 | 1 | Makrana | NAGAUR | VIKRAM OUTSOURCE |  | Done | 26.7951 | 74.2634 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-11 | 2025-08-17 | 2025-08-17 | 2025-08-17 | [20 empty] | TENBnesTehsil-Degana | [13 empty] | JLJH
I-RJ-DDWN-ENB-6018 | I-RJ-DDWN-PMP-0004 | I-RJ-DDWN-ENB-9017 | I-RJ-DDWN-PMP-0062 | IRJ-DDWN-PMP-M-0004 | I-RJ-DDWN-ENB-6018-I-RJ-DDWN-ENB-9017 | 1 | Ladnu | NAGAUR | SANDEEP OUTSOURCE |  | Done | 27.2014 | 74.3384 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-11 | 2025-08-18 | 2025-08-18 | [21 empty] | Badbara | [13 empty] | JLJH
I-RJ-SRGR-ENB-9015 | I-RJ-SRGR-PMP-0032 | I-RJ-SRGR-ENB-9094 | I-RJ-SRGR-PMP-0083 | IRJ-SRGR-PMP-M-0032 | I-RJ-SRGR-ENB-9015-I-RJ-SRGR-ENB-9094 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 28.9939 | 73.8514 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-17 | 2025-08-17 | [21 empty] | Mokalsar | [13 empty] | JLKD
I-RJ-JAAL-ENB-9010 | I-RJ-JAAL-PMP-0005 | I-RJ-JAAL-ENB-I013 | I-RJ-JAAL-PMP-0043 | IRJ-JAAL-PMP-M-0005 | I-RJ-JAAL-ENB-9010-I-RJ-JAAL-ENB-I013 | 1 | Ladnu | NAGAUR | VIKRAM OUTSOURCE |  | Done | 27.3416 | 73.9537 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-11 | 2025-08-19 | 2025-08-19 | [21 empty] | Gardiya | [13 empty] | JLJH
I-RJ-SRGR-ENB-H001 | I-RJ-SRGR-PMP-0059 | I-RJ-SRGR-ENB-I010 | I-RJ-SRGR-PMP-0106 | IRJ-SRGR-PMP-M-0059 | I-RJ-SRGR-ENB-H001-I-RJ-SRGR-ENB-I010 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.0404 | 73.9669 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-20 | 2025-08-20 | [21 empty] | RATTASAR | [13 empty] | JLKD
I-RJ-SRGR-ENB-6003 | I-RJ-SRGR-PMP-0020 | I-RJ-SRGR-ENB-9091 | I-RJ-SRGR-PMP-0082 | IRJ-SRGR-PMP-M-0020 | I-RJ-SRGR-ENB-6003-I-RJ-SRGR-ENB-9091 | 1 | Suratgarh | Ganganagar | Rohit & Team |  | Done | 29.0613 | 73.5976 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B06 | 2025-08-19 | 2025-08-19 | 2025-08-20 | 2025-08-20 | [21 empty] | Gopalasar | [13 empty] | JLKD
I-RJ-SRGR-ENB-9106 | I-RJ-SRGR-PMP-0050 | I-RJ-SRGR-ENB-9082 | I-RJ-SRGR-PMP-0081 | IRJ-SRGR-PMP-M-0050 | I-RJ-SRGR-ENB-9106-I-RJ-SRGR-ENB-9082 | 1 | Suratgarh | Ganganagar | Rohit & Team |  | Done | 29.1292 | 73.6889 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-21 | 2025-08-21 | [21 empty] | Lalgadiya | [13 empty] | JLKD
I-RJ-LKNR-ENB-9069 | I-RJ-LKNR-PMP-0030 | I-RJ-SRGR-ENB-9080 | I-RJ-SRGR-PMP-0080 | IRJ-LKNR-PMP-M-0030 | I-RJ-LKNR-ENB-9069-I-RJ-SRGR-ENB-9080 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 28.9045 | 73.9452 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-18 | 2025-08-19 | [21 empty] | Village Singrasar | [13 empty] | JLKD
I-RJ-ANUG-ENB-6002 | I-RJ-ANUG-PMP-0001 | I-RJ-ANUG-ENB-I011 | I-RJ-ANUG-PMP-0037 | IRJ-ANUG-PMP-M-0001 | I-RJ-ANUG-ENB-6002-I-RJ-ANUG-ENB-I011 | 1 | Suratgarh | Ganganagar | Rohit & Team |  | Done | 29.0935 | 73.1369 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B06 | 2025-08-19 | 2025-08-19 | 2025-08-22 | 2025-08-25 | [21 empty] | 6 P | [13 empty] | JLKD
I-RJ-SRGR-ENB-6004 | I-RJ-SRGR-PMP-0021 | I-RJ-SRGR-ENB-I017 | I-RJ-SRGR-PMP-0103 | IRJ-SRGR-PMP-M-0021 | I-RJ-SRGR-ENB-6004-I-RJ-SRGR-ENB-I017 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1611 | 73.727 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B06 | 2025-08-19 | 2025-08-19 | 2025-08-22 | 2025-08-22 | [35 empty] | JLKD
I-RJ-JWAL-ENB-6000 | I-RJ-JWAL-PMP-0001 | I-RJ-ANGR-ENB-9048 | I-RJ-ANGR-PMP-0028 | IRJ-JWAL-PMP-M-0001 | I-RJ-JWAL-ENB-6000-I-RJ-ANGR-ENB-9048 | 1 | Suratgarh | Ganganagar | Rohit & Team |  | Done | 28.9063 | 73.0483 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-23 | 2025-08-23 | [21 empty] | 7 MLD (B) | [13 empty] | JLKD
I-RJ-ANUG-ENB-I012 | I-RJ-ANUG-PMP-0014 | I-RJ-ANUG-ENB-I010 | I-RJ-ANUG-PMP-0036 | IRJ-ANUG-PMP-M-0014 | I-RJ-ANUG-ENB-I012-I-RJ-ANUG-ENB-I010 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.3311 | 73.2262 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-24 | 2025-08-24 | [21 empty] | 11SJM | [13 empty] | JLKD
I-RJ-MKRN-ENB-9049 | I-RJ-MKRN-PMP-0032 | I-RJ-MKRN-ENB-9061 | I-RJ-MKRN-PMP-0052 | IRJ-MKRN-PMP-M-0032 | I-RJ-MKRN-ENB-9049-I-RJ-MKRN-ENB-9061 | 1 | Ladnu | Nagaur | SANDEEP OUTSOURCE |  | Done | 27.1451 | 74.5968 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-25 | 2025-08-25 | [21 empty] | Dhananwana | [13 empty] | JLJH
I-RJ-ANUG-ENB-6002 | I-RJ-ANUG-PMP-0001 | I-RJ-ANUG-ENB-I003 | I-RJ-ANUG-PMP-0025 | IRJ-ANUG-PMP-M-0001 | I-RJ-ANUG-ENB-6002-I-RJ-ANUG-ENB-I003 | 1 | Suratgarh | Ganganagar | Rohit & Team |  | Done | 29.0935 | 73.1369 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-12 | 2025-08-26 | 2025-08-26 | [21 empty] | 1 NWM | [13 empty] | JLKD
I-RJ-MKRN-ENB-9035 | I-RJ-MKRN-PMP-0030 | I-RJ-MKRN-ENB-9037 | I-RJ-MKRN-PMP-0069 | IRJ-MKRN-PMP-M-0030 | I-RJ-MKRN-ENB-9035-I-RJ-MKRN-ENB-9037 | 1 | Makrana | Nagaur | SANDEEP OUTSOURCE |  | Done | 27.1246 | 74.6311 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-26 | 2025-08-26 | [21 empty] | Loroli | [13 empty] | JLJH
I-RJ-NAWW-ENB-9092 | I-RJ-NAWW-PMP-0018 | I-RJ-NAWW-ENB-I003 | I-RJ-NAWW-PMP-0056 | IRJ-NAWW-PMP-M-0018 | I-RJ-NAWW-ENB-9092-I-RJ-NAWW-ENB-I003 | 1 | Makrana | Nagaur | SANDEEP OUTSOURCE |  | Done | 27.1378 | 74.9694 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-27 | 2025-08-27 | [21 empty] | Gogor | [13 empty] | JLJH
I-RJ-LDNU-ENB-I010 | I-RJ-LDNU-PMP-0027 | I-RJ-DDWN-ENB-9105 | I-RJ-DDWN-PMP-0047 | IRJ-LDNU-PMP-M-0027 | I-RJ-LDNU-ENB-I010-I-RJ-DDWN-ENB-9105 | 1 | Nagaur | Nagaur | SANDEEP OUTSOURCE |  | Done | 27.47 | 74.3558 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-30 | 2025-08-30 | [21 empty] | Doodoli | [13 empty] | JLJH
I-RJ-DENA-ENB-9048 | I-RJ-DENA-PMP-0011 | I-RJ-MKRN-ENB-9050 | I-RJ-MKRN-PMP-0068 | IRJ-DENA-PMP-M-0011 | I-RJ-DENA-ENB-9048-I-RJ-MKRN-ENB-9050 | 1 | Nagaur | Nagaur | SANDEEP OUTSOURCE |  | Done | 26.9266 | 74.3371 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-29 | 2025-08-29 | [21 empty] | Bajoli | [13 empty] | JLJH
I-RJ-SRGR-ENB-G002 | I-RJ-SRGR-PMP-0058 | I-RJ-SRGR-ENB-9062 | I-RJ-SRGR-PMP-0102 | IRJ-SRGR-PMP-M-0058 | I-RJ-SRGR-ENB-G002-I-RJ-SRGR-ENB-9062 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1839 | 73.9429 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B06 | 2025-08-19 | 2025-08-19 | 2025-08-21 | 2025-08-21 | [21 empty] | Tehsil- Suratgarh | [13 empty] | JLKD
I-RJ-JAAL-ENB-9082 | I-RJ-JAAL-PMP-0013 | I-RJ-JAAL-ENB-9049 | I-RJ-JAAL-PMP-0045 | IRJ-JAAL-PMP-M-0013 | I-RJ-JAAL-ENB-9082-I-RJ-JAAL-ENB-9049 | 1 | Nagaur | Nagaur | VIKRAM OUTSOURCE |  | Done | 27.3066 | 73.9044 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-26 | 2025-08-27 | [21 empty] | Sarasani | [13 empty] | JLJH
I-RJ-NGUR-ENB-9038 | I-RJ-NGUR-PMP-0045 | I-RJ-NGUR-ENB-9089 | I-RJ-NGUR-PMP-0094 | IRJ-NGUR-PMP-M-0045 | I-RJ-NGUR-ENB-9038-I-RJ-NGUR-ENB-9089 | 1 | NAGAUR | NAGAUR | VIKRAM OUTSOURCE |  | Done | 26.8631 | 73.6338 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B05 | 2025-08-11 | 2025-08-11 | 2025-08-18 | 2025-08-21 | 2025-08-21 | [20 empty] | Kaliyass | [13 empty] | JLJH
I-RJ-NGUR-ENB-9020 | I-RJ-NGUR-PMP-0042 | I-RJ-KESR-ENB-9039 | I-RJ-KESR-PMP-0026 | IRJ-NGUR-PMP-M-0042 | I-RJ-NGUR-ENB-9020-I-RJ-KESR-ENB-9039 | 1 | Makrana | Nagaur | Aneesh & Team |  | Done | 27.0031 | 73.4805 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-31 | 2025-08-31 | [21 empty] | Khodwa | [13 empty] | JLJH
I-RJ-KESR-ENB-V001 | I-RJ-KESR-PMP-0018 | I-RJ-KESR-ENB-9038 | I-RJ-KESR-PMP-0025 | IRJ-KESR-PMP-M-0018 | I-RJ-KESR-ENB-V001-I-RJ-KESR-ENB-9038 | 1 | Makrana | Nagaur | VIKRAM OUTSOURCE |  | Done | 26.9725 | 73.4151 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-31 | 2025-08-31 | [21 empty] | Tadawas | [13 empty] | JLJH
I-RJ-NGUR-ENB-9064 | I-RJ-NGUR-PMP-0046 | I-RJ-NGUR-ENB-I014 | I-RJ-NGUR-PMP-0091 | IRJ-NGUR-PMP-M-0046 | I-RJ-NGUR-ENB-9064-I-RJ-NGUR-ENB-I014 | 1 | Nagaur | Nagaur | VIKRAM OUTSOURCE |  | Done | 27.1829 | 73.8224 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B07 | 2025-08-20 | 2025-08-21 | 2025-08-25 | 2025-08-25 | [21 empty] | GAGWANA | [13 empty] | JLJH
I-RJ-SRGR-ENB-9049 | I-RJ-SRGR-PMP-0040 | I-RJ-SRGR-ENB-9096 | I-RJ-SRGR-PMP-0093 | IRJ-SRGR-PMP-M-0040 | I-RJ-SRGR-ENB-9049-I-RJ-SRGR-ENB-9096 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.129 | 73.7479 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B08 | 2025-09-08 | 2025-09-08 | 2025-09-10 | 2025-09-10 | 2025-09-10 | 2025-09-10 | [19 empty] | Chak-8 MC (Near 285 RD) | [13 empty] | JLKD
I-RJ-AHOR-ENB-I002 | I-RJ-AHOR-PMP-0014 | I-RJ-AHOR-ENB-9048 | I-RJ-AHOR-PMP-0028 | IRJ-AHOR-PMP-M-0014 | I-RJ-AHOR-ENB-I002-I-RJ-AHOR-ENB-9048 | 1 | Jalor | Sirohi | Rohit & Team |  | Done | 25.4069 | 72.8204 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-12 | 2025-09-12 | [20 empty] | KAMBA | [13 empty] | JLJH
I-RJ-DENA-ENB-9056 | I-RJ-DENA-PMP-0012 | I-RJ-DENA-ENB-I021 | I-RJ-DENA-PMP-0053 | IRJ-DENA-PMP-M-0012 | I-RJ-DENA-ENB-9056-I-RJ-DENA-ENB-I021 | 1 | Makrana | Nagaur | SANDEEP OUTSOURCE |  | Done | 27.0108 | 74.3449 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-12 | 2025-09-12 | [20 empty] | Chandarun | [13 empty] | JLJH
I-RJ-MRTA-ENB-9012 | I-RJ-MRTA-PMP-0010 | I-RJ-MRTA-ENB-9057 | I-RJ-MRTA-PMP-0058 | IRJ-MRTA-PMP-M-0010 | I-RJ-MRTA-ENB-9012-I-RJ-MRTA-ENB-9057 | 1 | Nagaur | Nagaur | Dileep & Rajkumar Team |  | Done | 26.6115 | 74.1023 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-12 | 2025-09-12 | [20 empty] | Netadiya | [13 empty] | JLJH
I-RJ-SRGR-ENB-9034 | I-RJ-SRGR-PMP-0038 | I-RJ-SRGR-ENB-9070 | I-RJ-SRGR-PMP-0089 | IRJ-SRGR-PMP-M-0038 | I-RJ-SRGR-ENB-9034-I-RJ-SRGR-ENB-9070 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/fatp pending-not assigned | 29.1152 | 73.6371 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B08 | 2025-09-08 | 2025-09-08 | 2025-09-11 | 2025-09-11 | 2025-09-11 | [20 empty] | Gopalsar | [13 empty] | JLKD
I-RJ-SRGR-ENB-9034 | I-RJ-SRGR-PMP-0038 | I-RJ-SRGR-ENB-9097 | I-RJ-SRGR-PMP-0088 | IRJ-SRGR-PMP-M-0038 | I-RJ-SRGR-ENB-9034-I-RJ-SRGR-ENB-9097 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1152 | 73.6371 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B08 | 2025-09-08 | 2025-09-08 | 2025-09-12 | 2025-09-12 | 2025-09-12 | [20 empty] | Gopalsar | [13 empty] | JLKD
I-RJ-MRTA-ENB-9074 | I-RJ-MRTA-PMP-0024 | I-RJ-MRTA-ENB-9077 | I-RJ-MRTA-PMP-0060 | IRJ-MRTA-PMP-M-0024 | I-RJ-MRTA-ENB-9074-I-RJ-MRTA-ENB-9077 | 1 | Nagaur | Nagaur | Dileep & Rajkumar Team |  | Done/fatp pending-not assigned | 26.6023 | 74.1478 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-13 | [20 empty] | Gawardi | [13 empty] | JLJH
I-RJ-BNML-ENB-S001 | I-RJ-BNML-PMP-0018 | I-RJ-BNML-ENB-9046 | I-RJ-BNML-PMP-0027 | IRJ-BNML-PMP-M-0018 | I-RJ-BNML-ENB-S001-I-RJ-BNML-ENB-9046 | 1 | Jalor | Sirohi | Rohit & Team |  | Done/fatp penrong-not assigned | 25.016 | 72.6078 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-13 | 2025-09-13 | 2025-09-13 | [20 empty] | Mandoli | [13 empty] | JLJH
I-RJ-DENA-ENB-9013 | I-RJ-DENA-PMP-0009 | I-RJ-DENA-ENB-I020 | I-RJ-DENA-PMP-0057 | IRJ-DENA-PMP-M-0009 | I-RJ-DENA-ENB-9013-I-RJ-DENA-ENB-I020 | 1 | Makrana | Nagaur | Dileep & Rajkumar Team |  | Done | 26.7651 | 74.1758 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-14 | 2025-09-14 | 2025-09-14 |  | 2025-09-14 | Rajkumar | [17 empty] | Dotoli | [13 empty] | JLJH
I-RJ-SNCE-ENB-Y001 | I-RJ-SNCE-PMP-0048 | I-RJ-SNCE-ENB-9095 | I-RJ-SNCE-PMP-0060 | IRJ-SNCE-PMP-M-0048 | I-RJ-SNCE-ENB-Y001-I-RJ-SNCE-ENB-9095 | 1 | Jalor | Sirohi | Rohit & Team |  | Done | 24.8356 | 71.5602 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-14 | 2025-09-14 | 2025-09-14 |  | 2025-09-14 | Rohit | [17 empty] | Bagsari | [13 empty] | JLJH
I-RJ-KUKD-ENB-6000 | I-RJ-KUKD-PMP-0001 | I-RJ-JAAL-ENB-9073 | I-RJ-JAAL-PMP-0049 | IRJ-KUKD-PMP-M-0001 | I-RJ-KUKD-ENB-6000-I-RJ-JAAL-ENB-9073 | 1 | Ladnu | Nagaur | SANDEEP OUTSOURCE |  | Done | 27.1497 | 74.3457 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | 2025-09-14 | 2025-09-14 | 2025-09-14 |  | 2025-09-14 | Sandeep | [17 empty] | KHATU KHURD | [13 empty] | JLJH
I-RJ-SRGR-ENB-9064 | I-RJ-SRGR-PMP-0067 | I-RJ-SRGR-ENB-9075 | I-RJ-SRGR-PMP-0094 | IRJ-SRGR-PMP-M-0067 | I-RJ-SRGR-ENB-9064-I-RJ-SRGR-ENB-9075 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.2933 | 73.7592 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B08 | 2025-09-08 | 2025-09-08 | 2025-09-15 | 2025-09-15 | [21 empty] | Chak-2 PPM(Padampura) | [13 empty] | JLKD
I-RJ-DENA-ENB-9097 | I-RJ-DENA-PMP-0021 | I-RJ-DENA-ENB-9100 | I-RJ-DENA-PMP-0059 | IRJ-DENA-PMP-M-0021 | I-RJ-DENA-ENB-9097-I-RJ-DENA-ENB-9100 | 1 | Makrana | Nagaur | Dileep & Rajkumar Team |  | Done | 26.7406 | 74.4151 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-15 | 2025-09-15 | [21 empty] | Thata | [13 empty] | JLJH
I-RJ-SNCE-ENB-6001 | I-RJ-SNCE-PMP-0001 | I-RJ-SNCE-ENB-9104 | I-RJ-SNCE-PMP-0057 | IRJ-SNCE-PMP-M-0001 | I-RJ-SNCE-ENB-6001-I-RJ-SNCE-ENB-9104 | 1 | Jalor | Sirohi | Rohit & Team |  | Done | 24.8814 | 71.606 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-15 | 2025-09-15 | [21 empty] | Chitalwana | [13 empty] | JLJH
I-RJ-DENA-ENB-9085 | I-RJ-DENA-PMP-0018 | I-RJ-DENA-ENB-9053 | I-RJ-DENA-PMP-0055 | IRJ-DENA-PMP-M-0018 | I-RJ-DENA-ENB-9085-I-RJ-DENA-ENB-9053 | 1 | Makrana | Nagaur | Dileep & Rajkumar Team |  | Done | 26.9252 | 74.2508 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-16 | 2025-09-16 | 2025-09-16 | [20 empty] | Jalsoo Khurd | [13 empty] | JLJH
I-RJ-SNCE-ENB-9009 | I-RJ-SNCE-PMP-0006 | I-RJ-CWAN-ENB-9008 | I-RJ-CWAN-PMP-0003 | IRJ-SNCE-PMP-M-0006 | I-RJ-SNCE-ENB-9009-I-RJ-CWAN-ENB-9008 | 1 | Jalor | Sirohi | Rohit & Team |  | Done | 24.9605 | 71.6735 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-16 | 2025-09-16 | 2025-09-16 | [20 empty] | Heera Ram S/o Sh. Pralad Ram V/P Ranodor, The. Chitalwana, Distt. Jalor | [13 empty] | JLJH
I-RJ-SRGR-ENB-I015 | I-RJ-SRGR-PMP-0042 | I-RJ-SRGR-ENB-9072 | I-RJ-SRGR-PMP-0095 | IRJ-SRGR-PMP-M-0042 | I-RJ-SRGR-ENB-I015-I-RJ-SRGR-ENB-9072 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.2539 | 73.6947 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B08 | 2025-09-08 | 2025-09-08 | 2025-09-14 | 2025-09-16 | 2025-09-16 | [20 empty] | 10SD/KARNISAR | [13 empty] | JLKD
I-RJ-SNCE-ENB-6004 | I-RJ-SNCE-PMP-0002 | I-RJ-SNCE-ENB-I030 | I-RJ-SNCE-PMP-0056 | IRJ-SNCE-PMP-M-0002 | I-RJ-SNCE-ENB-6004-I-RJ-SNCE-ENB-I030 | 1 | Jalor | Sirohi | Rohit & Team |  | Done | 25.0405 | 71.7536 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | [23 empty] | Sahu Dookiyon Ki Dhani | [13 empty] | JLJH
I-RJ-SOJT-ENB-9058 | I-RJ-SOJT-PMP-0015 | I-RJ-SOJT-ENB-9048 | I-RJ-SOJT-PMP-0041 | IRJ-SOJT-PMP-M-0015 | I-RJ-SOJT-ENB-9058-I-RJ-SOJT-ENB-9048 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done | 26.0891 | 73.4488 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | [23 empty] | Abakai ki Dani | [13 empty] | JLJH
I-RJ-JAAL-ENB-G006 | I-RJ-JAAL-PMP-0021 | I-RJ-JAAL-ENB-I008 | I-RJ-JAAL-PMP-0039 | IRJ-JAAL-PMP-M-0021 | I-RJ-JAAL-ENB-G006-I-RJ-JAAL-ENB-I008 | 1 | Ladnu | Nagaur | VIKRAM/Mahendra & Team |  | Done/Rectification Required | 27.1391 | 74.1269 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | 2025-09-14 | 2025-09-14 | 2025-09-15 | [20 empty] | Tarnau | [13 empty] | JLJH
I-RJ-KCRA-ENB-6000 | I-RJ-KCRA-PMP-0001 | I-RJ-KCRA-ENB-9003 | I-RJ-KCRA-PMP-0004 | IRJ-KCRA-PMP-M-0001 | I-RJ-KCRA-ENB-6000-I-RJ-KCRA-ENB-9003 | 1 | Nagaur | Nagaur | VIKRAM OUTSOURCE |  | Done/Fatp Pending | 26.986 | 73.9718 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-15 | 2025-09-15 | 2025-09-19 | [20 empty] | KUCHERA | [13 empty] | JLJH
I-RJ-NGUR-ENB-9015 | I-RJ-NGUR-PMP-0040 | I-RJ-JAAL-ENB-I014 | I-RJ-JAAL-PMP-0040 | IRJ-NGUR-PMP-M-0040 | I-RJ-NGUR-ENB-9015-I-RJ-JAAL-ENB-I014 | 1 | Ladnu | Nagaur | VIKRAM OUTSOURCE |  | Done/Fatp Pending | 27.038 | 73.9087 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | 2025-09-14 | 2025-09-14 | 2025-09-14 | [20 empty] | Gothra | [13 empty] | JLJH
I-RJ-SOJT-ENB-I005 | I-RJ-SOJT-PMP-0027 | I-RJ-SOJT-ENB-I008 | I-RJ-SOJT-PMP-0037 | IRJ-SOJT-PMP-M-0027 | I-RJ-SOJT-ENB-I005-I-RJ-SOJT-ENB-I008 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done | 25.9228 | 73.5209 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | 2025-09-18 | 2025-09-18 | 2025-09-18 | [20 empty] | Suryata | [13 empty] | JLJH
I-RJ-PLBG-ENB-6003 | I-RJ-PLBG-PMP-0003 | I-RJ-SRGR-ENB-I009 | I-RJ-SRGR-PMP-0091 | IRJ-PLBG-PMP-M-0003 | I-RJ-PLBG-ENB-6003-I-RJ-SRGR-ENB-I009 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.3757 | 73.8649 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-18 | 2025-09-18 | 2025-09-18 | [20 empty] | SuratgarhAirf | [13 empty] | JLKD
I-RJ-SOJT-ENB-I009 | I-RJ-SOJT-PMP-0029 | I-RJ-SOJT-ENB-9056 | I-RJ-SOJT-PMP-0036 | IRJ-SOJT-PMP-M-0029 | I-RJ-SOJT-ENB-I009-I-RJ-SOJT-ENB-9056 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending from field | 26.0191 | 73.5774 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | 2025-09-19 | 2025-09-19 | 2025-09-19 | [20 empty] | Roopawas | [13 empty] | JLJH
I-RJ-SRGR-ENB-9103 | I-RJ-SRGR-PMP-0048 | I-RJ-SRGR-ENB-H002 | I-RJ-SRGR-PMP-0092 | IRJ-SRGR-PMP-M-0048 | I-RJ-SRGR-ENB-9103-I-RJ-SRGR-ENB-H002 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/Fatp Pending | 29.4208 | 73.749 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-19 | 2025-09-19 | 2025-09-19 | [20 empty] | 3 FDM | [13 empty] | JLKD
I-RJ-JAAL-ENB-9012 | I-RJ-JAAL-PMP-0007 | I-RJ-JAAL-ENB-I002 | I-RJ-JAAL-PMP-0044 | IRJ-JAAL-PMP-M-0007 | I-RJ-JAAL-ENB-9012-I-RJ-JAAL-ENB-I002 | 1 | Ladnu | Nagaur | VIKRAM OUTSOURCE |  | Done/fatp pending | 27.458 | 74.0661 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | 2025-09-17 | 2025-09-18 | 2025-09-20 | [20 empty] | Surpaliya | [13 empty] | JLJH
I-RJ-SRGR-ENB-9019 | I-RJ-SRGR-PMP-0036 | I-RJ-SRGR-ENB-9124 | I-RJ-SRGR-PMP-0086 | IRJ-SRGR-PMP-M-0036 | I-RJ-SRGR-ENB-9019-I-RJ-SRGR-ENB-9124 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/fatp Pending | 29.1513 | 73.8857 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-20 | 2025-09-20 | 2025-09-20 | [20 empty] | Kardu Phanta | [13 empty] | JLKD
I-RJ-NAWW-ENB-I001 | I-RJ-NAWW-PMP-0032 | I-RJ-NAWW-ENB-9052 | I-RJ-NAWW-PMP-0055 | IRJ-NAWW-PMP-M-0032 | I-RJ-NAWW-ENB-I001-I-RJ-NAWW-ENB-9052 | 1 | Makrana | Nagaur | SANDEEP OUTSOURCE |  | Done/fatp Pending | 27.0117 | 74.8031 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-20 | 2025-09-20 | 2025-09-20 | [20 empty] | Maglana | [13 empty] | JLJH
I-RJ-BALI-ENB-I005 | I-RJ-BALI-PMP-0016 | I-RJ-BALI-ENB-9050 | I-RJ-BALI-PMP-0021 | IRJ-BALI-PMP-M-0016 | I-RJ-BALI-ENB-I005-I-RJ-BALI-ENB-9050 | 1 | Pali | Sirohi | Rohit & Team |  | Done/fatp Pending | 25.0418 | 73.2335 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-20 | 2025-09-20 | 2025-09-20 | [20 empty] | Bhatoond | [13 empty] | JLJH
I-RJ-SOJT-ENB-9014 | I-RJ-SOJT-PMP-0009 | I-RJ-SOJT-ENB-9054 | I-RJ-SOJT-PMP-0040 | IRJ-SOJT-PMP-M-0009 | I-RJ-SOJT-ENB-9014-I-RJ-SOJT-ENB-9054 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/Fatp Pending | 25.9897 | 73.8233 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B10 | 2025-09-12 | 2025-09-12 | 2025-09-21 | 2025-09-21 | 2025-09-21 | [20 empty] | Chandawal Nagar | [13 empty] | JLJH
I-RJ-SRGR-ENB-9014 | I-RJ-SRGR-PMP-0031 | I-RJ-SRGR-ENB-I013 | I-RJ-SRGR-PMP-0104 | IRJ-SRGR-PMP-M-0031 | I-RJ-SRGR-ENB-9014-I-RJ-SRGR-ENB-I013 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/Fatp Pending | 29.1283 | 73.8654 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-21 | 2025-09-21 | 2025-09-21 | [20 empty] | Near Karni Petrol Pump | [13 empty] | JLKD
I-RJ-BALI-ENB-9062 | I-RJ-BALI-PMP-0007 | I-RJ-BALI-ENB-I004 | I-RJ-BALI-PMP-0026 | IRJ-BALI-PMP-M-0007 | I-RJ-BALI-ENB-9062-I-RJ-BALI-ENB-I004 | 1 | Pali | Sirohi | Rohit & Team |  | Done/Fatp Pending | 24.8908 | 73.1615 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-21 | 2025-09-21 | 2025-09-21 | [20 empty] | Kharda | [13 empty] | JLJH
I-RJ-MKRN-ENB-I006 | I-RJ-MKRN-PMP-0040 | I-RJ-MKRN-ENB-9031 | I-RJ-MKRN-PMP-0065 | IRJ-MKRN-PMP-M-0040 | I-RJ-MKRN-ENB-I006-I-RJ-MKRN-ENB-9031 | 1 | Makrana | Nagaur | SANDEEP OUTSOURCE |  | Done/Fatp Pending | 26.9654 | 74.5776 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-21 | 2025-09-21 | 2025-09-21 | [20 empty] | NANDOLIMERTIYA | [13 empty] | JLJH
I-RJ-NGUR-ENB-6014 | I-RJ-NGUR-PMP-0033 | I-RJ-NGUR-ENB-A004 | I-RJ-NGUR-PMP-0109 | IRJ-NGUR-PMP-M-0033 | I-RJ-NGUR-ENB-6014-I-RJ-NGUR-ENB-A004 | 1 | Nagaur | Nagaur | VIKRAM OUTSOURCE |  | Done/Fatp Pending | 27.2043 | 73.7375 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B09 | 2025-09-09 | 2025-09-10 | 2025-09-12 | 2025-09-21 | 2025-09-21 | [20 empty] | Kangrwara mohalla | [13 empty] | JLJH
I-RJ-DDWN-ENB-I039 | I-RJ-DDWN-PMP-0036 | I-RJ-DDWN-ENB-9076 | I-RJ-DDWN-PMP-0057 | IRJ-DDWN-PMP-M-0036 | I-RJ-DDWN-ENB-I039-I-RJ-DDWN-ENB-9076 | 1 | Ladnu | Nagaur | SANDEEP OUTSOURCE |  | Done/Fatp Pending | 27.2314 | 74.545 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-22 | 2025-09-22 | 2025-09-22 | [20 empty] | KHOJAS | [13 empty] | JLJH
I-RJ-SRGR-ENB-9018 | I-RJ-SRGR-PMP-0035 | I-RJ-SRGR-ENB-H003 | I-RJ-SRGR-PMP-0099 | IRJ-SRGR-PMP-M-0035 | I-RJ-SRGR-ENB-9018-I-RJ-SRGR-ENB-H003 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/Fatp Pending | 29.1037 | 73.8554 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-22 | 2025-09-22 | 2025-09-22 | [20 empty] | Indhor Bus Stand | [13 empty] | JLKD
I-RJ-JAAN-ENB-G001 | I-RJ-JAAN-PMP-0013 | I-RJ-JAAN-ENB-9046 | I-RJ-JAAN-PMP-0037 | IRJ-JAAN-PMP-M-0013 | I-RJ-JAAN-ENB-G001-I-RJ-JAAN-ENB-9046 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/Fatp Pending | 26.2726 | 73.9557 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-22 | 2025-09-22 | 2025-09-22 | [20 empty] | Bhanja Kuri | [13 empty] | JLJH
I-RJ-RSNG-ENB-I005 | I-RJ-RSNG-PMP-0020 | I-RJ-RSNG-ENB-9049 | I-RJ-RSNG-PMP-0043 | IRJ-RSNG-PMP-M-0020 | I-RJ-RSNG-ENB-I005-I-RJ-RSNG-ENB-9049 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/Fatp Pending | 29.3534 | 73.4979 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [20 empty] | Bajuwala | [13 empty] | JLKD
I-RJ-DDWN-ENB-9063 | I-RJ-DDWN-PMP-0008 | I-RJ-MOSR-ENB-9003 | I-RJ-MOSR-PMP-0004 | IRJ-DDWN-PMP-M-0008 | I-RJ-DDWN-ENB-9063-I-RJ-MOSR-ENB-9003 | 1 | Ladnu | Nagaur | SANDEEP OUTSOURCE |  | Done/Fatp Pending | 27.3416 | 74.683 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [20 empty] | chhapri kalan | [13 empty] | JLJH
I-RJ-JAAN-ENB-A002 | I-RJ-JAAN-PMP-0011 | I-RJ-JAAN-ENB-9052 | I-RJ-JAAN-PMP-0034 | IRJ-JAAN-PMP-M-0011 | I-RJ-JAAN-ENB-A002-I-RJ-JAAN-ENB-9052 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/Fatp Pending | 26.3059 | 74.1908 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-23 | 2025-09-23 | 2025-09-23 | [20 empty] | Ras | [13 empty] | JLJH
I-RJ-RAPR-ENB-9035 | I-RJ-RAPR-PMP-0009 | I-RJ-JAAN-ENB-9059 | I-RJ-JAAN-PMP-0031 | IRJ-RAPR-PMP-M-0009 | I-RJ-RAPR-ENB-9035-I-RJ-JAAN-ENB-9059 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 26.2664 | 74.2282 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-24 | 2025-09-24 | 2025-09-24 | [20 empty] | RAS SHREECEMENT Beawar | [13 empty] | JLJH
I-RJ-KKNI-ENB-9006 | I-RJ-KKNI-PMP-0005 | I-RJ-KKNI-ENB-9046 | I-RJ-KKNI-PMP-0024 | IRJ-KKNI-PMP-M-0005 | I-RJ-KKNI-ENB-9006-I-RJ-KKNI-ENB-9046 | 1 | Pali | Sirohi | Rohit & Team |  | Done/fatp pending | 25.858 | 73.2243 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-24 | 2025-09-24 | 2025-09-24 | [20 empty] | Kharda Band | [13 empty] | JLJH
I-RJ-DDWN-ENB-9014 | I-RJ-DDWN-PMP-0006 | I-RJ-DDWN-ENB-9068 | I-RJ-DDWN-PMP-0053 | IRJ-DDWN-PMP-M-0006 | I-RJ-DDWN-ENB-9014-I-RJ-DDWN-ENB-9068 | 1 | Ladnu | Nagaur | SANDEEP OUTSOURCE |  | Done/fatp pending | 27.4506 | 74.5229 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-24 | 2025-09-24 | 2025-09-24 | [20 empty] | Ajawa | [13 empty] | JLJH
I-RJ-RSNG-ENB-I002 | I-RJ-RSNG-PMP-0018 | I-RJ-ANUG-ENB-9056 | I-RJ-ANUG-PMP-0028 | IRJ-RSNG-PMP-M-0018 | I-RJ-RSNG-ENB-I002-I-RJ-ANUG-ENB-9056 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/fatp pending | 29.3581 | 73.3019 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-24 | 2025-09-24 | 2025-09-24 | [20 empty] | Makamwala | [13 empty] | JLKD
I-RJ-MKRN-ENB-6015 | I-RJ-MKRN-PMP-0027 | I-RJ-MKRN-ENB-I005 | I-RJ-MKRN-PMP-0066 | IRJ-MKRN-PMP-M-0027 | I-RJ-MKRN-ENB-6015-I-RJ-MKRN-ENB-I005 | 1 | Makrana | Nagaur | VIKRAM OUTSOURCE |  | Done/fatp pending | 2+L84+M87 | 74.4312 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-24 | 2025-09-24 | [21 empty] | Ranigaon | [13 empty] | JLJH
I-RJ-MKRN-ENB-6015 | I-RJ-MKRN-PMP-0027 | I-RJ-MKRN-ENB-G001 | I-RJ-MKRN-PMP-0072 | IRJ-MKRN-PMP-M-0027 | I-RJ-MKRN-ENB-6015-I-RJ-MKRN-ENB-G001 | 1 | Makrana | Nagaur | VIKRAM OUTSOURCE |  | Done/fatp pending | 27.0966 | 74.4312 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-24 | 2025-09-25 | 2025-09-24 | [20 empty] | Ranigaon | [13 empty] | JLJH
I-RJ-RSNG-ENB-I006 | I-RJ-RSNG-PMP-0021 | I-RJ-RSNG-ENB-I007 | I-RJ-RSNG-PMP-0046 | IRJ-RSNG-PMP-M-0021 | I-RJ-RSNG-ENB-I006-I-RJ-RSNG-ENB-I007 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/fatp pending | 29.3988 | 73.4866 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-25 | 2025-09-25 | 2025-09-25 | [20 empty] | 12SAD | [13 empty] | JLKD
I-RJ-DDWN-ENB-I036 | I-RJ-DDWN-PMP-0033 | I-RJ-DDWN-ENB-G005 | I-RJ-DDWN-PMP-0064 | IRJ-DDWN-PMP-M-0033 | I-RJ-DDWN-ENB-I036-I-RJ-DDWN-ENB-G005 | 1 | Ladnu | Nagaur | SANDEEP OUTSOURCE |  | Done/fatp pending | 27.4036 | 74.7491 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B12 | 2025-09-17 | 2025-09-19 | 2025-09-25 | 2025-09-25 | 2025-09-25 | [20 empty] | Deedarpura | [13 empty] | JLJH
I-RJ-PALI-ENB-9044 | I-RJ-PALI-PMP-0049 | I-RJ-PALI-ENB-I012 | I-RJ-PALI-PMP-0085 | IRJ-PALI-PMP-M-0049 | I-RJ-PALI-ENB-9044-I-RJ-PALI-ENB-I012 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 25.623 | 73.428 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-25 | 2025-09-25 | 2025-09-25 | [20 empty] | Sodawas | [13 empty] | JLJH
I-RJ-PALI-ENB-9057 | I-RJ-PALI-PMP-0052 | I-RJ-PALI-ENB-I007 | I-RJ-PALI-PMP-0086 | IRJ-PALI-PMP-M-0052 | I-RJ-PALI-ENB-9057-I-RJ-PALI-ENB-I007 | 1 | Pali | Sirohi | Rohit & Team |  | Done/fatp pending | 25.7038 | 73.3246 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-25 | 2025-09-25 | 2025-09-25 | [20 empty] | Hemawas | [13 empty] | JLJH
I-RJ-ANUG-ENB-9061 | I-RJ-ANUG-PMP-0011 | I-RJ-ANUG-ENB-9053 | I-RJ-ANUG-PMP-0033 | IRJ-ANUG-PMP-M-0011 | I-RJ-ANUG-ENB-9061-I-RJ-ANUG-ENB-9053 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done | 29.1751 | 73.379 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-26 | [22 empty] | 57 GB | [13 empty] | JLKD
I-RJ-MAJN-ENB-9061 | I-RJ-MAJN-PMP-0011 | I-RJ-MAJN-ENB-I005 | I-RJ-MAJN-PMP-0043 | IRJ-MAJN-PMP-M-0011 | I-RJ-MAJN-ENB-9061-I-RJ-MAJN-ENB-I005 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp Pending | 25.5789 | 73.6834 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-26 | 2025-09-26 | 2025-09-26 | [20 empty] | Esali, Panchyat Samiti- Marward | [13 empty] | JLJH
I-RJ-KKNI-ENB-I005 | I-RJ-KKNI-PMP-0019 | I-RJ-KKNI-ENB-9038 | I-RJ-KKNI-PMP-0036 | IRJ-KKNI-PMP-M-0019 | I-RJ-KKNI-ENB-I005-I-RJ-KKNI-ENB-9038 | 1 | Pali | Sirohi | Rohit & Team |  | Done/Fatp Pending | 25.7686 | 73.0256 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-26 | 2025-09-26 | 2025-09-26 | [20 empty] | Guralia | [13 empty] | JLJH
I-RJ-ANUG-ENB-I018 | I-RJ-ANUG-PMP-0017 | I-RJ-ANUG-ENB-H002 | I-RJ-ANUG-PMP-0030 | IRJ-ANUG-PMP-M-0017 | I-RJ-ANUG-ENB-I018-I-RJ-ANUG-ENB-H002 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/fatp pending | 29.1813 | 73.2734 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-27 | 2025-09-27 | 2025-09-27 | [20 empty] | 2PGM | [13 empty] | JLKD
I-RJ-SOJT-ENB-I011 | I-RJ-SOJT-PMP-0030 | I-RJ-SOJT-ENB-I012 | I-RJ-SOJT-PMP-0039 | IRJ-SOJT-PMP-M-0030 | I-RJ-SOJT-ENB-I011-I-RJ-SOJT-ENB-I012 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 26.0562 | 73.4778 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-27 | 2025-09-27 | 2025-09-27 | [20 empty] | Charwas_U | [13 empty] | JLJH
I-RJ-DDWN-ENB-9013 | I-RJ-DDWN-PMP-0005 | I-RJ-DDWN-ENB-I018 | I-RJ-DDWN-PMP-0070 | IRJ-DDWN-PMP-M-0005 | I-RJ-DDWN-ENB-9013-I-RJ-DDWN-ENB-I018 | 1 | Ladnu | Nagaur | SANDEEP OUTSOURCE |  | Done/fatp pending | 27.3795 | 74.5267 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B14 | 2025-09-25 | 2025-09-25 | 2025-09-27 | 2025-09-27 | 2025-09-27 | [20 empty] | IndolawKiDhani | [13 empty] | JLJH
I-RJ-ANUG-ENB-9060 | I-RJ-ANUG-PMP-0010 | I-RJ-ANUG-ENB-9063 | I-RJ-ANUG-PMP-0024 | IRJ-ANUG-PMP-M-0010 | I-RJ-ANUG-ENB-9060-I-RJ-ANUG-ENB-9063 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/fatp pending | 29.1553 | 73.1876 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-28 | 2025-09-28 | 2025-09-28 | [20 empty] | Anupgarh | [13 empty] | JLKD
I-RJ-NAWW-ENB-A003 | I-RJ-NAWW-PMP-0020 | I-RJ-NAWW-ENB-I018 | I-RJ-NAWW-PMP-0058 | IRJ-NAWW-PMP-M-0020 | I-RJ-NAWW-ENB-A003-I-RJ-NAWW-ENB-I018 | 1 | Makrana | Nagaur | SANDEEP OUTSOURCE |  | Done/fatp pending | 27.1268 | 75.023 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-28 | 2025-09-28 | 2025-09-28 | [20 empty] | Bhooni | [13 empty] | JLJH
I-RJ-JONT-ENB-9001 | I-RJ-JONT-PMP-0001 | I-RJ-RAPR-ENB-9009 | I-RJ-RAPR-PMP-0021 | IRJ-JONT-PMP-M-0001 | I-RJ-JONT-ENB-9001-I-RJ-RAPR-ENB-9009 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 26.037 | 73.98 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-28 | 2025-09-28 | 2025-09-28 | [20 empty] | Jhunta | [13 empty] | JLJH
I-RJ-ANUG-ENB-6002 | I-RJ-ANUG-PMP-0001 | I-RJ-ANUG-ENB-I001 | I-RJ-ANUG-PMP-0031 | IRJ-ANUG-PMP-M-0001 | I-RJ-ANUG-ENB-6002-I-RJ-ANUG-ENB-I001 | 1 | Suratgarh | Ganganagar | Aneesh & Team |  | Done/fatp pending | 29.0935 | 73.1369 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B11 | 2025-09-17 | 2025-09-17 | 2025-09-29 | 2025-09-29 | 2025-09-29 | [20 empty] | 11 P | [13 empty] | JLKD
I-RJ-REAR-ENB-G002 | I-RJ-REAR-PMP-0011 | I-RJ-REAR-ENB-H001 | I-RJ-REAR-PMP-0027 | IRJ-REAR-PMP-M-0011 | I-RJ-REAR-ENB-G002-I-RJ-REAR-ENB-H001 | 1 | Sirohi | Sirohi | Rohit & Team |  | Done/fatp pending | 24.7047 | 72.6855 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-29 | 2025-09-29 | 2025-09-29 | [20 empty] | Sirodi | [13 empty] | JLJH
I-RJ-RAPR-ENB-6006 | I-RJ-RAPR-PMP-0005 | I-RJ-RAPR-ENB-9059 | I-RJ-RAPR-PMP-0022 | IRJ-RAPR-PMP-M-0005 | I-RJ-RAPR-ENB-6006-I-RJ-RAPR-ENB-9059 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 26.0411 | 74.0207 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-29 | 2025-09-29 | 2025-09-29 | [20 empty] | Pagario ka bass | [13 empty] | JLJH
I-RJ-REAR-ENB-9036 | I-RJ-REAR-PMP-0004 | I-RJ-REAR-ENB-9039 | I-RJ-REAR-PMP-0025 | IRJ-REAR-PMP-M-0004 | I-RJ-REAR-ENB-9036-I-RJ-REAR-ENB-9039 | 1 | Sirohi | Sirohi | Rohit & Team |  | Done/fatp pending | 24.5994 | 72.4892 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B14 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-09-30 | [20 empty] | Kareli | [13 empty] | JLJH
I-RJ-SOJT-ENB-6000 | I-RJ-SOJT-PMP-0001 | I-RJ-SOJT-ENB-9064 | I-RJ-SOJT-PMP-0038 | IRJ-SOJT-PMP-M-0001 | I-RJ-SOJT-ENB-6000-I-RJ-SOJT-ENB-9064 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 25.8678 | 73.5507 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B14 | 2025-09-25 | 2025-09-25 | 2025-09-30 | 2025-09-30 | 2025-09-30 | [20 empty] | BAGAWAS-RJNHXXXXX093B | [13 empty] | JLJH
I-RJ-BNML-ENB-6007 | I-RJ-BNML-PMP-0005 | I-RJ-SRHI-ENB-9055 | I-RJ-SRHI-PMP-0041 | IRJ-BNML-PMP-M-0005 | I-RJ-BNML-ENB-6007-I-RJ-SRHI-ENB-9055 | 1 | Sirohi | Sirohi | Rohit & Team |  | Done/fatp pending | 25.0062 | 72.5491 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-30 | 2025-10-01 | 2025-10-02 | [20 empty] | Ramseen | [13 empty] | JLJH
I-RJ-MRTA-ENB-9013 | I-RJ-MRTA-PMP-0011 | I-RJ-MRTA-ENB-I009 | I-RJ-MRTA-PMP-0063 | IRJ-MRTA-PMP-M-0011 | I-RJ-MRTA-ENB-9013-I-RJ-MRTA-ENB-I009 | 1 | Nagaur | Nagaur | VIKRAM OUTSOURCE |  | Done/fatp pending | 26.7254 | 74.0651 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B14 | 2025-09-25 | 2025-09-25 | 2025-09-29 | 2025-09-29 | 2025-10-02 | [20 empty] | Santa Ki Dhani | [13 empty] | JLJH
I-RJ-NAWW-ENB-9071 | I-RJ-NAWW-PMP-0009 | I-RJ-NAWW-ENB-H005 | I-RJ-NAWW-PMP-0057 | IRJ-NAWW-PMP-M-0009 | I-RJ-NAWW-ENB-9071-I-RJ-NAWW-ENB-H005 | 1 | Makrana | nagaur | SANDEEP OUTSOURCE |  | Done/fatp pending | 27.0613 | 75.0469 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B15 | 2025-09-30 | 2025-09-30 | 2025-10-03 | 2025-10-03 | 2025-10-03 | [34 empty] | JLJH
I-RJ-KKNI-ENB-I007 | I-RJ-KKNI-PMP-0020 | I-RJ-KKNI-ENB-I004 | I-RJ-KKNI-PMP-0031 | IRJ-KKNI-PMP-M-0020 | I-RJ-KKNI-ENB-I007-I-RJ-KKNI-ENB-I004 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 25.83 | 72.891 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B15 | 2025-09-30 | 2025-09-30 | 2025-10-03 | 2025-10-03 | 2025-10-03 | [34 empty] | JLJH
I-RJ-SEGN-ENB-9008 | I-RJ-SEGN-PMP-0007 | I-RJ-SEGN-ENB-S001 | I-RJ-SEGN-PMP-0034 | IRJ-SEGN-PMP-M-0007 | I-RJ-SEGN-ENB-9008-I-RJ-SEGN-ENB-S001 | 1 | Sirohi | Sirohi | Rohit & Team |  | Done/fatp pending | 25.0387 | 72.9446 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B14 | 2025-09-25 | 2025-09-25 | 2025-09-28 | 2025-09-28 | 2025-09-28 | [20 empty] | Uthaman | [13 empty] | JLJH
I-RJ-AHOR-ENB-H001 | I-RJ-AHOR-PMP-0032 | I-RJ-AHOR-ENB-9054 | I-RJ-AHOR-PMP-0030 | IRJ-AHOR-PMP-M-0032 | I-RJ-AHOR-ENB-H001-I-RJ-AHOR-ENB-9054 | 1 | Jalor | Sirohi | Rohit & Team |  | Done/fatp pending | 25.4789 | 72.9808 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-09-27 | 2025-10-04 | 2025-09-27 | [20 empty] | Valdara | [13 empty] | JLJH
I-RJ-KKNI-ENB-6003 | I-RJ-KKNI-PMP-0003 | I-RJ-PALI-ENB-9045 | I-RJ-PALI-PMP-0084 | IRJ-KKNI-PMP-M-0003 | I-RJ-KKNI-ENB-6003-I-RJ-PALI-ENB-9045 | 1 | Pali | Sirohi | Dileep & Rajkumar Team |  | Done/fatp pending | 25.8778 | 73.3427 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B13 | 2025-09-23 | 2025-09-23 | 2025-10-04 | 2025-10-04 | 2025-10-04 | [20 empty] | Nimbali | [13 empty] | JLJH
I-RJ-DENA-ENB-I008 | I-RJ-DENA-PMP-0033 | I-RJ-DENA-ENB-9061 | I-RJ-DENA-PMP-0051 | IRJ-DENA-PMP-M-0033 | I-RJ-DENA-ENB-I008-I-RJ-DENA-ENB-9061 | 1 | Makrana | Nagaur | Rohit & Team |  | Done/fatp pending | 26.7845 | 74.4364 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B16 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-09 | 2025-10-09 | [34 empty] | JLJH
I-RJ-DENA-ENB-9080 | I-RJ-DENA-PMP-0015 | I-RJ-DENA-ENB-I010 | I-RJ-DENA-PMP-0056 | IRJ-DENA-PMP-M-0015 | I-RJ-DENA-ENB-9080-I-RJ-DENA-ENB-I010 | 1 | Makrana | Nagaur | Rohit & Team |  | Done/fatp pending | 26.6701 | 74.3374 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B16 | 2025-10-07 | 2025-10-08 | 2025-10-10 | 2025-10-10 | 2025-10-10 | [34 empty] | JLJH
I-RJ-JAAN-ENB-9015 | I-RJ-JAAN-PMP-0007 | I-RJ-JAAN-ENB-A001 | I-RJ-JAAN-PMP-0041 | IRJ-JAAN-PMP-M-0007 | I-RJ-JAAN-ENB-9015-I-RJ-JAAN-ENB-A001 | 1 | Pali | Sirohi | Rohit & Team |  | Done/fatp pending | 26.3477 | 73.9992 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B15 | 2025-09-30 | 2025-09-30 | 2025-10-11 | 2025-10-11 | 2025-10-11 | [34 empty] | JLJH
I-RJ-MRTA-ENB-9048 | I-RJ-MRTA-PMP-0017 | I-RJ-MRTA-ENB-9093 | I-RJ-MRTA-PMP-0048 | IRJ-MRTA-PMP-M-0017 | I-RJ-MRTA-ENB-9048-I-RJ-MRTA-ENB-9093 | 1 | Nagaur | Nagaur | VIKRAM OUTSOURCE |  | Done/fatp pending | 26.5366 | 73.8703 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B14 | 2025-09-25 | 2025-09-25 | 2025-09-28 | 2025-09-28 | 2025-10-01 | [20 empty] | Bayad | [13 empty] | JLJH
I-RJ-DENA-ENB-9080 | I-RJ-DENA-PMP-0015 | I-RJ-DENA-ENB-I012 | I-RJ-DENA-PMP-0060 | IRJ-DENA-PMP-M-0015 | I-RJ-DENA-ENB-9080-I-RJ-DENA-ENB-I012 | 1 | Makrana | Nagaur | Rohit & Team |  | Done/fatp pending | 26.6701 | 74.3374 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B17 | 2025-10-11 | 2025-10-11 | 2025-10-12 | 2025-10-12 | 2025-10-12 | [20 empty] | Bikharniya Kalan, | [13 empty] | JLJH
I-RJ-DDWN-ENB-I028 | I-RJ-DDWN-PMP-0028 | I-RJ-MOSR-ENB-9001 | I-RJ-MOSR-PMP-0002 | IRJ-DDWN-PMP-M-0028 | I-RJ-DDWN-ENB-I028-I-RJ-MOSR-ENB-9001 | 1 | Ladnu | Nagaur | Prema Ram Outsource |  | Done/fatp pending | 27.407 | 74.8057 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B16 | 2025-10-07 | 2025-10-08 | 2025-10-12 | 2025-10-12 | [35 empty] | JLJH
I-RJ-PASS-ENB-9043 | I-RJ-PASS-PMP-0012 | I-RJ-MKRN-ENB-I013 | I-RJ-MKRN-PMP-0075 | IRJ-PASS-PMP-M-0012 | I-RJ-PASS-ENB-9043-I-RJ-MKRN-ENB-I013 | 1 | Makrana | Nagaur | Rohit & Team | 2025-10-13 |  | 26.8166 | 74.4067 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B17 | 2025-10-11 | 2025-10-11 | [23 empty] | Merasi | [13 empty] | JLJH
I-RJ-BNML-ENB-6004 | I-RJ-BNML-PMP-0003 | I-RJ-BNML-ENB-9051 | I-RJ-BNML-PMP-0033 | IRJ-BNML-PMP-M-0003 | I-RJ-BNML-ENB-6004-I-RJ-BNML-ENB-9051 | 1 | Jalor | Sirohi | Dileep & Rajkumar Team | 2025-10-13 |  | 24.8137 | 72.456 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B16 | 2025-10-07 | 2025-10-08 | [37 empty] | JLJH
I-RJ-LDNU-ENB-6007 | I-RJ-LDNU-PMP-0013 | I-RJ-LDNU-ENB-9048 | I-RJ-LDNU-PMP-0046 | IRJ-LDNU-PMP-M-0013 | I-RJ-LDNU-ENB-6007-I-RJ-LDNU-ENB-9048 | 1 | Ladnu | Nagaur |  |  |  | 27.4073 | 74.3438 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B16 | 2025-10-07 | 2025-10-08 | [37 empty] | JLJH
I-RJ-REAR-ENB-I001 | I-RJ-REAR-PMP-0012 | I-RJ-REAR-ENB-9042 | I-RJ-REAR-PMP-0024 | IRJ-REAR-PMP-M-0012 | I-RJ-REAR-ENB-I001-I-RJ-REAR-ENB-9042 | 1 | Sirohi | Sirohi |  |  |  | 24.6701 | 72.4962 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B17 | 2025-10-11 | 2025-10-11 | [23 empty] | JEERAVAL | [13 empty] | JLJH
I-RJ-PASS-ENB-9043 | I-RJ-PASS-PMP-0012 | I-RJ-PASS-ENB-I002 | I-RJ-PASS-PMP-0025 | IRJ-PASS-PMP-M-0012 | I-RJ-PASS-ENB-9043-I-RJ-PASS-ENB-I002 | 1 | Makrana | Nagaur | Mangilal Outsource |  | 60M Power Required | 74.4775 | 26.8166 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B16 | 2025-10-07 | 2025-10-08 | [37 empty] | JLJH
I-RJ-NAWW-ENB-9074 | I-RJ-NAWW-PMP-0011 | I-RJ-NAWW-ENB-9047 | I-RJ-NAWW-PMP-0060 | IRJ-NAWW-PMP-M-0011 | I-RJ-NAWW-ENB-9074-I-RJ-NAWW-ENB-9047 | 1 | Makrana | Nagaur |  |  |  | 27.1545 | 74.9956 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B17 | 2025-10-11 | 2025-10-11 | [23 empty] | Kankariya | [13 empty] | JLJH
I-RJ-MBLT-ENB-V001 | I-RJ-MBLT-PMP-0001 | I-RJ-BALI-ENB-9060 | I-RJ-BALI-PMP-0024 | IRJ-MBLT-PMP-M-0001 | I-RJ-MBLT-ENB-V001-I-RJ-BALI-ENB-9060 | 1 | Pali | Sirohi |  |  |  | 25.1958 | 73.3841 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B18 | 2025-11-11 | 2025-11-11 | [23 empty] | Mundara | [13 empty] | JLJH
I-RJ-DDWN-ENB-I016 | I-RJ-DDWN-PMP-0021 | I-RJ-MOSR-ENB-9004 | I-RJ-JAAL-PMP-0029 | IRJ-DDWN-PMP-M-0021 | I-RJ-DDWN-ENB-I016-I-RJ-MOSR-ENB-9004 | 1 | Ladnu | Nagaur |  |  |  | 27.1657 | 74.4475 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B18 | 2025-11-11 | 2025-11-11 | [23 empty] | Mandookara | [13 empty] | JLJH
I-RJ-LDNU-ENB-9039 | I-RJ-LDNU-PMP-0016 | I-RJ-JAAL-ENB-9080 | I-RJ-MOSR-PMP-0003 | IRJ-LDNU-PMP-M-0016 | I-RJ-LDNU-ENB-9039-I-RJ-JAAL-ENB-9080 | 1 | Ladnu | Nagaur |  |  |  | 27.3013 | 74.307 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B18 | 2025-11-11 | 2025-11-11 | [23 empty] | I-RJ-LDNU-ENB-9039 | [13 empty] | JLJH
I-RJ-MRTA-ENB-9013 | I-RJ-MRTA-PMP-0011 | I-RJ-MRTA-ENB-9086 | I-RJ-MRTA-PMP-0057 | IRJ-MRTA-PMP-M-0011 | I-RJ-MRTA-ENB-9013-I-RJ-MRTA-ENB-9086 | 1 | Nagaur | Nagaur |  |  |  | 26.7254 | 74.0651 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B19 | 2025-11-14 | 2025-11-14 | [23 empty] | Santa Ki Dhani | [13 empty] | JLJH
I-RJ-NGUR-ENB-6016 | I-RJ-NGUR-PMP-0035 | I-RJ-NGUR-ENB-I001 | I-RJ-NGUR-PMP-0102 | IRJ-NGUR-PMP-M-0035 | I-RJ-NGUR-ENB-6016-I-RJ-NGUR-ENB-I001 | 1 | Nagaur | Nagaur |  |  |  | 27.2047 | 73.7378 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B19 | 2025-11-14 | 2025-11-14 | [23 empty] | Near Duggad Bhawan | [13 empty] | JLJH
I-RJ-RSNG-ENB-9038 | I-RJ-RSNG-PMP-0010 | I-RJ-RSNG-ENB-9050 | I-RJ-RSNG-PMP-0045 | I-RJ-RSNG-PMP-0010 | I-RJ-RSNG-ENB-9038-I-RJ-RSNG-ENB-9050 | 1 | Makrana | Nagaur |  |  |  | 29.5523 | 73.4811 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B20 | 2025-11-15 | 2025-11-17 | [23 empty] | 11 P.S | [13 empty] | JLKD
I-RJ-RSNG-ENB-6001 | I-RJ-RSNG-PMP-0001 | I-RJ-RSNG-ENB-I001 | I-RJ-RSNG-PMP-0052 | I-RJ-RSNG-PMP-0001 | I-RJ-RSNG-ENB-6001-I-RJ-RSNG-ENB-I001 | 1 | Suratgarh | Ganganagar |  |  |  | 29.414 | 73.279 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B20 | 2025-11-15 | 2025-11-17 | [23 empty] | 15 Ptd-A | [13 empty] | JLKD
I-RJ-NAWW-ENB-I009 | I-RJ-NAWW-PMP-0039 | I-RJ-NAWW-ENB-9061 | I-RJ-NAWW-PMP-0067 | I-RJ-NAWW-PMP-0039 | I-RJ-NAWW-ENB-I009-I-RJ-NAWW-ENB-9061 | 1 | Suratgarh | Ganganagar |  |  |  | 27.3207 | 74.9203 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B20 | 2025-11-15 | 2025-11-17 | [23 empty] | PAREWADI | [13 empty] | JLKD
I-RJ-NOHR-ENB-G002 | I-RJ-NOHR-PMP-0019 | I-RJ-SRGR-ENB-I020 | I-RJ-SRGR-PMP-0097 | I-RJ-NOHR-PMP-0019 | I-RJ-NOHR-ENB-G002-I-RJ-SRGR-ENB-I020 | 1 | Suratgarh | Ganganagar |  |  |  | 29.0342 | 74.1547 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B20 | 2025-11-15 | 2025-11-17 | [23 empty] | Motair | [13 empty] | JLJH
I-RJ-PALI-ENB-0071 | I-RJ-PALI-PMP-0033 | I-RJ-PALI-ENB-V001 | I-RJ-PALI-PMP-0090 | IRJ-PALI-PMP-M-0033 | I-RJ-PALI-ENB-0071-I-RJ-PALI-ENB-V001_A6 | 1 | Pali | Sirohi |  |  |  | 25.7724 | 73.2955 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B21 | 2025-11-20 | 2025-11-21 | [37 empty] | JLJH
I-RJ-JAAN-ENB-I008 | I-RJ-JAAN-PMP-0019 | I-RJ-RAPR-ENB-9047 | I-RJ-RAPR-PMP-0023 | IRJ-JAAN-PMP-M-0019 | I-RJ-JAAN-ENB-I008-I-RJ-RAPR-ENB-9047_A6 | 1 | Pali | Sirohi |  |  |  | 26.1084 | 73.9022 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B21 | 2025-11-20 | 2025-11-21 | [37 empty] | JLJH
I-RJ-SMRP-ENB-6008 | I-RJ-SMRP-PMP-0017 | I-RJ-SMRP-ENB-V001 | I-RJ-SMRP-PMP-0030 | IRJ-SMRP-PMP-M-0017 | I-RJ-SMRP-ENB-6008-I-RJ-SMRP-ENB-V001_A6 | 1 | Pali | Sirohi |  |  |  | 25.1525 | 73.0808 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B21 | 2025-11-20 | 2025-11-21 | [37 empty] | JLJH
I-RJ-SNCE-ENB-I028 | I-RJ-SNCE-PMP-0046 | I-RJ-SNCE-ENB-V001 | I-RJ-SNCE-PMP-0066 | IRJ-SNCE-PMP-M-0046 | I-RJ-SNCE-ENB-I028-I-RJ-SNCE-ENB-V001_A6 | 1 | Jalor | Sirohi |  |  |  | 24.7569 | 71.7732 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B21 | 2025-11-20 | 2025-11-21 | [37 empty] | JLJH
I-RJ-SMRP-ENB-W001 | I-RJ-SMRP-PMP-0004 | I-RJ-SMRP-ENB-9056 | I-RJ-SMRP-PMP-0020 | IRJ-SMRP-PMP-M-0004 | I-RJ-SMRP-ENB-W001-I-RJ-SMRP-ENB-9056_A6 | 1 | Pali | Sirohi |  |  |  | 25.3013 | 73.1773 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B21 | 2025-11-20 | 2025-11-21 | [37 empty] | JLJH
I-RJ-PNDW-ENB-9055 | I-RJ-PNDW-PMP-0017 | I-RJ-PNDW-ENB-I010 | I-RJ-PNDW-PMP-0051 | IRJ-PNDW-PMP-M-0017 | I-RJ-PNDW-ENB-9055-I-RJ-PNDW-ENB-I010_A6 | 1 | Sirohi | Sirohi |  |  |  | 24.7945 | 73.0494 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B21 | 2025-11-20 | 2025-11-21 | [37 empty] | JLJH
I-RJ-PNDW-ENB-9055 | I-RJ-PNDW-PMP-0017 | I-RJ-PNDW-ENB-I011 | I-RJ-PNDW-PMP-0048 | IRJ-PNDW-PMP-M-0017 | I-RJ-PNDW-ENB-9055-I-RJ-PNDW-ENB-I011_A6 | 1 | Sirohi | Sirohi |  |  |  | 24.7945 | 73.0494 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B21 | 2025-11-20 | 2025-11-21 | [37 empty] | JLJH
I-RJ-MKRN-ENB-9051 | I-RJ-MKRN-PMP-0033 | I-RJ-MKRN-ENB-9060 | I-RJ-MKRN-PMP-0053 | I-RJ-MKRN-PMP-0033 | I-RJ-MKRN-ENB-9051-I-RJ-MKRN-ENB-9060_A6 | 1 | Makrana | Nagaur |  |  |  | 27.1483 | 74.7819 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Barwala | [13 empty] | JLJH
I-RJ-DENA-ENB-I008 | I-RJ-DENA-PMP-0033 | I-RJ-PASS-ENB-9039 | I-RJ-PASS-PMP-0028 | I-RJ-DENA-PMP-0033 | I-RJ-DENA-ENB-I008-I-RJ-PASS-ENB-9039_A6 | 1 | Makrana | Nagaur |  |  |  | 26.7845 | 74.4364 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Mahrana | [13 empty] | JLJH
I-RJ-MKRN-ENB-I014 | I-RJ-MKRN-PMP-0042 | I-RJ-MKRN-ENB-9040 | I-RJ-MKRN-PMP-0061 | I-RJ-MKRN-PMP-0042 | I-RJ-MKRN-ENB-I014-I-RJ-MKRN-ENB-9040_A6 | 1 | Makrana | Nagaur |  |  |  | 27.0824 | 74.4734 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Beenjari | [13 empty] | JLJH
I-RJ-SNNU-ENB-I001 | I-RJ-SNNU-PMP-0001 | I-RJ-SNNU-ENB-I002 | I-RJ-SNNU-PMP-0003 | I-RJ-SNNU-PMP-0001 | I-RJ-SNNU-ENB-I001-I-RJ-SNNU-ENB-I002_A6 | 1 | Sirohi | Sirohi |  |  |  | 24.4981 | 72.7907 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Maanpur | [13 empty] | JLJH
I-RJ-JAAL-ENB-I016 | I-RJ-JAAL-PMP-0025 | I-RJ-JAAL-ENB-9055 | I-RJ-JAAL-PMP-0060 | I-RJ-JAAL-PMP-0025 | I-RJ-JAAL-ENB-I016-I-RJ-JAAL-ENB-9055_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.1418 | 74.1942 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | UCHAIRA | [13 empty] | JLJH
I-RJ-NAWW-ENB-A001 | I-RJ-NAWW-PMP-0019 | I-RJ-NAWW-ENB-9066 | I-RJ-NAWW-PMP-0068 | I-RJ-NAWW-PMP-0019 | I-RJ-NAWW-ENB-A001-I-RJ-NAWW-ENB-9066_A6 | 1 | Makrana | Nagaur |  |  |  | 27.0619 | 74.9168 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Bangla Wala | [13 empty] | JLJH
I-RJ-DDWN-ENB-I004 | I-RJ-DDWN-PMP-0018 | I-RJ-DDWN-ENB-9081 | I-RJ-DDWN-PMP-0071 | I-RJ-DDWN-PMP-0018 | I-RJ-DDWN-ENB-I004-I-RJ-DDWN-ENB-9081_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.1013 | 74.3611 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | PAWA | [13 empty] | JLJH
I-RJ-GJSP-ENB-I001 | I-RJ-GJSP-PMP-0002 | I-RJ-RSNG-ENB-9076 | I-RJ-RSNG-PMP-0053 | I-RJ-GJSP-PMP-0002 | I-RJ-GJSP-ENB-I001-I-RJ-RSNG-ENB-9076_A6 | 1 | Suratgarh | Ganganagar |  |  |  | 29.656 | 73.4436 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | GAJSING PURA | [13 empty] | JLKD
I-RJ-SEGN-ENB-I005 | I-RJ-SEGN-PMP-0021 | I-RJ-SEGN-ENB-9035 | I-RJ-SEGN-PMP-0035 | I-RJ-SEGN-PMP-0021 | I-RJ-SEGN-ENB-I005-I-RJ-SEGN-ENB-9035_A6 | 1 | Sirohi | Sirohi |  |  |  | 25.1296 | 73.0551 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Sheoganj-3 | [13 empty] | JLJH
I-RJ-RNWR-ENB-9030 | I-RJ-RNWR-PMP-0006 | I-RJ-RNWR-ENB-9051 | I-RJ-RNWR-PMP-0034 | I-RJ-RNWR-PMP-0006 | I-RJ-RNWR-ENB-9030-I-RJ-RNWR-ENB-9051_A6 | 1 | Jalor | Sirohi |  |  |  | 24.761 | 72.1159 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Heerapura Raniwara | [13 empty] | JLJH
I-RJ-ANUG-ENB-I014 | I-RJ-ANUG-PMP-0015 | I-RJ-ANUG-ENB-9072 | I-RJ-ANUG-PMP-0034 | I-RJ-ANUG-PMP-0015 | I-RJ-ANUG-ENB-I014-I-RJ-ANUG-ENB-9072_A6 | 1 | Suratgarh | Ganganagar |  |  |  | 29.274 | 73.226 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | 24 APA | [13 empty] | JLKD
I-RJ-SNCE-ENB-9086 | I-RJ-SNCE-PMP-0016 | I-RJ-SNCE-ENB-9105 | I-RJ-SNCE-PMP-0071 | I-RJ-SNCE-PMP-0016 | I-RJ-SNCE-ENB-9086-I-RJ-SNCE-ENB-9105_A6 | 1 | Jalor | Sirohi |  |  |  | 24.8478 | 71.7276 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B22 | 2025-12-12 | 2025-12-13 | [23 empty] | Dawal | [13 empty] | JLJH
I-RJ-ANGR-ENB-H001 | I-RJ-ANGR-PMP-0013 | I-RJ-ANGR-ENB-I001 | I-RJ-ANGR-PMP-0030 | I-RJ-ANGR-PMP-0013 | I-RJ-ANGR-ENB-H001-I-RJ-ANGR-ENB-I001_A6 | 1 | Suratgarh | Ganganagar |  |  |  | 28.9361 | 72.9613 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B23 | 2026-02-11 | 2026-02-11 | [37 empty] | JLKD
I-RJ-PLBG-ENB-9004 | I-RJ-PLBG-PMP-0005 | I-RJ-SRGR-ENB-9104 | I-RJ-SRGR-PMP-0084 | I-RJ-PLBG-PMP-0005 | I-RJ-PLBG-ENB-9004-I-RJ-SRGR-ENB-9104_A6 | 1 | Suratgarh | Ganganagar |  |  |  | 29.4943 | 73.8752 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B23 | 2026-02-13 | 2026-02-13 | [37 empty] | JLKD
I-RJ-MENW-ENB-9008 | I-RJ-MENW-PMP-0001 | I-RJ-MENW-ENB-9008 | I-RJ-MENW-PMP-0008 | I-RJ-MENW-PMP-0001 | I-RJ-MENW-ENB-6000-I-RJ-MENW-ENB-9008_A6 | 1 | Nagaur | Nagaur |  |  |  | 26.6542 | 73.7347 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Gothan | [13 empty] | JLJH
I-RJ-SMRP-ENB-9046 | #N/A | I-RJ-SMRP-ENB-9046 | I-RJ-SMRP-PMP-0032 | #N/A | I-RJ-SMRP-ENB-I001-I-RJ-SMRP-ENB-9046_A6 | 1 | Pali | Sirohi |  |  |  | 25.2526 | 73.1451 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Sindru | [13 empty] | JLJH
I-RJ-RAPR-ENB-9036 | I-RJ-RAPR-PMP-0030 | I-RJ-RAPR-ENB-9036 | I-RJ-RAPR-PMP-0032 | I-RJ-RAPR-PMP-0030 | I-RJ-RAPR-ENB-9045-I-RJ-RAPR-ENB-9036_A6 | 1 | Pali | Sirohi |  |  |  | 25.9709 | 74.0221 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Gram Khiwal | [13 empty] | JLJH
I-RJ-REAR-ENB-9017 | I-RJ-REAR-PMP-0013 | I-RJ-REAR-ENB-9017 | I-RJ-REAR-PMP-0038 | I-RJ-REAR-PMP-0013 | I-RJ-REAR-ENB-I002-I-RJ-REAR-ENB-9017_A6 | 1 | Sirohi | Sirohi |  |  |  | 24.7306 | 72.4344 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | NIMBAJ | [13 empty] | JLJH
I-RJ-RNWR-ENB-I005 | I-RJ-KDRD-PMP-0001 | I-RJ-RNWR-ENB-I005 | I-RJ-RNWR-PMP-0032 | I-RJ-KDRD-PMP-0001 | I-RJ-KDRD-ENB-6000-I-RJ-RNWR-ENB-I005_A6 | 1 | Jalor | Sirohi |  |  |  | 24.8898 | 72.0926 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | KARDA | [13 empty] | JLJH
I-RJ-SNCE-ENB-6003 | I-RJ-SNCE-PMP-0041 | I-RJ-SNCE-ENB-6003 | I-RJ-SNCE-PMP-0074 | I-RJ-SNCE-PMP-0041 | I-RJ-SNCE-ENB-I019-I-RJ-SNCE-ENB-6003_A6 | 1 | Jalor | Sirohi |  |  |  | 24.7628 | 71.8362 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Hadetar | [13 empty] | JLJH
I-RJ-PASS-ENB-I005 | I-RJ-PASS-PMP-0020 | I-RJ-PASS-ENB-I005 | I-RJ-PASS-PMP-0038 | I-RJ-PASS-PMP-0020 | I-RJ-PASS-ENB-G005-I-RJ-PASS-ENB-I005_A6 | 1 | Makrana | Nagaur |  |  |  | 26.8099 | 74.5902 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Bagot | [13 empty] | JLJH
I-RJ-PALI-ENB-9032 | I-RJ-KKNI-PMP-0003 | I-RJ-PALI-ENB-9032 | I-RJ-PALI-PMP-0101 | I-RJ-KKNI-PMP-0003 | I-RJ-KKNI-ENB-6003-I-RJ-PALI-ENB-9032_A6 | 1 | Pali | Sirohi |  |  |  | 25.8778 | 73.3427 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Nimbali | [13 empty] | JLJH
I-RJ-MAJN-ENB-9047 | I-RJ-MAJN-PMP-0001 | I-RJ-MAJN-ENB-9047 | I-RJ-MAJN-PMP-0045 | I-RJ-MAJN-PMP-0001 | I-RJ-MAJN-ENB-6002-I-RJ-MAJN-ENB-9047_A6 | 1 | Pali | Sirohi |  |  |  | 25.7894 | 73.8329 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | KANTALIYA | [13 empty] | JLJH
I-RJ-SRHI-ENB-9006 | I-RJ-PNDW-PMP-0012 | I-RJ-SRHI-ENB-9006 | I-RJ-SRHI-PMP-0053 | I-RJ-PNDW-PMP-0012 | I-RJ-PNDW-ENB-9027-I-RJ-SRHI-ENB-9006_A6 | 1 | Sirohi | Sirohi |  |  |  | 24.8678 | 72.9362 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Naya Sanwara | [13 empty] | JLJH
I-RJ-LDNU-ENB-I020 | I-RJ-LDNU-PMP-0011 | I-RJ-LDNU-ENB-I020 | I-RJ-LDNU-PMP-0054 | I-RJ-LDNU-PMP-0011 | I-RJ-LDNU-ENB-6005-I-RJ-LDNU-ENB-I020_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.6413 | 74.3907 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | LADNU-RJ6LDNUN0001G | [13 empty] | JLJH
I-RJ-LDNU-ENB-I005 | I-RJ-LDNU-PMP-0021 | I-RJ-LDNU-ENB-I005 | I-RJ-LDNU-PMP-0050 | I-RJ-LDNU-PMP-0021 | I-RJ-LDNU-ENB-9053-I-RJ-LDNU-ENB-I005_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.5339 | 74.456 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Gunpaliya | [13 empty] | JLJH
I-RJ-SMRP-ENB-9037 | #N/A | I-RJ-SMRP-ENB-9037 | I-RJ-SMRP-PMP-0033 | #N/A | I-RJ-SMRP-ENB-I001-I-RJ-SMRP-ENB-9037_A6 | 1 | Pali | Sirohi |  |  |  | 25.2526 | 73.1451 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B24 | 2026-02-14 | [24 empty] | Sindru | [13 empty] | JLJH
I-RJ-JAAL-ENB-6006 | I-RJ-JAAL-PMP-0003 | I-RJ-JAAL-ENB-9066 | I-RJ-JAAL-PMP-0046 | I-RJ-JAAL-PMP-0003 | I-RJ-JAAL-ENB-6006-I-RJ-JAAL-ENB-9066_A6 | 1 | Ladnu | nagaur |  |  |  | 27.1256 | 74.3149 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B25 | 2026-02-20 | [38 empty] | JLJH
I-RJ-JAAW-ENB-6004 | I-RJ-JAAW-PMP-0005 | I-RJ-JAAW-ENB-9036 | I-RJ-JAAW-PMP-0025 | I-RJ-JAAW-PMP-0005 | I-RJ-JAAW-ENB-6004-I-RJ-JAAW-ENB-9036_A6 | 1 | Jalor | sirohi |  |  |  | 25.2226 | 72.0922 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B25 | 2026-02-20 | [38 empty] | JLJH
I-RJ-BNML-ENB-6004 | I-RJ-BNML-PMP-0003 | I-RJ-BHAS-ENB-H001 | I-RJ-BHAS-PMP-0002 | I-RJ-BNML-PMP-0003 | I-RJ-BNML-ENB-6004-I-RJ-BHAS-ENB-H001_A6 | 1 | Jalor | sirohi |  |  |  | 24.8137 | 72.456 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B25 | 2026-02-20 | [38 empty] | JLJH
I-RJ-DDWN-ENB-6015 | I-RJ-DDWN-PMP-0003 | I-RJ-DDWN-ENB-I005 | I-RJ-DDWN-PMP-0058 | I-RJ-DDWN-PMP-0003 | I-RJ-DDWN-ENB-6015-I-RJ-DDWN-ENB-I005_A6 | 1 | Ladnu | nagaur |  |  |  | 27.3511 | 74.4682 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B25 | 2026-02-20 | [38 empty] | JLJH
I-RJ-DDWN-ENB-I016 | I-RJ-DDWN-PMP-0021 | I-RJ-DDWN-ENB-I022 | I-RJ-DDWN-PMP-0066 | I-RJ-DDWN-PMP-0021 | I-RJ-DDWN-ENB-I016-I-RJ-DDWN-ENB-I022_A6 | 1 | Ladnu | nagaur |  |  |  | 27.1657 | 74.4475 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B25 | 2026-02-20 | [38 empty] | JLJH
I-RJ-BSBM-ENB-9003 | I-RJ-BSBM-PMP-0001 | I-RJ-BSBM-ENB-I003 | I-RJ-BSBM-PMP-0003 | I-RJ-BSBM-PMP-0001 | I-RJ-BSBM-ENB-9003-I-RJ-BSBM-ENB-I003_A6 | 1 | Nagaur | Nagaur |  |  |  | 27.1711 | 73.6482 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B26 | 2026-03-10 | 2026-03-12 | [23 empty] | Basni Belima | [13 empty] | JLJH
I-RJ-SRHI-ENB-6000 | I-RJ-SRHI-PMP-0001 | I-RJ-JADE-ENB-9002 | I-RJ-JADE-PMP-0002 | I-RJ-SRHI-PMP-0001 | I-RJ-SRHI-ENB-6000-I-RJ-JADE-ENB-9002_A6 | 1 | Sirohi | Sirohi |  |  |  | 24.9907 | 72.757 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B26 | 2026-03-10 | 2026-03-12 | [23 empty] | JAWAL | [13 empty] | JLJH
I-RJ-RSNG-ENB-B001 | I-RJ-RSNG-PMP-0016 | I-RJ-RSNG-ENB-V002 | I-RJ-RSNG-PMP-0051 | I-RJ-RSNG-PMP-0016 | I-RJ-RSNG-ENB-B001-I-RJ-RSNG-ENB-V002_A6 | 1 | Suratgarh | Ganganagar |  |  |  | 29.5342 | 73.4517 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B26 | 2026-03-10 | 2026-03-12 | [23 empty] | Raisinghnagar | [13 empty] | JLKD
I-RJ-SMRP-ENB-S001 | I-RJ-SMRP-PMP-0016 | I-RJ-SMRP-ENB-9048 | I-RJ-SMRP-PMP-0034 | I-RJ-SMRP-PMP-0016 | I-RJ-SMRP-ENB-S001-I-RJ-SMRP-ENB-9048_A6 | 1 | Pali | Sirohi |  |  |  | 25.4493 | 73.2294 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B26 | 2026-03-10 | 2026-03-12 | [23 empty] | Dhola Ka Gaon | [13 empty] | JLJH
I-RJ-LDNU-ENB-9043 | I-RJ-LDNU-PMP-0038 | I-RJ-LDNU-ENB-9019 | I-RJ-LDNU-PMP-0038 | I-RJ-LDNU-PMP-0038 | I-RJ-LDNU-ENB-9043-I-RJ-LDNU-ENB-9019_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.6234 | 74.4591 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B26 | 2026-03-10 | 2026-03-12 | [23 empty] | Dabri | [13 empty] | JLJH
I-RJ-BNML-ENB-9063 | I-RJ-BNML-PMP-0010 | I-RJ-BNML-ENB-9012 | I-RJ-BNML-PMP-0021 | I-RJ-BNML-PMP-0010 | I-RJ-BNML-ENB-9063-I-RJ-BNML-ENB-9012_A6 | 1 | Jalor | Sirohi |  |  |  | 25.0686 | 72.4125 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B26 | 2026-03-10 | 2026-03-12 | [23 empty] | Rota | [13 empty] | JLJH
I-RJ-JAAN-ENB-9014 | I-RJ-JAAN-PMP-0006 | I-RJ-JAAN-ENB-9023 | I-RJ-JAAN-PMP-0024 | I-RJ-JAAN-PMP-0006 | I-RJ-JAAN-ENB-9014-I-RJ-JAAN-ENB-9023_A6 | 1 | Pali | Sirohi |  |  |  | 26.3467 | 74.1256 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B26 | 2026-03-10 | 2026-03-12 | [23 empty] | Rabadiyawas | [13 empty] | JLJH
I-RJ-NGUR-ENB-6005 | I-RJ-NGUR-PMP-0026 | I-RJ-NGUR-ENB-9087 | I-RJ-NGUR-PMP-0092 | I-RJ-NGUR-PMP-0026 | I-RJ-NGUR-ENB-6005-I-RJ-NGUR-ENB-9087_A6 | 1 | Nagaur | Nagaur |  |  |  | 27.089 | 73.6455 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Kharnal | [13 empty] | JLJH
I-RJ-MKRN-ENB-9051 | I-RJ-MKRN-PMP-0033 | I-RJ-MKRN-ENB-9064 | I-RJ-MKRN-PMP-0062 | I-RJ-MKRN-PMP-0033 | I-RJ-MKRN-ENB-9051-I-RJ-MKRN-ENB-9064_A6 | 1 | Makrana | Nagaur |  |  |  | 27.1483 | 74.7819 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Barwala | [13 empty] | JLJH
I-RJ-RNWR-ENB-I002 | I-RJ-RNWR-PMP-0016 | I-RJ-RNWR-ENB-9026 | I-RJ-RNWR-PMP-0031 | I-RJ-RNWR-PMP-0016 | I-RJ-RNWR-ENB-I002-I-RJ-RNWR-ENB-9026_A6 | 1 | Jalor | Sirohi |  |  |  | 24.7493 | 72.2099 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | RaniwaraInfill | [13 empty] | JLJH
I-RJ-JAAN-ENB-9050 | I-RJ-JAAN-PMP-0030 | I-RJ-JAAN-ENB-9073 | I-RJ-JAAN-PMP-0046 | I-RJ-JAAN-PMP-0030 | I-RJ-JAAN-ENB-9050-I-RJ-JAAN-ENB-9073_A6 | 1 | Pali | Sirohi |  |  |  | 26.2351 | 74.1138 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Village- Toonkara | [13 empty] | JLJH
I-RJ-BORA-ENB-I003 | I-RJ-BORA-PMP-0010 | I-RJ-BNML-ENB-9079 | I-RJ-BNML-PMP-0031 | I-RJ-BORA-PMP-0010 | I-RJ-BORA-ENB-I003-I-RJ-BNML-ENB-9079_A6 | 1 | Jalor | Sirohi |  |  |  | 25.088 | 71.9618 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | MEDA BRAHMNAN | [13 empty] | JLJH
I-RJ-BKRI-ENB-6000 | I-RJ-BKRI-PMP-0001 | I-RJ-JLOR-ENB-I011 | I-RJ-JLOR-PMP-0055 | I-RJ-BKRI-PMP-0001 | I-RJ-BKRI-ENB-6000-I-RJ-JLOR-ENB-I011_A6 | 1 | Jalor | Sirohi |  |  |  | 25.2522 | 72.4591 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Bakra | [13 empty] | JLJH
I-RJ-JAAL-ENB-H001 | I-RJ-JAAL-PMP-0022 | I-RJ-JAAL-ENB-9058 | I-RJ-JAAL-PMP-0061 | I-RJ-JAAL-PMP-0022 | I-RJ-JAAL-ENB-H001-I-RJ-JAAL-ENB-9058_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.4562 | 73.9137 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Jalniyasar | [13 empty] | JLJH
I-RJ-JAAN-ENB-9014 | I-RJ-JAAN-PMP-0006 | I-RJ-JAAN-ENB-9047 | I-RJ-JAAN-PMP-0045 | I-RJ-JAAN-PMP-0006 | I-RJ-JAAN-ENB-9014-I-RJ-JAAN-ENB-9047_A6 | 1 | Pali | Sirohi |  |  |  | 26.3467 | 74.1256 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Rabadiyawas | [13 empty] | JLJH
I-RJ-NAWW-ENB-9021 | I-RJ-NAWW-PMP-0001 | I-RJ-NAWW-ENB-9090 | I-RJ-NAWW-PMP-0071 | I-RJ-NAWW-PMP-0001 | I-RJ-NAWW-ENB-9021-I-RJ-NAWW-ENB-9090_A6 | 1 | Makrana | Nagaur |  |  |  | 27.1455 | 74.939 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Bhanwata | [13 empty] | JLJH
I-RJ-PNDW-ENB-9066 | I-RJ-PNDW-PMP-0021 | I-RJ-PNDW-ENB-9015 | I-RJ-PNDW-PMP-0055 | I-RJ-PNDW-PMP-0021 | I-RJ-PNDW-ENB-9066-I-RJ-PNDW-ENB-9015_A6 | 1 | Sirohi | Sirohi |  |  |  | 24.7512 | 72.9988 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Kojra pindwara | [13 empty] | JLJH
I-RJ-JAAL-ENB-9082 | I-RJ-JAAL-PMP-0013 | I-RJ-NGUR-ENB-9084 | I-RJ-NGUR-PMP-0112 | I-RJ-JAAL-PMP-0013 | I-RJ-JAAL-ENB-9082-I-RJ-NGUR-ENB-9084_A6 | 1 | Nagaur | Nagaur |  |  |  | 27.3066 | 73.9044 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Jayal | [13 empty] | JLJH
I-RJ-NAWW-ENB-9071 | I-RJ-NAWW-PMP-0009 | I-RJ-NAWW-ENB-9096 | I-RJ-NAWW-PMP-0070 | I-RJ-NAWW-PMP-0009 | I-RJ-NAWW-ENB-9071-I-RJ-NAWW-ENB-9096_A6 | 1 | Makrana | Nagaur |  |  |  | 27.0613 | 75.0469 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | BHAGANPURA | [13 empty] | JLJH
I-RJ-JAAL-ENB-G004 | I-RJ-JAAL-PMP-0053 | I-RJ-JAAL-ENB-9053 | I-RJ-JAAL-PMP-0033 | I-RJ-JAAL-PMP-0053 | I-RJ-JAAL-ENB-G004-I-RJ-JAAL-ENB-9053_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.2454 | 74.0934 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Dugastau | [13 empty] | JLJH
I-RJ-DDWN-ENB-6015 | I-RJ-DDWN-PMP-0003 | I-RJ-DDWN-ENB-9083 | I-RJ-DDWN-PMP-0043 | I-RJ-DDWN-PMP-0003 | I-RJ-DDWN-ENB-6015-I-RJ-DDWN-ENB-9083_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.3511 | 74.4682 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Koliya | [13 empty] | JLJH
I-RJ-SMRP-ENB-9044 | I-RJ-SMRP-PMP-0008 | I-RJ-SMRP-ENB-9036 | I-RJ-SMRP-PMP-0026 | I-RJ-SMRP-PMP-0008 | I-RJ-SMRP-ENB-9044-I-RJ-SMRP-ENB-9036_A6 | 1 | Pali | Sirohi |  |  |  | 25.1511 | 73.0867 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | BhairuChowkRoad | [13 empty] | JLJH
I-RJ-BNML-ENB-6005 | I-RJ-BNML-PMP-0004 | I-RJ-BNML-ENB-9066 | I-RJ-BNML-PMP-0020 | I-RJ-BNML-PMP-0004 | I-RJ-BNML-ENB-6005-I-RJ-BNML-ENB-9066_A6 | 1 | Jalor | Sirohi |  |  |  | 25.1805 | 72.4312 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Narpara | [13 empty] | JLJH
I-RJ-JAAL-ENB-G004 | I-RJ-JAAL-PMP-0053 | I-RJ-JAAL-ENB-9074 | I-RJ-JAAL-PMP-0030 | I-RJ-JAAL-PMP-0053 | I-RJ-JAAL-ENB-G004-I-RJ-JAAL-ENB-9074_A6 | 1 | Ladnu | Nagaur |  |  |  | 27.2454 | 74.0934 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | Dugastau | [13 empty] | JLJH
I-RJ-BALI-ENB-A003 | I-RJ-BALI-PMP-0009 | I-RJ-BALI-ENB-9009 | I-RJ-BALI-PMP-0030 | I-RJ-BALI-PMP-0009 | I-RJ-BALI-ENB-A003-I-RJ-BALI-ENB-9009_A6 | 1 | Pali | Sirohi |  |  |  | 25.3146 | 73.2742 | GBT | 0 | UBR I&C |  |  | ALLOTMENT B27 | 2026-03-13 | 2026-03-13 | [23 empty] | KHEEMEL | [13 empty] | JLJH

## WORK ORDER STATUS
ACTIVITY |  | PO/CO Given to You |  |  | Billing Done and you got payment |  | Files submitted to QSD and payment pending |  | Files submitted to ISP Deployment |  | Work done by you and file submission pending
| S.No. | PO/CO number | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount | Qty | Amount
AIRFIBER | 1 | 540081672 | 190 | 1308150 | 165 | 1114928 | 0 | 0 | 0 | 0 | 0 | 0
AIRFIBER | 2 | 540087816 | 82 | 933570 | 119 | 648722 | 32 | 168610 | 11 | 65882 | 0 | 0
PB SWAP | 3 | 630310259 | 83 | 1444500 | 0 | 0 | 29 | 250806 | 25 | 338322 | 0 | 0
BSA DISMANTLE | 4 | 630312399 | 6 | 48144 | 0 | 0 | 6 | 44004 | 0 | 0 | 0 | 0
AIRFIBER | 5 | 630312070 | 36 | 282808 | 0 | 0 | 4 | 26607 | 3 | 13377 | 0 | 0
AIRFIBER | 6 | 630314171 | 151 | 1275338 | 0 | 0 | 5 | 33782 | 2 | 10616 | 0 | 0
AIRFIBER | 7 | 630315889 | 894 | 5116890 | 0 | 0 | 104 | 658094 | 78 | 464054 | 0 | 0
AIRFIBER | 8 | 630317697 | 164 | 1553674 | 0 | 0 | 59 | 381319 | 8 | 51248 | 0 | 0
AIRFIBER | 9 | 630322732 | 62 | 594250 | 0 | 0 | 0 | 0 | 27 | 199313 | 1 | 5200
AIRFIBER | 10 | 630319006 | 5 | 61710 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2200
AIRFIBER | 11 | 630324754 | 4 | 50420 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11408
A6+B6 | 12 | 630322047 | 23 | 414135 | 0 | 0 | 0 | 0 | 18 | 349680 | 0 | 0
A6+B6 | 13 | 630324788 | 102 | 982740 | 0 | 0 | 0 | 0 | 26 | 471780 | 0 | 0
PB SWAP | 14 | 630325435 | 161 | 1406080 | 0 | 0 | 0 | 0 | 25 | 158770 | 0 | 0
BSA DISMANTLE | 15 | 630318642 | 36 | 320020 | 0 | 0 | 0 | 0 | 36 | 312000 | 0 | 0
MM WAVE | 16 | 630326916 | 51 | 387775 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 9880
|  | 9904636293 | 2050 | 16180204 | 284 | 1763650 | 239 | 1563222 | 259 | 2435042 | 5 | 28688

## HOTO NUMBER
JC NAME | CMP NAME | HOTO REPRESENTATIVE NAME | NO
GANGAPUR CITY | KOTA | ASAD | 70144 10037
SAWAI MADHOPUR | KOTA | GIRIRAJ | 8824142510
BUNDI | KOTA | JALALUDDIN | 98751 79387
JHALAWAR | KOTA | NIKHIL | 79 7659 8409
MANOHAR THANA | KOTA | NIKHIL | 79 7659 8409
KOTA | KOTA | BHUVNESH | 7023903349
BARAN | KOTA | DHANRAJ | 861 910 5552
HANUMANGARH | GANGANAGAR | HANIF | 81048 30786
GANGANAGAR | GANGANAGAR | SUKHVINDER | 83879 72881
SURATGARH | GANGANAGAR | RAGHUVEER | 6375740019
KISHANGARH | AJMER | SONU | 99280 87334
AJMER | AJMER | SONU | 99280 87334
BEAWAR | AJMER | SONU | 99280 87334
TONK | AJMER | SONU | 99280 87334
NAGAUR | NAGAUR | PRATIK | 79 7615 2530
| NAGAUR | PRATIK | 79 7615 2530
| NAGAUR | PRATIK | 79 7615 2530

## TOOLS DETAILS
TOOLS REQUIRED FOR AIRFIBER I&C (MINIMUM 2 PERSON REQUIRED)
FULL BODY HARNESS | 2 SET PER TEAM
RASSA-PULLY(ANY) | 100M
SAFETY SHOES | PER PERSON
SAFETY HELMET | PER PERSON
REFLECTIVE JACKET | PER PERSON
MULTIMETER | 1 PCS PER TEAM
SPANNER SET 10 TO 15 NO | 1 SET PER TEAM
L&KEY | 1 SET PER TEAM
COMPASS | 1 SET PER TEAM
MEASURING TAPE 60M | 1 SET PER TEAM
TAPARIA SET | 1 SET PER TEAM
PLIAR | 1
TIE CUTTER | 1
KNIFE | 1