## Main WCC
Work Completion Certificate
State |  | RAJASTHAN |  |  |  | Maintenance Point | Jaipur
Project Type |  | 93 K | Infill | Growth | Other (Specify) _________________________ |  | Air Fiber Installation
ZXZ
Site Type |  | Own Built | IP Colo | RP1 | BSNL | MAG1 NLD AG1
Tower type |  | GBT | RTT | RTP | GBM | NBT Other (Specify) _________________________________ |  | Air Fiber Installation
This is to certify that work has been completed as per specification given in workorder on the sites mentioned
The required ITP / Checklists are available and verified in system
Site Name |  | As per Annexture |  |  |  | SAP ID | As per Annexture
W.O.Number |  | P14/630330726 |  |  |  | Vendor Name M/S. | DIGITCOM INDIA TECHNOLOGIES
No of Sites |  | 22 SITES |  |  |  | Completion Date | 30-JAN-26 TO 04-FEB-26
| Vendor Representative |  |  |  |  | RJIL Representative
| Name | ANKUSH SRIVASTAVA |  |  |  | Name | MR. Manish Nahar
| Sign |  |  |  |  | Sign
| Date |  |  |  |  | Date
Remarks, if any:
| Note : | In case of Multiple sites, please attach applicable site details with this certificate

## WCC
Work Completion Certificate
This is to certify that below sites pertaining to WO/WCO No.P14/630330726 Dated in 03-10-2025 respect of Digitcom India Technologies has been successfully completed in all respect.
Sr. No | ENB SITE ID | PMP SAP ID | GIS SECTOR_ID | No of Sectors | Tower type | JC | WH | VEHICLE NO | MIN NO | MIN Date | Completion Date | REMARKS | ACTUAL KM | KM IN WO | GAP | USED KM IN WCC
1 | I-RJ-MRTA-ENB-9036 | I-RJ-MRTA-PMP-0053 | I-RJ-MRTA-ENB-9036-3 | 1 | GBT | Nagaur | JLJH | RJ21GA6945 | 255623353 | 2026-01-29 | 2026-01-31 | RFS DONE | 14 | 126 |  | 14
2 | I-RJ-DENA-ENB-6083 | I-RJ-DENA-PMP-0006 | I-RJ-DENA-ENB-6083-1 | 1 | GBT | Makrana | JLJH | RJ21GA6945 | 275977438 | 2026-01-29 | 2026-01-31 | RFS DONE | 126 | 193 |  | 126
3 | I-RJ-PASS-ENB-9017 | I-RJ-PASS-PMP-0007 | I-RJ-PASS-ENB-9017-1 | 1 | GBT | Makrana | JLJH | RJ21GA6945 | 275977591 | 2026-01-29 | 2026-01-31 | RFS DONE | 35 | 216 |  | 35
4 | I-RJ-PASS-ENB-9023 | I-RJ-PASS-PMP-0008 | I-RJ-PASS-ENB-9023-1 | 1 | GBT | Makrana | JLJH | RJ21GA6945 | 275977592 | 2026-01-29 | 2026-01-31 | RFS DONE | 5 | 218 |  | 5
5 | I-RJ-KESR-ENB-V001 | I-RJ-KESR-PMP-0018 | I-RJ-KESR-ENB-V001-2 | 1 | GBT | Nagaur | JLJH | RJ21GA6945 | 275991865 | 2026-01-29 | 2026-02-04 | RFS DONE | 62 | 128 |  | 62
6 | I-RJ-DDWN-ENB-9017 | I-RJ-DDWN-PMP-0062 | I-RJ-DDWN-ENB-9017-2 | 1 | GBT | Ladnu | JLJH | RJ21GA6945 | 256653182 | 2026-01-29 | 2026-02-02 | RFS DONE | 167 | 229 |  | 167
7 | I-RJ-MKRN-ENB-9035 | I-RJ-MKRN-PMP-0030 | I-RJ-MKRN-ENB-9035-1 | 1 | GBT | Makrana | JLJH | RJ21GA6945 | 275977586 | 2026-01-29 | 2026-02-02 | RFS DONE | 30 | 247 |  | 30
8 | I-RJ-JAAW-ENB-6003 | I-RJ-JAAW-PMP-0004 | I-RJ-JAAW-ENB-6003-3 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977441 | 2026-01-29 | 2026-02-02 | RFS DONE | 114 | 179 |  | 114
9 | I-RJ-JAAW-ENB-6004 | I-RJ-JAAW-PMP-0005 | I-RJ-JAAW-ENB-6004-2-3 | 2 | GBT | Jalor | JLJH | RJ21GA6945 | 275977552 | 2026-01-29 | 2026-01-31 | RFS DONE | 8 | 184 |  | 8
10 | I-RJ-SNCE-ENB-9092 | I-RJ-SNCE-PMP-0017 | I-RJ-SNCE-ENB-9092-1-2-3 | 3 | GBT | Jalor | JLJH | RJ21GA6945 | 275977597 | 2026-01-29 | 2026-02-02 | RFS DONE | 40 | 221 |  | 40
11 | I-RJ-BORA-ENB-6003 | I-RJ-BORA-PMP-0004 | I-RJ-BORA-ENB-6003-1 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977435 | 2026-01-29 | 2026-01-30 | RFS DONE | 168 | 212 |  | 168
12 | I-RJ-BORA-ENB-9028 | I-RJ-BORA-PMP-0021 | I-RJ-BORA-ENB-9028-1 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977437 | 2026-01-29 | 2026-01-31 | RFS DONE | 21 | 193 |  | 21
13 | I-RJ-BNML-ENB-9034 | I-RJ-BNML-PMP-0008 | I-RJ-BNML-ENB-9034-2 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977432 | 2026-01-29 | 2026-01-31 | RFS DONE | 20 | 193 |  | 20
14 | I-RJ-JLOR-ENB-9037 | I-RJ-JLOR-PMP-0016 | I-RJ-JLOR-ENB-9037-3 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977564 | 2026-01-29 | 2026-01-30 | RFS DONE | 71 | 129 |  | 71
15 | I-RJ-BAGA-ENB-6000 | I-RJ-BAGA-PMP-0001 | I-RJ-BAGA-ENB-6000-3 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977429 | 2026-01-29 | 2026-01-30 | RFS DONE | 21 | 150 |  | 21
16 | I-RJ-BNML-ENB-6004 | I-RJ-BNML-PMP-0003 | I-RJ-BNML-ENB-6004-1 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977430 | 2026-01-29 | 2026-01-30 | RFS DONE | 55 | 209 |  | 55
17 | I-RJ-SNCE-ENB-9008 | I-RJ-SNCE-PMP-0005 | I-RJ-SNCE-ENB-9008-2-3 | 2 | GBT | Jalor | JLJH | RJ21GA6945 | 275977593 | 2026-01-29 | 2026-01-31 | RFS DONE | 185 | 254 |  | 185
18 | I-RJ-SNCE-ENB-9036 | I-RJ-SNCE-PMP-0013 | I-RJ-SNCE-ENB-9036-1 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977594 | 2026-01-29 | 2026-01-31 | RFS DONE | 18 | 267 |  | 18
19 | I-RJ-SNCE-ENB-9076 | I-RJ-SNCE-PMP-0014 | I-RJ-SNCE-ENB-9076-3 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977596 | 2026-01-29 | 2026-02-02 | RFS DONE | 31 | 283 |  | 31
20 | I-RJ-KDRD-ENB-6000 | I-RJ-KDRD-PMP-0001 | I-RJ-KDRD-ENB-6000-2 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977585 | 2026-01-29 | 2026-01-30 | RFS DONE | 184 | 222 |  | 184
21 | I-RJ-SNCE-ENB-9107 | I-RJ-SNCE-PMP-0020 | I-RJ-SNCE-ENB-9107-1 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977600 | 2026-01-29 | 2026-01-30 | RFS DONE | 28 | 250 |  | 28
22 | I-RJ-SNCE-ENB-9102 | I-RJ-SNCE-PMP-0019 | I-RJ-SNCE-ENB-9102-3 | 1 | GBT | Jalor | JLJH | RJ21GA6945 | 275977598 | 2026-01-29 | 2026-01-30 | RFS DONE | 15 | 264 |  | 15
SIGN: |  |  | SIGN: | [6 empty] | SIGN:
|  |  | PROJECT-IN-CHARGE | [6 empty] | DEPLOYMENT HEAD
|  |  | MR. YUNUS KHAN | [6 empty] | MR. MANISH NAHAR
DATE: DATE: |  |  | DATE: | [6 empty] | DATE:

## JMS
JMS
Work Order No :P14/630330726
Contractor Name: DIGITCOM INDIA TECHNOLOGIES | [6 empty] | Work Order Dated: 03-10-2025
WO for Airspan A6 and C6 Radios for Airfiber
Service Done From Date: 30-01-26
Service Done To Date: 04-02-26
| Count - |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Code | Site ID -- |  | I-RJ-MRTA-PMP-0053 | I-RJ-DENA-PMP-0006 | I-RJ-PASS-PMP-0007 | I-RJ-PASS-PMP-0008 | I-RJ-KESR-PMP-0018 | I-RJ-DDWN-PMP-0062 | I-RJ-MKRN-PMP-0030 | I-RJ-JAAW-PMP-0004 | I-RJ-JAAW-PMP-0005 | I-RJ-SNCE-PMP-0017 | I-RJ-BORA-PMP-0004 | I-RJ-BORA-PMP-0021 | I-RJ-BNML-PMP-0008 | I-RJ-JLOR-PMP-0016 | I-RJ-BAGA-PMP-0001 | I-RJ-BNML-PMP-0003 | I-RJ-SNCE-PMP-0005 | I-RJ-SNCE-PMP-0013 | I-RJ-SNCE-PMP-0014 | I-RJ-KDRD-PMP-0001 | I-RJ-SNCE-PMP-0020 | I-RJ-SNCE-PMP-0019 | Total Quantity | RATE AS PER SOW | AMOUNT
| Site Type |  | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT
| Sectors |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Item code | Description of Item | UOM
3367489 | CHRG BASE RADIO INST&COMS AZIMUTH | EA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  | 200
3367548 | CHRG LAYING-MULTIMODE FIBER CABLE | M | 5 | 5 | 5 | 5 | 5 | 5 | 50 | 5 | 10 | 60 | 5 | 50 | 5 | 5 | 5 | 5 | 100 | 5 | 50 | 5 | 50 | 50 |  | 5
3137158 | LAYING-2CX2.5SQMM POWER CABLE | M | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 150 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 50 | 50 | 50 | 50 | 50 |  | 12
3397253 | CHRG EXTRA TRANSPORT. > 50 KM (PICKUP | KM | 14 | 126 | 35 | 5 | 62 | 167 | 30 | 114 | 8 | 40 | 168 | 21 | 20 | 71 | 21 | 55 | 185 | 18 | 31 | 184 | 28 | 15 |  | 20
3397271 | CHRG TRANSPORT-UPTO 50KM-SCV-2-3SITE | EA | [23 empty] | 1500 | bar: 1 to Service Done To Date: 04-02-26 22
3367713 | CHRG ATP-11C - WIFI A6 DEPLOYMENT | EA | [23 empty] | 700 | bar: 1 to Service Done To Date: 04-02-26 22
3367739 | CHRG ATP-11A - WIFI A6 DEPLOYMENT | EA | [23 empty] | 700 | bar: 1 to Service Done To Date: 04-02-26 22
3317347 | SITC 1CX6 SQMM CU CBL YY FRLSH | M | [23 empty] | 68
3383067 | CHRG APPLY PUFF SEALENT AT CABLE ENTRY | EA | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 |  | 330
3269867 | TERMINATION OF CABLE 1CX6 SQMM Y | M | [23 empty] | 40
3397248 | EXTRA VISIT | EA
3268025 | INSTALLATION OF POLE MOUNT ON TOWER | EA
TOTAL
SIGN: |  |  | 5: SIGN:; Service Done To Date: 04-02-26 20: SIGN:
[7 empty] | PROJECT-IN-CHARGE | [14 empty] | DEPLOYMENT HEAD
[6 empty] | MR. YUNUS KHAN | [15 empty] | MR. MANISH NAHAR
DATE: DATE: |  |  | 5: DATE:; Service Done To Date: 04-02-26 20: DATE:

## Abstract
Abstract
Work Order No :P14/630330726
Contractor Name: DIGITCOM INDIA TECHNOLOGIES | [15 empty] | Work Order Dated: 03-10-2025
WO for Airspan A6 and C6 Radios for Airfiber
Service Done From Date: 30-01-26
Service Done To Date: 04-02-26
| Count - |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Code | Site ID -- |  | I-RJ-MRTA-PMP-0053 | I-RJ-DENA-PMP-0006 | I-RJ-PASS-PMP-0007 | I-RJ-PASS-PMP-0008 | I-RJ-KESR-PMP-0018 | I-RJ-DDWN-PMP-0062 | I-RJ-MKRN-PMP-0030 | I-RJ-JAAW-PMP-0004 | I-RJ-JAAW-PMP-0005 | I-RJ-SNCE-PMP-0017 | I-RJ-BORA-PMP-0004 | I-RJ-BORA-PMP-0021 | I-RJ-BNML-PMP-0008 | I-RJ-JLOR-PMP-0016 | I-RJ-BAGA-PMP-0001 | I-RJ-BNML-PMP-0003 | I-RJ-SNCE-PMP-0005 | I-RJ-SNCE-PMP-0013 | I-RJ-SNCE-PMP-0014 | I-RJ-KDRD-PMP-0001 | I-RJ-SNCE-PMP-0020 | I-RJ-SNCE-PMP-0019 | Total Quantity | RATE AS PER SOW | AMOUNT
| Site Type |  | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT
| Sectors |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Item code | Description of Item | UOM
3367489 | CHRG BASE RADIO INST&COMS AZIMUTH | EA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  | 200
3367548 | CHRG LAYING-MULTIMODE FIBER CABLE | M | 5 | 5 | 5 | 5 | 5 | 5 | 50 | 5 | 10 | 60 | 5 | 50 | 5 | 5 | 5 | 5 | 100 | 5 | 50 | 5 | 50 | 50 |  | 5
3137158 | LAYING-2CX2.5SQMM POWER CABLE | M | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 150 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 50 | 50 | 50 | 50 | 50 |  | 12
3397253 | CHRG EXTRA TRANSPORT. > 50 KM (PICKUP | KM | 14 | 126 | 35 | 5 | 62 | 167 | 30 | 114 | 8 | 40 | 168 | 21 | 20 | 71 | 21 | 55 | 185 | 18 | 31 | 184 | 28 | 15 |  | 20
3397271 | CHRG TRANSPORT-UPTO 50KM-SCV-2-3SITE | EA | [23 empty] | 1500 | bar: 1 to Service Done To Date: 04-02-26 22
3367713 | CHRG ATP-11C - WIFI A6 DEPLOYMENT | EA | [23 empty] | 700 | bar: 1 to Service Done To Date: 04-02-26 22
3367739 | CHRG ATP-11A - WIFI A6 DEPLOYMENT | EA | [23 empty] | 700 | bar: 1 to Service Done To Date: 04-02-26 22
3317347 | SITC 1CX6 SQMM CU CBL YY FRLSH | M | [23 empty] | 68
3383067 | CHRG APPLY PUFF SEALENT AT CABLE ENTRY | EA | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 |  | 330
3269867 | TERMINATION OF CABLE 1CX6 SQMM Y | M | [23 empty] | 40
TOTAL
SIGN: |  | SIGN: | Service Done To Date: 04-02-26 14: SIGN:
|  | PROJECT-IN-CHARGE | Service Done To Date: 04-02-26 14: DEPLOYMENT HEAD
| MR. YUNUS KHAN |  | Service Done To Date: 04-02-26 14: MR. MANISH NAHAR
DATE: DATE: |  | DATE: | Service Done To Date: 04-02-26 14: DATE:

## BOQ
BOQ
Work Order No :P14/630330726
Contractor Name: DIGITCOM INDIA TECHNOLOGIES | [17 empty] | Work Order Dated: 03-10-2025
WO for Airspan A6 and C6 Radios for Airfiber
Service Done From Date: 30-01-26
Service Done To Date: 04-02-26
| Count - |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22
Code | Site ID -- |  | I-RJ-MRTA-PMP-0053 | I-RJ-DENA-PMP-0006 | I-RJ-PASS-PMP-0007 | I-RJ-PASS-PMP-0008 | I-RJ-KESR-PMP-0018 | I-RJ-DDWN-PMP-0062 | I-RJ-MKRN-PMP-0030 | I-RJ-JAAW-PMP-0004 | I-RJ-JAAW-PMP-0005 | I-RJ-SNCE-PMP-0017 | I-RJ-BORA-PMP-0004 | I-RJ-BORA-PMP-0021 | I-RJ-BNML-PMP-0008 | I-RJ-JLOR-PMP-0016 | I-RJ-BAGA-PMP-0001 | I-RJ-BNML-PMP-0003 | I-RJ-SNCE-PMP-0005 | I-RJ-SNCE-PMP-0013 | I-RJ-SNCE-PMP-0014 | I-RJ-KDRD-PMP-0001 | I-RJ-SNCE-PMP-0020 | I-RJ-SNCE-PMP-0019 | Total Quantity | RATE AS PER SOW | AMOUNT
| Site Type |  | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT | GBT
| Sectors |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1
Item code | Description of Item | UOM
3367489 | CHRG BASE RADIO INST&COMS AZIMUTH | EA | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  | 200
3367548 | CHRG LAYING-MULTIMODE FIBER CABLE | M | 5 | 5 | 5 | 5 | 5 | 5 | 50 | 5 | 10 | 60 | 5 | 50 | 5 | 5 | 5 | 5 | 100 | 5 | 50 | 5 | 50 | 50 |  | 5
3137158 | LAYING-2CX2.5SQMM POWER CABLE | M | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 150 | 50 | 50 | 50 | 50 | 50 | 50 | 100 | 50 | 50 | 50 | 50 | 50 |  | 12
3397253 | CHRG EXTRA TRANSPORT. > 50 KM (PICKUP | KM | 14 | 126 | 35 | 5 | 62 | 167 | 30 | 114 | 8 | 40 | 168 | 21 | 20 | 71 | 21 | 55 | 185 | 18 | 31 | 184 | 28 | 15 |  | 20
3397271 | CHRG TRANSPORT-UPTO 50KM-SCV-2-3SITE | EA | [23 empty] | 1500 | bar: 1 to Service Done To Date: 04-02-26 22
3367713 | CHRG ATP-11C - WIFI A6 DEPLOYMENT | EA | [23 empty] | 700 | bar: 1 to Service Done To Date: 04-02-26 22
3367739 | CHRG ATP-11A - WIFI A6 DEPLOYMENT | EA | [23 empty] | 700 | bar: 1 to Service Done To Date: 04-02-26 22
3317347 | SITC 1CX6 SQMM CU CBL YY FRLSH | M | [23 empty] | 68
3383067 | CHRG APPLY PUFF SEALENT AT CABLE ENTRY | EA | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 |  | 330
3269867 | TERMINATION OF CABLE 1CX6 SQMM Y | M | [23 empty] | 40
TOTAL
SIGN: |  | SIGN: | 11: SIGN:; Service Done To Date: 04-02-26 21: SIGN:
|  | PROJECT-IN-CHARGE | 11: DEPLOYMENT HEAD; Service Done To Date: 04-02-26 21: RJIO CTO
| MR. YUNUS KHAN |  | 11: MR. MANISH NAHAR; Service Done To Date: 04-02-26 21: MR.RAJEEV KUMAR GUPTA
DATE: DATE: |  | DATE: | 11: DATE:; Service Done To Date: 04-02-26 21: DATE:

## Declaration
DECLARATION STATEMENT
Name of Contractor | DIGITCOM INDIA TECHNOLOGIES
Authorised Signatory
Vendor Code | 3267708
Work Order No: | P14/630330726
SAP ID/WBS : | As per Annexture
Warehouse Location | JODHPUR
Declaration
We hereby certify that this Material Reconcilation Statement as on 30.03.2026 attached herein is certified and justified by Bills submited by Contractor for given Work Done on given site as per Work Order Issued.
22 SITES(A6)
Warehouse Incharge | Circle Project Head | Contractor | Remark
Checked By Material Coordinator | Through FC&A

## Reco
Name of Contractor |  | DIGITCOM INDIA TECHNOLOGIES | [7 empty] | R4G Project
WO No |  | P14/630330726
Site ID |  | As per attached Detail
WBS Code |  | As per attached Detail
Site Name |  | As per attached Detail
Warehouse Location |  | JODHPUR
Time Period |  | 30-JAN-26 TO 04-FEB-26
Material Reconciliation Statement
| Material Description | A6 FIXED WIRELESS WI-FI ACCESS POINT | Fiber Patchcord MM 5M | CPRI CABLE 50 MTR - (MULTIMODE) | EARTHING CLAMP | SFP MULTIMODE 1G 10 KM | SFP MULTIMODE 1G 10 KM | SFP MULTIMODE 1G 10 KM | SFP MULTIMODE 10G | MOUNTING BRACKET | MOUNTING BRACKET | INSTALLATION IRM KIT | INSTALLATION IRM KIT | POWR CABLE 50 MTR
| Material Code | 2002495907 | 2002503216 | 2002334231 | 2002269100 | 2002668786 | 2001649259 | 9500172828 | 2002668758 | 2002677184 | 2002669131 | 2002456956 | 2002475640 | 2002462695
A. | Receipt details as confirmed by Contractor:
1 | Received directly from Warehouse | 26 | 18 | 8 | 1 | 8 | 2 | 2 | 40 | 25 | 1 | 2 | 24 | 26
2 | Material received from other contractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total (1+2)
B. | Material Transferred to other contractors / returned to Warehouse | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Material Transferred to other contractors | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Material Returned to Warehouse (in line with MRN Guidelines) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total
C | Balance ( A - B )
D | CONSUMPTION
1 | Material Consumed |  |  |  | 5
2 | Wastage (max as per WO norms) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total -Actual consumption (1+2) |  |  |  | 5
E. | Excess consumption for which cost to be recovered from the Contractor (C-D) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Annexture
Annexture
Row Labels | I-RJ-MRTA-PMP-0053 | I-RJ-DENA-PMP-0006 | I-RJ-PASS-PMP-0007 | I-RJ-PASS-PMP-0008 | I-RJ-KESR-PMP-0018 | I-RJ-DDWN-PMP-0062 | I-RJ-MKRN-PMP-0030 | I-RJ-JAAW-PMP-0004 | I-RJ-JAAW-PMP-0005 | I-RJ-SNCE-PMP-0017 | I-RJ-BORA-PMP-0004 | I-RJ-BORA-PMP-0021 | I-RJ-BNML-PMP-0008 | I-RJ-JLOR-PMP-0016 | I-RJ-BAGA-PMP-0001 | I-RJ-BNML-PMP-0003 | I-RJ-SNCE-PMP-0005 | I-RJ-SNCE-PMP-0013 | I-RJ-SNCE-PMP-0014 | I-RJ-KDRD-PMP-0001 | I-RJ-SNCE-PMP-0020 | I-RJ-SNCE-PMP-0019 | Grand Total
2002495907 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  | A6 FIXED WIRELESS WI-FI ACCESS POINT
2002503216 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 2 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 0 | 0 |  | Fiber Patchcord MM 5M
2002334231 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 1 |  | CPRI CABLE 50 MTR - (MULTIMODE)
2002269100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | EARTHING CLAMP
2002668786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 2 | 0 | 0 | 2 |  | SFP MULTIMODE 1G 10 KM
2001649259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | SFP MULTIMODE 1G 10 KM
9500172828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | SFP MULTIMODE 1G 10 KM
2002668758 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 6 | 2 | 2 | 2 | 0 | 2 | 2 | 0 | 2 | 0 | 2 | 0 | 0 |  | SFP MULTIMODE 10G
2002677184 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 1 |  | MOUNTING BRACKET
2002669131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | MOUNTING BRACKET
2002456956 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | INSTALLATION IRM KIT
2002475640 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 0 | 1 |  | INSTALLATION IRM KIT
2002462695 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 1 |  | POWR CABLE 50 MTR
Grand Total